## Schemes completed
APPROVED LANGUISHING PROJECTS
COMPLETED PROJECTS
//LANGUISHING PROJECTS
| S. No | Mtg No | Date | LUP Code | Name of Project / Location | SS/ CRF | Sector | R&B / JKPCC | Divn | District | R&B Division | Nodal officer | AA Cost | Sanctioned Amount | Actual Date of start of project | Alloted Cost | Total funds released | Expdt incld deposit | Phy% by CE | Cumm Phy % | Pending with FD | Query | Funds released I | Date | Funds released II | Date | Funds released III | Date | Funds released IV | Date | Funds released V | Date | Funds released VI | Date | Funds released VII | Date | Total | SD | Saving | Target DOC | Completed in | Tender issuance date and numbers | PCC Month | Remarks
| 1 | I | 03.10.2018 | LUP0098 | Constr of 1x18 mtr span trussed girder Foot Bridge at Checkpora Aragam Bandipora | SS | Bridge | R&B | Kashmir | Bandipora | Bandipora | Hamid Ahmad Bhat |  | 82.93 | 2018-09-01 |  | 23.143 | 25.7142 | 100% | 40% |  |  | 23.143 | 2020-03-13 | [12 empty] | 23.143 | 2.5712 |  |  | 2020-09-01
| 2 | I | 03.10.2018 | LUP0099 | Const of 1x25 mtr span foot bridge at Athwathoo Bandipora | SS | Bridge | R&B | Kashmir | Bandipora | Bandipora | Hamid Ahmad Bhat |  | 86.71 | 2011-11-01 |  | 48.99 | 54.4328 | 100% | 80% |  |  | 48.99 | 2020-10-29 | [12 empty] | 48.99 | 5.4428 |  |  | 2020-08-01
| 3 | III | 24.10.2018 | LUP0761 | Const. of 1x11 mtr span plate girer motorable Bridge over Khundri Nallah at Peer Mohalla Erin Bandipora | SS | Bridge | R&B | Kashmir | Bandipora | Bandipora | Hamid Ahmad Bhat |  | 78.81 | 2018-09-01 |  | 64.276 | 71.4171 | 100% | 93% |  |  | 64.276 | 2020-07-29 | [12 empty] | 64.276 | 7.1411 |  |  | 2020-06-01
| 4 | V | 12.12.2018 | LUP1501 | Inner links at Kehnoosa | SS | Road | R&B | Kashmir | Bandipora | Bandipora | Hamid Ahmad Bhat |  | 215.93 | 2019-06-01 |  | 175.569 | 195.0747 | 100% | 100% |  |  | 111.276 | 2019-10-24 | 8.067 | 2020-09-03 | 54.194 | 2020-10-21 | 2.032 | 2020-12-31 | [6 empty] | 175.569 | 19.5057 |  |  | 2020-07-01
| 5 | I | 03.10.2018 | LUP0127 | Const of 1x22 mtr span steel girder bridge over Nallah at Pethgam Wagoora | SS | Bridge | R&B | Kashmir | Baramulla | Baramulla | Sheikh Basharat Hussain |  | 56.09 | 2011-05-01 |  | 50.003 | 55.5583 | 100% | 100% |  |  | 50.003 | 2019-11-26 | [12 empty] | 50.003 | 5.5553 | 0.53167 |  | 2019-20 | 112/8974-84/2018-19/Rnb/Bla dated 12-12-18
| 6 | I | 03.10.2018 | LUP0128 | Construction 1x120 mtr span trussed girder steel foot bridge over river Jehlum at Fish Market, Baramulla | SS | Bridge | R&B | Kashmir | Baramulla | Baramulla | Sheikh Basharat Hussain |  | 250 | 2015-05-01 |  | 222.715 | 247.4586 | 100% | 100% | 1.568 |  | 90.788 | 2020-01-20 | 62.121 | 2020-07-29 | 69.806 | 2021-02-05 | [8 empty] | 222.715 | 24.7436 |  |  | 2020-10-01
| 7 | III | 24.10.2018 | LUP0770 | Construction of road from Zandfaran to Gurivan | SS | Road | R&B | Kashmir | Baramulla | Baramulla | Sheikh Basharat Hussain | 400.15 | 156.64 | 2007-03-01 |  | 132.468 | 147.1852 | 100% | 100% |  |  | 104.18 | 2019-10-04 | 28.288 | 2021-02-19 | [10 empty] | 132.468 | 14.7172 |  |  | 2020-10-01
| 8 | III | 24.10.2018 | LUP0772 | Upgradation of Malpora to Larridora via Kawhar | SS | Road | R&B | Kashmir | Baramulla | Baramulla | Sheikh Basharat Hussain |  | 100.59 | 2010-10-01 |  | 85.829 | 95.3646 | 100% | 100% |  |  | 4.595 | 2019-09-25 | 69.452 | 2019-10-24 | 11.782 | 2020-10-21 | [8 empty] | 85.829 | 9.5356 | 5.2254 |  | 2020-08-01
| 9 | IV | 20.11.2018 | LUP1224 | Construction of 1x22 Mtr span steel girder bridge on Chanmohalla link road over existing nallah | SS | Bridge | R&B | Kashmir | Baramulla | Baramulla | Sheikh Basharat Hussain |  | 44.27 | 2010-10-01 |  | 30.38 | 33.7552 | 100% | 100% |  |  | 13.705 | 2019-10-18 | 12.395 | 2020-03-13 | 3.164 | 2020-08-20 | 1.116 | 2020-12-14 | [6 empty] | 30.38 | 3.3752 | 10.5148 |  | 2020-07-01
| 10 | IV | 20.11.2018 | LUP1225 | Construction of 1x20 Mtr span steel girder bridge over existing nallah at Bangdhara | SS | Bridge | R&B | Kashmir | Baramulla | Baramulla | Sheikh Basharat Hussain |  | 41.94 | 2010-10-01 |  | 37.746 | 41.9396 | 100% | 100% |  |  | 26.911 | 2019-09-04 | 10.835 | 2020-06-25 | [10 empty] | 37.746 | 4.1936 | 0.0004194 |  | 2019-20 | 110/8706-12/2018-19/Rnb/Bla dated 01-12-18
| 11 | IV | 20.11.2018 | LUP1226 | Construction of /Upgradation of road from Yedipora Hyderbeigh via Nillah Palpora to Wanigam | SS | Road | R&B | Kashmir | Baramulla | Baramulla | Sheikh Basharat Hussain |  | 167.57 | 2010-10-01 |  | 74.461 | 82.7336 | 100% | 100% |  |  | 5.463 | 2019-07-01 | 58.532 | 2019-09-05 | 10.466 | 2020-10-29 | [8 empty] | 74.461 | 8.2726 | 84.8364 |  | 2019-20
| 12 | VI | 28.02.2019 | LUP1901 | Const.of Bhaddu to Phongal Road | SS | Road | R&B | Jammu | Kathua | Basohli | Rajesh Kumar Sumbria | 177.24 | 152.36 | 02/2010 | 29.94 | 80.598 | 89.5524 | 100% | 78% |  |  | 26.9 | 2020-10-29 | 53.698 | 2021-01-28 | [10 empty] | 80.598 | 8.9544 |  | 2021-03-01 | 2020-12-01
| 13 | VI | 28.02.2019 | LUP1903 | Const. of Circular Road to Thantoo Kalai | SS | Road | R&B | Jammu | Kathua | Basohli | Rajesh Kumar Sumbria | 107.13 | 79.36 | 02/2010 | 15.53 | 58.805 | 65.3382 | 100% | 84% |  |  | 13.97 | 2019-12-17 | 44.835 | 2020-10-14 | [10 empty] | 58.805 | 6.5332 |  |  | 2020-09-01
| 14 | VI | 28.02.2019 | LUP1907 | Const. of Marta Nagrota to Pantair via Bari and Khlow road | SS | Road | R&B | Jammu | Kathua | Basohli | Rajesh Kumar Sumbria | 333 | 248.97 | 04/2003 | 242.49 | 217.75 | 241.942 | 100% | 100% |  |  | 24.08 | 2019-10-24 | 14.055 | 2019-12-17 | 153.469 | 2020-03-31 | 26.146 | 2020-08-21 | [6 empty] | 217.75 | 24.192 | 7.028 |  | 2019-20 | e-NIT No.93 of 2018-19 dated 06.03.2019 & e-NIT No.17 of 2019-20 dated 10.06.2019
| 15 | VI | 28.02.2019 | LUP1910 | Imp./Upgradation of Parnalla Seri Mooni Plail Banhore road. | SS | Road | R&B | Jammu | Kathua | Basohli | Rajesh Kumar Sumbria | 585.74 | 580.74 | 03/2004 | 388.4 | 369.925 | 411.0237 | 100% | 63% |  |  | 186.795 | 2019-10-24 | 61.576 | 2020-03-31 | 69.997 | 2020-08-21 | 51.557 | 2020-10-21 | [6 empty] | 369.925 | 41.0987 |  | 2020-12-01 | 2021-01-01
| 16 | I | 03.10.2018 | LUP0072 | Const. of motorable Bridge over Chilli nallah in Km 4th RD 50-100 of Gajote to Dugli road. | SS | Bridge | R&B | Jammu | Doda | Bhaderwah | Abdul Ghani Jagil | 199.9 | 90.9 | 11/2015 | 90.9 | 62.874 | 69.8593 | 100% | 85% |  |  | 32.625 | 2019-12-24 | 30.249 | 2020-06-23 | [10 empty] | 62.874 | 6.9853 |  | 2020-12-01 | 2020-12-01
| 17 | I | 03.10.2018 | LUP0073 | Const. of motorable Bridge over Jathi nallah Gajote in Km 2nd RD 275 - 3235 of Gajote to Dugli road (34 Mtr span) | SS | Bridge | R&B | Jammu | Doda | Bhaderwah | Abdul Ghani Jagil | 188.2 | 68.2 | 03/2016 | 68.2 | 39.15 | 43.4996 | 100% | 95% |  |  | 13.41 | 2020-03-31 | 20.79 | 2020-09-09 | 4.95 | 2020-10-01 | [8 empty] | 39.15 | 4.3496 |  | 2021-02-01 | 2020-12-01
| 18 | IV | 20.11.2018 | LUP1235 | Const. of 54 Mtr span Motorable through Type Single Truss Bridge over Neeru Nallah at Kulsari Bhaderwah | SS | Bridge | JKPCC | Jammu | Doda | Bhaderwah | Abdul Ghani Jagil | 225.85 | 22.95 | 4/2010 | Allotment U/Process | 0 | 0 | 100% | [17 empty] | 0 | 0 |  |  | 2020-08-01
| 19 | IV | 20.11.2018 | LUP1236 | Const. of 40 mtr span Motrable through Type Single Truss Bridge over Nehrru Nallah at Dheraja Bhaderwah. | SS | Bridge | JKPCC | Jammu | Doda | Bhaderwah | Abdul Ghani Jagil | 184.5 | 115.5 | 04/2010 | Tender U/Process | 0 | 0 | 100% | [17 empty] | 0 | 0 |  |  | 2020-10-01
| 20 | IV | 20.11.2018 | LUP1240 | Const. of road from Launcher Morh to Akhrote Bagh | SS | Road | R&B | Jammu | Doda | Bhaderwah | Abdul Ghani Jagil | 150 | 60 | 03/2013 | 38.97 | 35.633 | 39.5918 | 100% | 100% |  |  | 24.408 | 2019-12-24 | 6.846 | 2020-06-23 | 4.379 | 2020-09-09 | [8 empty] | 35.633 | 3.9588 | 20.4082 |  | 2020-06-01
| 21 | IV | 20.11.2018 | LUP1241 | Gatha Gawari Hospital road | SS | Road | R&B | Jammu | Doda | Bhaderwah | Abdul Ghani Jagil | 160.36 | 39.74 | 03/2010 | 41 | 29.833 | 33.1474 | 100% | 100% |  |  | 27.549 | 2019-12-24 | 2.284 | 2020-08-21 | [10 empty] | 29.833 | 3.3144 | 6.5926 |  | 2019-20 | No:- 60 of 2018-19, Dated:- 20-09-2018 issue under No:- 2798-2819/cs Dated:- 20-09-2018 and No:- 97 of 2018-19, Dated:- 17-12-2018 issue under No:- 4616-37/cs Dated:- 17-12-2018
| 22 | VI | 28.02.2019 | LUP1853 | Const. of Chakka to Upper Dandi link road KM 1st RD (0-1000) District Doda Length 1kms | SS | Road | R&B | Jammu | Doda | Bhaderwah | Abdul Ghani Jagil | 145 | 45.5 | 06/2009 | 45.5 | 37.455 | 41.6163 | 100% | 100% |  |  | 34.335 | 2019-12-24 | 3.12 | 2020-08-21 | [10 empty] | 37.455 | 4.1613 | 3.8837 |  | 2020-06-01
| 23 | I | 03.10.2018 | LUP0088 | Construction of 1x36 Mtr Span Steel girder Foot bridge on Nallah Sukhnag at Peth Kanihama Hanjibugh | SS | Bridge | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali |  | 90.12 | 2015-07-01 |  | 41.846 | 46.4951 | 100% | 66% |  |  | 41.846 | 2019-07-09 | [12 empty] | 41.846 | 4.6491 |  |  | 2020-09-01 |  | 2020-09-01
| 24 | I | 03.10.2018 | LUP0090 | Const of 2x20 mtr span steel girder bridge on Hazarpora Kandhama link road at Khag | SS | Bridge | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali | 363.82 | 165.88 | 2010-03-01 |  | 112.095 | 124.5488 | 100% | 99% |  |  | 76.461 | 2019-07-03 | 8.78 | 2019-10-23 | 6.776 | 2020-02-03 | 18.612 | 2020-07-27 | 1.466 | 2020-10-29 |  |  |  |  | 112.095 | 12.4538 |  |  | 2019-20 |  | 2020-03-01
| 25 | I | 03.10.2018 | LUP0091 | Constt. of 3x27 mtr span steel trussed girder bridge over Nallah Shaliganga on at Dragger Hill Kachwari road | SS | Bridge | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali | 784.21 | 513.869 | 2013-06-01 |  | 426.064 | 473.3997 | 100% | 96% |  |  | 158.437 | 2019-06-12 | 95.559 | 2019-08-23 | 114.501 | 2019-09-25 | 13.901 | 2019-10-18 | 43.666 | 2020-07-07 |  |  |  |  | 426.064 | 47.3357 |  |  | 2020-06-01
| 26 | III | 24.10.2018 | LUP0775 | Constr. Of 1x18 mtr span steel girder Bridge with RCC slab deck in Km 5th at Sebdan over Ahaji Canal connecting to Bathar Railway Road | SS | Bridge | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali | 205.75 | 118.25 | 2013-06-01 |  | 99.156 | 110.1722 | 100% | 97% |  |  | 49.449 | 2019-07-09 | 7.569 | 2019-10-18 | 32.655 | 2020-10-29 | 9.483 | 2020-01-11 | [6 empty] | 99.156 | 11.0162 |  |  | 2019-20 |  | 2020-08-01
| 27 | III | 24.10.2018 | LUP0776 | Constr of 1x24 mtr span steel bridge at Karipora (Intermediate lane truss girder bridge) | SS | Bridge | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali |  | 136.27 | 2014-07-01 |  | 86.215 | 95.7935 | 100% | 76% |  |  | 33.207 | 2019-07-09 | 53.008 | 2020-01-14 | [10 empty] | 86.215 | 9.5785 |  |  | 2019-20 |  | 2020-03-01
| 28 | IV | 20.11.2018 | LUP1228 | Construction of 1x10 Mtr span steel decked bridge on Wamin Nallah at Brass Gujjar Basti | SS | Bridge | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali |  | 44.68 | 2017-10-01 |  | 40.005 | 44.4496 | 100% | 100% |  |  | 15.705 | 2019-07-09 | 24.3 | 2019-08-23 | [10 empty] | 40.005 | 4.4446 | 0.23044 |  | 2019-20 |  | 2020-03-01
| 29 | IV | 20.11.2018 | LUP1230 | Construction of 1x22 Mtr span steel girder bridge at Rakhi Wachoo Khansahib | SS | Bridge | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali |  | 173.72 | 2013-08-01 |  | 138.062 | 153.4007 | 100% | 100% | 18.286 |  | 48.337 | 2019-07-08 | 18.584 | 2020-02-03 | 71.141 | 2020-07-27 | [8 empty] | 138.062 | 15.3387 |  | 2020-12-01 | 2020-12-01 |  | 2020-12-01
| 30 | V | 12.12.2018 | LUP1508 | Construction of Kremshore Dreygam and Dreygam Banderpora road | SS | Road | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali |  | 300.45 | 2016-07-01 |  | 269.733 | 299.7003 | 100% | 100% |  |  | 103.446 | 2019-07-16 | 88.564 | 2019-09-18 | 77.723 | 2019-10-18 | [8 empty] | 269.733 | 29.9673 | 0.74966 |  | 2019-20 |  | 2020-03-01
| 31 | V | 12.12.2018 | LUP1509 | Construction of inner links of Village Suresh & Larkipora Khag | SS | Road | R&B | Kashmir | Budgam | Budgam | Asgar Ali Watali |  | 273.19 | 2017-05-01 |  | 169.864 | 188.7359 | 100% | 70% |  |  | 147.615 | 2019-10-24 | 22.249 | 2019-12-17 | [10 empty] | 169.864 | 18.8719 |  |  | 2020-06-01 |  | 2020-03-01
| 32 | I | 03.10.2018 | LUP0027 | Const of 15mtr span single lane RCC bridge over Palyal Nallah onkotli Palyal link road at Chowadhi including approach road and protection work | SS | Bridge | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 86 | 61 | 03/2018 | 57.75 | 37.778 | 41.9751 | 100% | 62% |  |  | 9.518 | 2019-06-12 | 15.489 | 2019-07-03 | 12.771 | 2019-10-10 | [8 empty] | 37.778 | 4.1971 |  |  | 2019-20
| 33 | I | 03.10.2018 | LUP0028 | Const. of 15.30 mtr span vented causeway near Temple/ Little Flower School at Greater kailash | SS | Bridge | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 74.5 | 43.44 | 09/2012 | 50.39 | 38.889 | 43.2096 | 100% | 100% |  |  | 33.174 | 2019-09-18 | 5.715 | 2020-01-27 | [10 empty] | 38.889 | 4.3206 | 0.23043 |  | 2019-20
| 34 | II | 10.10.2018 | LUP0469 | Const of 33m concrete motorable bridge over Nallah between Sec. A & G Sainik Colony Adjacent to Railway Track | SS | Bridge | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 155 | 120 | 03/2018 | 112.47 | 107.913 | 119.9021 | 100% | 100% |  |  | 35.037 | 2019-09-25 | 64.15 | 2020-01-27 | 8.726 | 2020-08-03 | [8 empty] | 107.913 | 11.9891 | 0.097866 |  | 2020-06-01
| 35 | III | 24.10.2018 | LUP0781 | Const. of road from Bund-Khandyal-Lalyal | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 174 | 82.49 | 03/2016 | 65.81 | 66.111 | 73.4559 | 100% | 100% |  |  | 50.13 | 2019-07-23 | 7.209 | 2020-03-31 | 2.472 | 2020-08-11 | 6.3 | 2020-08-21 | [6 empty] | 66.111 | 7.3449 | 9.0341 |  | 2019-20
| 36 | III | 24.10.2018 | LUP0782 | Const. of road from Milk Derian Balla enclave to Rama Channi Masjid Mohalla (L- 2.00 kms) upto ITBP Camp including const. of vented causeway | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 72 | 57 | 02/2017 | 57 | 46.778 | 51.975 | 100% | 100% |  |  | 19.674 | 2019-06-03 | 24.98 | 2019-07-09 | 2.124 | 2020-01-01 | [8 empty] | 46.778 | 5.197 | 5.025 |  | 2019-20
| 37 | III | 24.10.2018 | LUP0783 | Const. of road (double lane) to Public Park at Kharian via NIITS College. | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 291.6 | 151.6 | 04/2008 | 130.09 | 104.288 | 115.8744 | 100% | 95% |  |  | 92.745 | 2020-02-27 | 8.226 | 2020-08-21 | 3.317 | 2020-10-21 | [8 empty] | 104.288 | 11.5864 |  |  | 2020-10-01
| 38 | III | 24.10.2018 | LUP0785 | Const. of road from Kotli Galabana to Kullian Khalsa road in km 3rd via Bhure-De-Kothey | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 182.42 | 157.4 | 02/2017 | 116.93 | 35.496 | 39.4396 | 100% | 40% |  |  | 22.743 | 2019-12-09 | 12.753 | 2020-10-29 | [10 empty] | 35.496 | 3.9436 |  |  | 2020-10-01
| 39 | III | 24.10.2018 | LUP0790 | Const. of 18 Mtr span Steel Girder Bridge at Bhore Camp Jammu | SS | Bridge | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 193.2 | 83.2 | 07/2014 | 73.12 | 60.839 | 67.5982 | 100% | 100% |  |  | 30.897 | 2019-06-12 | 28.125 | 2019-09-09 | 1.817 | 2020-08-11 | [8 empty] | 60.839 | 6.7592 | 15.6018 |  | 2019-20
| 40 | V | 12.12.2018 | LUP1515 | Roads in Sainik Colony | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 1091.91 | 383.91 | 06/2009 | 385.29 | 344.682 | 382.9762 | 100% | 100% |  |  | 216 | 2019-10-24 | 4.428 | 2020-02-14 | 124.254 | 2020-06-25 | [8 empty] | 344.682 | 38.2942 | 0.93383 |  | 2019-20
| 41 | V | 12.12.2018 | LUP1516 | Const of Road from Bathindi to Ratti Sarari Vai Bermini | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 430 | 197.22 | 02/2007 | 197.22 | 140.32 | 155.9096 | 100% | 97% |  |  | 85.86 | 2019-09-04 | 31.455 | 2019-10-11 | 2.966 | 2020-06-25 | 4.028 | 2020-10-13 | 16.011 | 2020-12-15 |  |  |  |  | 140.32 | 15.5896 |  |  | 2019-20
| 42 | VI | 28.02.2019 | LUP1862 | Const. of various links/approach road to Jeevan Nagar Murallian Miran Sahib road Jammu | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 344.79 | 293.79 | 03/2013 | 291.34 | 259.018 | 287.7949 | 100% | 100% |  |  | 188.665 | 2019-09-18 | 1.107 | 2019-10-24 | 9.402 | 2020-01-01 | 27.864 | 2020-02-14 | 4.959 | 2020-07-07 | 19.143 | 2020-08-03 | 7.878 | 2020-08-21 | 259.018 | 28.7769 | 5.9951 |  | 2019-20
| 43 | VI | 28.02.2019 | LUP1864 | Roads in Digiana | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 817 | 236.03 | 07/2009 | 235.67 | 209.802 | 233.111 | 100% | 100% |  |  | 77.787 | 2019-12-17 | 89.374 | 2020-07-29 | 27.098 | 2020-08-21 | 9.018 | 2020-12-19 | 6.525 | 2021-02-10 |  |  |  |  | 209.802 | 23.309 |  |  | 2020-10-01
| 44 | VI | 28.02.2019 | LUP1865 | Const. of road form Fatwal to chumbian Panditian L=1 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 57.6 | 47.6 | 03/2014 | 47.6 | 42.804 | 47.5595 | 100% | 100% |  |  | 40.059 | 2020-01-14 | 1.71 | 2020-08-03 | 1.035 | 2020-08-21 | [8 empty] | 42.804 | 4.7555 | 0.040476 |  | 2019-20
| 45 | VI | 28.02.2019 | LUP1866 | Imp./Upgradation of link road to Bishnah Ashram W. No 02 upto to KC Morh Bishnah L=1.20 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 103.8 | 86.8 | 06/2014 | 86.8 | 74.25 | 82.4992 | 100% | 100% |  |  | 74.25 | 2020-01-14 | [12 empty] | 74.25 | 8.2492 | 4.3008 |  | 2019-20
| 46 | VI | 28.02.2019 | LUP1867 | Const. of Road from Nandpur to Pindi Charkan Via Duali Khui in Km 3rd Rd 800 -1000 km 4th &5th L=22 mtrs | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 154.5 | 81 | 02/2010 | 80.83 | 66.488 | 73.8748 | 100% | 100% |  |  | 58.707 | 2020-01-01 | 4.68 | 2020-07-27 | 3.101 | 2020-08-11 | [8 empty] | 66.488 | 7.3868 | 7.1252 |  | 2019-20
| 47 | VI | 28.02.2019 | LUP1868 | Const. of Road from Palli to Chak Avtara L=3 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 156.8 | 99.8 | 03/2010 | 99.8 | 86.522 | 96.1346 | 100% | 100% |  |  | 79.254 | 2020-01-27 | 7.268 | 2020-08-11 | [10 empty] | 86.522 | 9.6126 | 3.6654 |  | 2019-20
| 48 | VI | 28.02.2019 | LUP1869 | Const. of Road at Sarore along Distributory No. 3 L=2.40 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 122.5 | 83.24 | 03/2010 | 83.24 | 72.09 | 80.0992 | 100% | 100% |  |  | 72.09 | 2019-12-17 | [12 empty] | 72.09 | 8.0092 | 3.1408 |  | 2019-20
| 49 | VI | 28.02.2019 | LUP1870 | Const. of link road from Sai Khurd to Sardari Camp (Birdhipur Bana) L=2 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 149.7 | 86.7 | 02/2010 | 86.7 | 56.592 | 62.8794 | 100% | 94% |  |  | 49.086 | 2020-01-27 | 3.663 | 2020-08-21 | 3.843 | 2020-12-15 | [8 empty] | 56.592 | 6.2874 |  |  | 2020-09-01
| 50 | VI | 28.02.2019 | LUP1871 | Cosnt. Of Road from Chak Keema to Karyal L=2 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 79.5 | 54.86 | 02/2010 | 54.79 | 47.943 | 53.2695 | 100% | 98% |  |  | 47.943 | 2020-12-19 | [12 empty] | 47.943 | 5.3265 |  | 2021-03-01 | 2020-12-01
| 51 | VI | 28.02.2019 | LUP1872 | Const. of link road from Kalapul Satrayian to Chowala Fattu Chak L=1.15 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 135.2 | 85.2 | 03/2010 | 72.38 | 47.695 | 52.9939 | 100% | 80% |  |  | 11.218 | 2020-06-25 | 27.657 | 2020-07-27 | 8.82 | [9 empty] | 47.695 | 5.2989 |  |  | 2020-11-01
| 52 | VI | 28.02.2019 | LUP1873 | Const. of Road form Mana to Shamshan Ghat L=2.10 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 157.5 | 116.5 | 02/2013 | 103.85 | 66.807 | 74.2293 | 100% | 85% |  |  | 9.198 | 2019-12-17 | 55.26 | 2020-07-27 | 2.349 | 2020-01-16 | [8 empty] | 66.807 | 7.4223 |  |  | 2020-10-01
| 53 | VI | 28.02.2019 | LUP1874 | Const. of Road from Talli Morh to Darsopur Ganda L=1.50 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 99.5 | 70.5 | 01/2010 | 70.5 | 37.157 | 41.2851 | 100% | 74% |  |  | 33.912 | 2020-02-06 | 3.245 | 2020-06-25 | [10 empty] | 37.157 | 4.1281 |  |  | 2020-10-01
| 54 | VI | 28.02.2019 | LUP1875 | Const. of Road from Gondla to Shamshan Ghat (Village Agwan) L=1.75 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 149.6 | 100.1 | 02/2010 | 89.76 | 51.129 | 56.8094 | 100% | 83% |  |  | 38.277 | 2020-08-21 | 11.763 | 2020-10-01 | 1.089 | 2021-02-12 | [8 empty] | 51.129 | 5.6804 |  |  | 2020-10-01
| 55 | VI | 28.02.2019 | LUP1876 | Const. of link road from Baspur to Samka (Suchetgarh Constituency L=1.80 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 187.35 | 123.35 | 02/2009 | 122.36 | 75.996 | 84.4392 | 100% | 85% |  |  | 58.68 | 2020-02-27 | 2.448 | 2020-09-18 | 14.868 | 2020-10-29 | [8 empty] | 75.996 | 8.4432 |  |  | 2020-10-01
| 56 | VI | 28.02.2019 | LUP1877 | Imp/ Upgradation of link road Nari Khaper L=1.10 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 71 | 50 | 03/2010 | 48.01 | 24.759 | 27.5097 | 100% | 76% |  |  | 19.323 | 2020-08-11 | 4.347 | 2020-08-21 | 1.089 | 2020-10-01 | [8 empty] | 24.759 | 2.7507 |  | 2020-12-01 | 2020-12-01
| 57 | VI | 28.02.2019 | LUP1878 | Const. of Internal links at Dhyansar L=2.50 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 125.6 | 87.1 | 01/2010 | 87.1 | 72.54 | 80.5992 | 100% | 100% |  |  | 72.54 | 2019-12-17 | [12 empty] | 72.54 | 8.0592 | 6.5008 |  | 2019-20
| 58 | VI | 28.02.2019 | LUP1879 | Imp/ Upgradation of Road from Krishna Nagar to Gazian (Muralian Upto Shamshan Ghat ) L=1 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 150.85 | 41.85 | 03/2010 | 115.46 | 29.822 | 33.1352 | 100% | 100% |  |  | 5.135 | 2020-01-14 | 20.952 | 2020-02-06 | 2.556 | 2020-08-21 | 1.179 | 2020-09-18 | [6 empty] | 29.822 | 3.3132 | 8.7148 |  | 2020-07-01
| 59 | VI | 28.02.2019 | LUP1880 | Const. of Road from Salehar to Chak Majra L- 3 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 129.5 | 115.85 | 10/2009 | 69.34 | 99.747 | 110.8289 | 100% | 97% |  |  | 99.747 | 2020-12-19 | [12 empty] | 99.747 | 11.0819 |  | 2020-12-01 | 2020-12-01
| 60 | VI | 28.02.2019 | LUP1881 | Const. of Road from Kothi Morh to Lala Chak Road at RD 2-450 on Bari Brahmana Bishnah Road L=1.90 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 180.75 | 69.5 | 07/2010 | 105.72 | 62.442 | 69.3793 | 100% | 100% |  |  | 53.901 | 2019-12-17 | 3.132 | 2020-08-21 | 5.409 | 2020-09-18 | [8 empty] | 62.442 | 6.9373 | 0.12069 |  | 2020-07-01
| 61 | VI | 28.02.2019 | LUP1882 | Const. of link road from Biaspur Parlah to Talad road L=1.40 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 187.55 | 118.25 | 09/2008 | 109.69 | 79.435 | 88.2602 | 100% | 100% |  |  | 22.635 | 2019-10-11 | 35.343 | 2020-02-03 | 5.427 | 2020-03-04 | 5.847 | 2020-07-07 | 1.71 | 2020-09-18 | 8.473 | 2020-10-21 |  |  | 79.435 | 8.8252 | 29.9898 |  | 2020-09-01
| 62 | VI | 28.02.2019 | LUP1883 | Const./ Extension of Road from Kotli Charkan to Byepass Road Bishnah via Dhinday Khurd including links L-2 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 172.55 | 126.55 | 06/2013 | 129.2 | 87.692 | 97.4346 | 100% | 90% |  |  | 10.805 | 2020-01-01 | 56.664 | 2020-03-12 | 3.096 | 2020-05-23 | 2.349 | 2020-08-11 | 9.153 | 2020-10-01 | 5.625 | 2020-01-12 |  |  | 87.692 | 9.7426 |  |  | 2020-10-01
| 63 | VI | 28.02.2019 | LUP1884 | Const. of Road from Tanda to Chowala Fattu Chak L 3 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 239.7 | 132.55 | 09/2010 | 93.05 | 109.972 | 122.1899 | 100% | 100% |  |  | 98.051 | 2020-01-01 | 6.327 | 2020-08-11 | 3.537 | 2020-08-21 | 2.057 | 2020-10-01 | [6 empty] | 109.972 | 12.2179 | 10.3601 |  | 2020-06-01
| 64 | VI | 28.02.2019 | LUP1886 | Imp./upgradation and strengthening of Road from Pindi Sarochan to Garore Nallah L=0.96 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 91.35 | 95 | 11/2010 | 66.19 | 58.243 | 64.7138 | 100% | 100% |  |  | 13.451 | 2019-12-09 | 25.776 | 2020-02-03 | 12.108 | 2020-02-14 | 5.774 | 2020-07-07 | 1.134 | 2020-08-21 |  |  |  |  | 58.243 | 6.4708 | 30.2862 |  | 2020-08-01
| 65 | VI | 28.02.2019 | LUP1887 | Const. o Road from Deoli Preet Nagar to Shamshan Ghat L=1.80 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 127.25 | 66.35 | 12/2010 | 110.96 | 40.923 | 45.4695 | 100% | 80% |  |  | 40.923 | 2020-12-19 | [12 empty] | 40.923 | 4.5465 |  |  | 2020-10-01
| 66 | VI | 28.02.2019 | LUP1888 | Const. of link road from Devigarh to Jobowal L 2.20 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 133 | 114.75 | 07/2015 | 96.95 | 90.657 | 100.729 | 100% | 100% |  |  | 82.476 | 2019-12-17 | 5.625 | 2020-03-16 | 2.556 | 2020-08-21 | [8 empty] | 90.657 | 10.072 | 14.021 |  | 2020-07-01
| 67 | VI | 28.02.2019 | LUP1889 | Const. of Road from Makhanpur to Pasgal L 2.50 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 150.1 | 97 | 11/2010 | 92.33 | 85.446 | 94.9391 | 100% | 99% |  |  | 85.446 | 2020-12-19 | [12 empty] | 85.446 | 9.4931 |  |  | 2020-10-01
| 68 | VI | 28.02.2019 | LUP1890 | Const. of Road from Palli to Bhatyari via Kanhal L 3 kms | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 217.1 | 92.6 | 09/2010 | 179.25 | 79.416 | 88.2391 | 100% | 97% |  |  | 79.416 | 2020-07-27 | [12 empty] | 79.416 | 8.8231 |  |  | 2020-09-01
| 69 | VII | 02.03.2019 | LUP2499 | Imp./upgd. of roads in Shastri Nagar including drain, metalling in sector 1 & 2 at Sanjay Nagar. | SS | Road | R&B | Jammu | Jammu | CD 1st Jmu | Er.Parvez Malik | 853.56 | 398.06 | 09/2010 | 397.57 | 344.088 | 382.3162 | 100% | 100% | 5.597 |  | 104.355 | 2020-01-01 | 102.582 | 2020-02-03 | 19.458 | 2020-03-04 | 59.31 | 2020-07-30 | 25.119 | 2020-08-21 | 16.389 | 2020-12-18 | 16.875 | 2020-12-19 | 344.088 | 38.2282 |  |  | 2020-10-01
| 70 | IV | 20.11.2018 | LUP1270 | Construction of 4.75 Mtr span RCC culvert at Novbugh Gulab Bagh including construction of protection works and development of approaches | SS | Road | R&B | Kashmir | Srinagar | CD 1st Sgr | Ajit Singh Chopra |  | 124.36 | 2017-12-01 |  | 111.785 | 124.2043 | 100% | 100% |  |  | 39.848 | 2019-07-01 | 60.813 | 2019-12-09 | 11.124 | 2020-07-27 | [8 empty] | 111.785 | 12.4193 | 0.15569 |  | 2019-20 | 6/e-tendering/CD-1st/441-59 dated 18-04-17, 127 / CD-1st/13513-32 dated 17-03-18
| 71 | III | 24.10.2018 | LUP0786 | Imprvtt./ Upgd of road from Kangrail Majali road to Ratti Chappri. | SS | Road | R&B | Jammu | Jammu | CD 2nd Jmu | Rajesh Bhagat | 105.28 | 105.28 | 07/2006 | 69.52 | 61.799 | 68.6649 | 100% | 100% |  |  | 44.267 | 2019-10-24 | 17.397 | 2020-07-27 | 0.135 | 2020-10-21 | [8 empty] | 61.799 | 6.8659 | 36.6151 |  | 2019-20 | 144 of 2018-19 dated 31-12-18
| 72 | III | 24.10.2018 | LUP0787 | Imprvtt./ Upgd of road from main road Jandyal to Tower road via Bhupa Talab Beri Chapri Ranjan. | SS | Road | R&B | Jammu | Jammu | CD 2nd Jmu | Rajesh Bhagat | 87.5 | 87.5 | 08/2005 | 55.77 | 47.907 | 53.2295 | 100% | 89% |  |  | 36.009 | 2019-12-17 | 11.898 | 2020-01-12 | [10 empty] | 47.907 | 5.3225 |  |  | 2020-10-01
| 73 | IV | 20.11.2018 | LUP1245 | Impvt. And Upgd. of link road from Beri Chapri to Mera Dabbar Block | SS | Road | R&B | Jammu | Jammu | CD 2nd Jmu | Rajesh Bhagat | 188 | 161 | 10/2008 | 102.28 | 90.194 | 100.2146 | 100% | 100% |  |  | 25.61 | 2019-10-11 | 60.453 | 2020-02-27 | 4.131 | 2020-10-29 | [8 empty] | 90.194 | 10.0206 | 60.7854 |  | 2019-20 | 145 of 2018-19 dated 31-12-18
| 74 | IV | 20.11.2018 | LUP1246 | Cosnt. of Road Bajalta Peer Baba including link of Mohallah Mohd Ali | SS | Road | R&B | Jammu | Jammu | CD 2nd Jmu | Rajesh Bhagat | 518.2 | 461.2 | 08/2010 | 260 | 238.847 | 265.3829 | 100% | 100% |  |  | 82.787 | 2019-10-11 | 48.051 | 2020-02-06 | 78.804 | 2020-07-27 | 29.205 | 2020-01-11 | [6 empty] | 238.847 | 26.5359 |  |  | 2020-10-01
| 75 | IV | 20.11.2018 | LUP1247 | Imp. /Up-gradation of Road from Sarah sandori | SS | Road | R&B | Jammu | Jammu | CD 2nd Jmu | Rajesh Bhagat | 453.5 | 326.5 | 08/2010 | 198 | 191.007 | 212.2279 | 100% | 100% |  |  | 103.14 | 2019-11-26 | 84.132 | 2020-02-06 | 3.735 | 2020-01-11 | [8 empty] | 191.007 | 21.2209 |  |  | 2019-20 | 146 of 2018-19 dated 01-01-20
| 76 | I | 03.10.2018 | LUP0031 | Const. of Bridge over Kanah Nallah Seoni to Lale Da Chabara | SS | Bridge | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 252 | 236 | 05/2011 | 236 | 212.337 | 235.9276 | 100% | 100% |  |  | 88.821 | 2019-12-17 | 60.201 | 2020-03-13 | 63.315 | 2020-09-03 | [8 empty] | 212.337 | 23.5906 | 0.072359 |  | 2020-08-01
| 77 | I | 03.10.2018 | LUP0032 | Const of Multi Span Box culvert on Pouni Chak to Akalpur Road with Approaches | SS | Bridge | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 100 | 35 | 05/2010 | 35 | 29.7 | 32.9997 | 100% | 97% |  |  | 29.7 | 2019-12-09 | [12 empty] | 29.7 | 3.2997 |  |  | 2019-20 | No.110 of 2017-18 Dt.08-09-2017
| 78 | I | 03.10.2018 | LUP0033 | 13 mtr span RCC culvert on link road from Nai Basti to Govt. Middle school Lower Muthi Jammu | SS | Bridge | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 40 | 32 | 06/2017 | 21.78 | 12.438 | 13.8199 | 100% | 58% |  |  | 12.438 | 2020-03-31 | [12 empty] | 12.438 | 1.3819 |  |  | 2019-20 | No. 219 of 207-18 Dt.12-01-2018
| 79 | I | 03.10.2018 | LUP0034 | Const . Of 26.70 mtr span Multi box Vented Causeway over Choi Nallah at Dhateryal at Village Halque (Bl | SS | Bridge | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 235.11 | 146.61 | 05/2011 | 99 | 87.928 | 97.6968 | 100% | 100% |  |  | 36.72 | 2019-10-24 | 51.208 | 2021-02-10 | [10 empty] | 87.928 | 9.7688 |  |  | 2019-20
| 80 | I | 03.10.2018 | LUP0035 | Const .of 27.70 mtr span vneted causeway with 5 nos. Vents (5.0 m X 5.0 ) on road from Ghari to Ladore Block Marh Jammu | SS | Bridge | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 115 | 85 | 06/2017 | 72.42 | 75.473 | 83.8581 | 100% | 100% |  |  | 65.178 | 2019-07-16 | 10.295 | 2019-12-09 | [10 empty] | 75.473 | 8.3851 | 1.1419 |  | 2019-20 | E-231 of 2017-18 Dt.08-03-2018
| 81 | III | 24.10.2018 | LUP0789 | Const. of road from 4th Tawi Bridge to Karnaile Chak | SS | Road | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 214.25 | 70.35 | 07/2015 | 67 | 59.376 | 65.9727 | 100% | 100% |  |  | 18.333 | 2019-09-04 | 28.76 | 2020-03-06 | 12.283 | 2020-07-30 | [8 empty] | 59.376 | 6.5967 | 4.3773 |  | 2019-20 | NIT No.113 of 2017-18 Dt.14-09-2017
| 82 | V | 12.12.2018 | LUP1513 | Up-gradation of Dori Degair Road from Single Lane to Double Lane | SS | Road | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 404 | 291 | 05/2011 | 228.43 | 229.194 | 254.6575 | 100% | 100% |  |  | 49.878 | 2019-12-09 | 80.793 | 2020-07-27 | 98.523 | 2020-12-31 | [8 empty] | 229.194 | 25.4635 |  |  | 2020-07-01
| 83 | VII | 02.03.2019 | LUP2525 | Const. of link road from Pannu the Hatti road to (Sualpur road) to H/O Sh. Ram lal Sharma marh | SS | Road | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 95.26 | 72.26 | 06/2009 | 68 | 51.05 | 56.7217 | 100% | 88% |  |  | 51.05 | 2020-04-15 | [12 empty] | 51.05 | 5.6717 |  |  | 2019-20 | E-66 of 2019-20 Dt.27-09-2019
| 84 | VII | 02.03.2019 | LUP2526 | Const. of road from dub soodan to rakh kharoon | SS | Road | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 114.96 | 58.96 | 06/2009 | 54.85 | 40.365 | 44.8496 | 100% | 89% |  |  | 40.365 | 2020-03-31 | [12 empty] | 40.365 | 4.4846 |  |  | 2019-20 | No. 69 of 2019-20 Dt.01-10-2019
| 85 | VII | 02.03.2019 | LUP2528 | Const. of road from Ganeshu chak to Karnale chak upto Shamshan ghat | SS | Road | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 129.54 | 109.54 | 05/2011 | 102.4 | 87.775 | 97.5268 | 100% | 91% |  |  | 12.517 | 2020-04-15 | 75.258 | 2020-07-27 | [10 empty] | 87.775 | 9.7518 |  |  | 2020-05-01
| 86 | VII | 02.03.2019 | LUP2530 | Imp./upgd. Of road from machine Domana to Chibbe Chak in Marh block | SS | Road | R&B | Jammu | Jammu | CD 3rd Jmu | Balbir Singh | 150 | 115 | 07/2010 | 105 | 43.449 | 48.2762 | 100% | 59% |  |  | 43.449 | 2020-10-21 | [12 empty] | 43.449 | 4.8272 |  | 2020-12-01 | 2020-12-01
| 87 | I | 03.10.2018 | LUP0082 | Construction of 1x30 Mtr Trussed Girder Bridge with Chequered plate decking & side approaches at Baghi-i-Mehtab connecting Bund Road Rawalpora | SS | Bridge | R&B | Kashmir | Srinagar | Chadoora | HILAL AHMAD SHEIKH |  | 43.11 | 2015-05-01 |  | 37.612 | 41.7907 | 100% | 99% |  |  | 22.607 | 2019-07-16 | 15.005 | 2020-02-14 | [10 empty] | 37.612 | 4.1787 |  |  | 2019-20 | NIT No 75 of 2/2015 and 24 of 6/2019
| 88 | III | 24.10.2018 | LUP0915 | Construction of community centre at Checki Mehtan, Baghi-i-Mehtab | SS | NFB | R&B | Kashmir | Srinagar | Chadoora | HILAL AHMAD SHEIKH |  | 54.11 | 2013-01-01 |  | 37.976 | 42.1951 | 100% | 96% |  |  | 37.976 | 2020-01-14 | [12 empty] | 37.976 | 4.2191 |  |  | 2019-20 | NIT 113 of 2013
| 89 | I | 03.10.2018 | LUP0070 | Const. of 85 Mtr span steel foot bridge over river Marsudar at Bungam Tagood. | SS | Bridge | R&B | Jammu | Kishtwar | Chatroo | Mohinder Kumar | 265 | 123.95 | 06/2009 | 136.666 | 61.925 | 68.8049 | 100% | 91% |  |  | 61.925 | 2021-01-01 | [12 empty] | 61.925 | 6.8799 |  |  | 2019-20
| 90 | I | 03.10.2018 | LUP0076 | Missing link by way of Bridge and re-installation of existing Bridge (Const. of 45 mtr span Bridge over Koti Nallah at Doda Bharat road) | SS | Bridge | R&B | Jammu | Doda | Doda | Mohammad Ayub Wani | 280 | 174.5 | 05/2013 | 158 | 157.05 | 174.4983 | 100% | 100% |  |  | 99.132 | 2019-09-04 | 57.918 | 2019-11-26 | [10 empty] | 157.05 | 17.4483 | 0.001745 |  | 2019-20 |  | 2019-10-01
| 91 | IV | 20.11.2018 | LUP1243 | Const . Of Link Road from Shahpura Pranoo to Fangota in Distt. Doda | SS | Road | R&B | Jammu | Doda | Doda | Mohammad Ayub Wani | 296.81 | 244.81 | 06/2013 | 180.53 | 125.755 | 139.7264 | 100% | 60% |  |  | 58.86 | 2020-01-01 | 35.147 | 2020-08-11 | 31.748 | 2020-12-31 | [8 empty] | 125.755 | 13.9714 |  |  | 2020-10-01 |  | 2020-12-01
| 92 | III | 24.10.2018 | LUP0780 | Construction of Nilgrath Baltal road | SS | Road | R&B | Kashmir | Ganderbal | Ganderbal | Sayed Sajad Ahmad |  | 374.2 | 2017-06-01 |  | 266.908 | 296.5615 | 100% | 90% |  |  | 170.568 | 2019-07-08 | 52.074 | 2020-01-01 | 27 | 2020-02-03 | 17.266 | 2021-01-01 | [6 empty] | 266.908 | 29.6535 |  |  | 2019-20 | NIT No. 5/2017-18 dated 15-04-2017 35/2018-19 dt.02-06-2018, 169/2018-19 Dated:23.03.2019 and No.02/2019-20 Dt:15.04.2019
| 93 | VI | 28.02.2019 | LUP1858 | Construction of 1x20 Mtr span single lane plate girder bridge including Development of road approaches at Bala Sathun on Tulmulla Wakoora road | SS | Bridge | R&B | Kashmir | Ganderbal | Ganderbal | Sayed Sajad Ahmad |  | 141.42 | 2011-03-01 |  | 123.354 | 137.0586 | 100% | 99% | 2.893 |  | 83.646 | 2020-01-01 | 23.229 | 2020-02-03 | 16.479 | 2020-08-11 | [8 empty] | 123.354 | 13.7046 |  |  | 2019-20 | NIT No. 35/2019-20 dated:28.05.2019, 37/2019-20 Dt:30.05.2019 and No. 73/2019-20 Dt:23.07.2019
ns | 94 | I | 03.10.2018 | LUP0077 | Const. of 46 mtr span Foot Jhulla Bridge over Chilly nallah at Juri B. | SS | Bridge | R&B | Jammu | Doda | Gandoh | M.K Vikram | 55.38 | 16.38 | 07/2010 | 11.17 | 0 | 0 | 100% | [17 empty] | 0 | 0 |  |  | 2019-20
ns | 95 | I | 03.10.2018 | LUP0078 | Const. of 40 Mtr span FJb over Chilly Nallah over Chowan. | SS | Bridge | R&B | Jammu | Doda | Gandoh | M.K Vikram | 50.53 | 9.53 | 08/2010 | 4.31 | 0 | 0 | 100% | 100% |  | 3.843 | [14 empty] | 0 | 0 | 9.53 |  | 2019-20
| 96 | I | 03.10.2018 | LUP0079 | Const. of 50 M span FJB over Chansar nalah at Mahndan. | SS | Bridge | R&B | Jammu | Doda | Gandoh | M.K Vikram | 50.58 | 12.58 | 07/2010 | 3.88 | 3.492 | 3.88 | 100% | 100% |  |  | 3.492 | 2020-09-18 | [12 empty] | 3.492 | 0.38796 | 8.7 |  | 2019-20
| 97 | I | 03.10.2018 | LUP0080 | Const. of 40 Mtr span FJB at Inhara Bhagat Mohalla Bisran. | SS | Bridge | R&B | Jammu | Doda | Gandoh | M.K Vikram | 62.44 | 10.44 | 12/2010 | 5.67 | 4.662 | 5.1799 | 100% | 100% |  |  | 4.662 | 2020-09-18 | [12 empty] | 4.662 | 0.51795 | 5.2601 |  | 2019-20
| 98 | I | 03.10.2018 | LUP0100 | Constr. of 1x50 mtr span through type steel bridge over river kishan Ganga at Dawar Gurez | SS | Bridge | R&B | Kashmir | Bandipora | Gurez | Sidhrath Zutshi | 348.58 | 122.85 | 2012-09-01 |  | 78.184 | 86.8702 | 100% | 99% |  |  | 55.761 | 2019-09-18 | 18.98 | 2020-02-03 | 3.443 | 2020-12-19 | [8 empty] | 78.184 | 8.6862 |  |  | 2019-20
| 99 | I | 03.10.2018 | LUP0139 | Const of 2x32 mtr span trussed girder foot bridge over Nallah Pohru at Hangishort | SS | Bridge | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 130.86 | 2008-03-01 |  | 91.688 | 101.8745 | 100% | 99% | 3.002 |  | 43.321 | 2019-09-25 | 3.732 | 2020-02-03 | 41.577 | 2020-02-14 | 3.058 | 2020-12-15 | [6 empty] | 91.688 | 10.1865 |  |  | 2019-20
| 100 | III | 24.10.2018 | LUP0798 | Constr. Of 10 Mtr span Bridge on Nallah Talri at Warpora Ahgam | SS | Bridge | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 52.38 | 2016-09-01 |  | 23.628 | 26.2531 | 100% | 72% |  |  | 15.839 | 2019-09-25 | 7.789 | 2020-09-24 | [10 empty] | 23.628 | 2.6251 |  |  | 2019-20
| 101 | III | 24.10.2018 | LUP0799 | Constr. Of 14Mtr span double barrel box type culvert on Zaferkhani Mandoori Road in Km 1st | SS | Bridge | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 46.2 | 2016-09-01 |  | 40.394 | 44.8818 | 100% | 100% |  |  | 19.2 | 2019-07-09 | 16.731 | 2019-08-23 | 4.463 | 2020-09-24 | [8 empty] | 40.394 | 4.4878 | 1.3182 |  | 2020-07-20
| 102 | III | 24.10.2018 | LUP0803 | Construction/Upgradation of road Kenyal Dachina to Dogripora including Lilum to Waisa road | SS | Road | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 121.19 | 2010-06-01 |  | 107.208 | 119.1188 | 100% | 99% |  |  | 20.274 | 2019-07-03 | 65.641 | 2020-05-23 | 21.293 | 2020-09-18 | [8 empty] | 107.208 | 11.9108 |  |  | 2020-09-01
| 103 | IV | 20.11.2018 | LUP1257 | Construction of 1x25 Mtr. Span Bridge at Loolipora Yahama | SS | Bridge | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 61.81 | 2010-06-01 |  | 42.06 | 46.7329 | 100% | 85% |  |  | 20.311 | 2019-10-10 | 3.283 | 2019-11-26 | 18.466 | 2020-01-27 | [8 empty] | 42.06 | 4.6729 |  |  | 2019-20
| 104 | V | 12.12.2018 | LUP1525 | Upgrd of Kandi Sadhu Ganga road | SS | Road | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 245.77 | 2018-10-01 |  | 142.051 | 157.8329 | 100% | 91% |  |  | 76.271 | 2020-01-27 | 63.895 | 2020-12-10 | 1.885 | 2021-01-28 | [8 empty] | 142.051 | 15.7819 |  |  | 2020-10-01
NS | 105 | VI | 28.02.2019 | LUP1923 | Upgradation of Langate Hajin Takiya road including Langate Panditpora Shailnar link | SS | Road | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 329.39 | 2015-04-01 |  | 0 | 0 | 100% | [17 empty] | 0 | 0 |  |  | 2020-09-01
| 106 | VI | 28.02.2019 | LUP1924 | Upgradation of Geeripora Tumpora road | SS | Road | R&B | Kashmir | Kupwara | Handwara | Muzaffar Khaliq Kharoo |  | 271.02 | 2018-10-01 |  | 143.374 | 159.3029 | 100% | 70% |  |  | 64.584 | 2019-07-16 | 38.437 | 2020-02-03 | 40.353 | 2021-02-10 | [8 empty] | 143.374 | 15.9289 |  |  | 2019-20
| 107 | I | 03.10.2018 | LUP0039 | Const .of 15 mtr span (Single lane) reinforced Cement bridge over Banyari Nallah on Khanpur banyari Link Road District Kathua | SS | Bridge | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 99 | 87.24 | 11/2018 | 38.44 | 56.606 | 62.8949 | 100% | 100% |  |  | 31.896 | 2020-03-04 | 24.678 | 2020-10-29 | 0.032 | 2021-02-12 | [8 empty] | 56.606 | 6.2889 | 24.3451 |  | 2020-10-01 |  | 2020-11-01
| 108 | I | 03.10.2018 | LUP0040 | Const.of 25 mtr spand bridge on Krola Gharit upto Kasori Road | SS | Bridge | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 118..10 | 42.1 | 10/2013 | 23.17 | 15.381 | 17.0898 | 100% | 100% |  |  | 13.995 | 2019-11-26 | 1.386 | 2020-01-16 | [10 empty] | 15.381 | 1.7088 |  |  | 2019-20 | 64 of 2018-19/7277-96/G dtd. 08.11.2018 | 2019-06-01
| 109 | I | 03.10.2018 | LUP0041 | Const. of 40 mtr span vented causeway on Bhaiya & Mela link Road | SS | Bridge | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 96.5 | 50 | 10/2016 | 29.5 | 32.679 | 36.3096 | 100% | 100% |  |  | 25.578 | 2019-08-23 | 0.972 | 2020-03-31 | 6.129 | 2020-08-03 | [8 empty] | 32.679 | 3.6306 | 13.6904 |  | 2019-20 |  | 2020-06-01
| 110 | I | 03.10.2018 | LUP0042 | Const. of 105 m span vented causeway in Km 5th on Hiranagar Jandi Road Kathua | SS | Bridge | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 234.35 | 48.35 | 11/2010 | 28.9 | 26.082 | 28.9797 | 100% | 100% |  |  | 25.29 | 2019-09-05 | 0.792 | 2020-03-31 | [10 empty] | 26.082 | 2.8977 | 19.3703 |  | 2019-20 | 75 of 2018-19/8321-40/G dtd. 06.12.2018 | 2019-11-01
| 111 | III | 24.10.2018 | LUP0791 | Const. of link road from Dhaba/Tube well Morh to DugWell/Cremation Ground Sallan | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 59.8 | 52.55 | 09/2013 | 32.51 | 30.798 | 34.2197 | 100% | 100% |  |  | 17.046 | 2019-09-12 | 5.661 | 2020-03-06 | 8.091 | 2020-08-11 | [8 empty] | 30.798 | 3.4217 | 18.3303 |  | 2019-20 | 71 of 2018-19/7828-47/G dtd. 19.11.2018 and 29 of 2019-20/3248-67/G dtd. 21.06.2019 | 2020-06-01
| 112 | III | 24.10.2018 | LUP0792 | Const. of Pranta Patyari to Balan Talab road | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 65 | 40 | 11/2010 | 41.14 | 35.757 | 39.7296 | 100% | 100% |  |  | 16.317 | 2020-01-20 | 19.44 | 2020-04-15 | [10 empty] | 35.757 | 3.9726 | 0.2704 |  | 2019-20 | 71 of 2018-19/7828-47/G dtd. 19.11.2018 and 29 of 2019-20/3248-67/G dtd. 21.06.2019 | 2020-01-01
| 113 | III | 24.10.2018 | LUP0793 | Const. of link road to Patoli | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 65 | 48 | 12/2008 | 26.89 | 27.684 | 30.7597 | 100% | 100% |  |  | 12.807 | 2020-01-20 | 6.66 | 2020-07-30 | 3.51 | 2020-09-18 | 4.707 | 2021-01-28 | [6 empty] | 27.684 | 3.0757 |  |  | 2020-10-01 |  | 2020-10-01
| 114 | III | 24.10.2018 | LUP0794 | Kalaspur to Darhal Kathua | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 30 | 19.5 | 01/2011 | 15.07 | 14.301 | 15.8898 | 100% | 100% |  |  | 13.887 | 2020-01-20 | 0.414 | 2020-12-19 | [10 empty] | 14.301 | 1.5888 |  |  | 2019-20 | 71 of 2018-19/7828-47/G dtd. 19.11.2018 and 29 of 2019-20/3248-67/G dtd. 21.06.2019 | 2019-07-01
| 115 | III | 24.10.2018 | LUP0795 | Jasrota to Rakh Hoshiari road | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 112.53 | 90.53 | 12/2010 | 71.53 | 56.502 | 62.7794 | 100% | 100% |  |  | 11.772 | 2019-12-09 | 44.289 | 2020-02-03 | 0.441 | 2020-09-03 | [8 empty] | 56.502 | 6.2774 | 27.7506 |  | 2019-20 | 71 of 2018-19/7828-47/G dtd. 19.11.2018 and 29 of 2019-20/3248-67/G dtd. 21.06.2019 | 2019-10-01
| 116 | III | 24.10.2018 | LUP0796 | Maroli to Kalaspur via Upper Govindsar link road Kathua | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 76.65 | 46.65 | 01/2010 | 30.47 | 24.957 | 27.7297 | 100% | 100% |  |  | 15.363 | 2020-01-20 | 9.036 | 2020-03-31 | 0.558 | 2020-12-19 | [8 empty] | 24.957 | 2.7727 |  |  | 2019-20 | 71 of 2018-19/7828-47/G dtd. 19.11.2018 and 29 of 2019-20/3248-67/G dtd. 21.06.2019 | 2020-01-01
| 117 | VII | 02.03.2019 | LUP2517 | Const. of link road to Chak Rijju Railway Station road | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 61 | 39 | 08/2005 | 46.67 | 34.011 | 37.7896 | 100% | 100% |  |  | 34.011 | 2020-01-14 | [12 empty] | 34.011 | 3.7786 | 1.2104 |  | 2019-20 | 11 of 2019-20/1497-1516/G dtd. 17.05.2019 | 2019-07-01
| 118 | VII | 02.03.2019 | LUP2518 | Const. link road to village thein from Basoli road | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 61.8 | 41.8 | 11/2015 | 14.78 | 32.238 | 35.8196 | 100% | 100% |  |  | 10.593 | 2020-02-03 | 2.367 | 2020-09-03 | 19.278 | 2020-12-14 | [8 empty] | 32.238 | 3.5816 | 5.9804 |  | 2020-10-01 |  | 2020-10-01
| 119 | VII | 02.03.2019 | LUP2519 | Const. of sallan link road | SS | Road | R&B | Jammu | Kathua | Kathua | ER. RAJAN GUPTA | 80.79 | 67.79 | 02/2007 | 64.98 | 58.473 | 64.9694 | 100% | 100% |  |  | 55.305 | 2019-09-04 | 3.168 | 2020-03-06 | [10 empty] | 58.473 | 6.4964 | 2.8206 |  | 2019-20 | 05 of 2019-20/1097-1116/G dtd. 10.05.2019 | 2020-02-01
| 120 | II | 10.10.2018 | LUP0474 | Const. of 25 Mtr span Steel Girder Motorable Bridge with its approaches including link road to village Maghal Katra | SS | Bridge | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 479 | 288.5 | 10/2007 | 222.26 | 197.731 | 219.6989 | 100% | 100% |  |  | 20.832 | 2019-08-23 | 63.602 | 2019-10-04 | 19.88 | 2020-05-23 | 17.73 | 2020-07-07 | 48.756 | 2020-12-19 | 26.931 | 2021-01-28 |  |  | 197.731 | 21.9679 |  |  | 2020-09-01
| 121 | III | 24.10.2018 | LUP0895 | Imprvtt./Upgd of road from Kalika Nagar to Latori Length= 3.50 Km | SS | Road | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 89.51 | 89.51 | 09/2005 | 60.57 | 74.131 | 82.367 | 100% | 100% |  |  | 17.609 | 2019-06-12 | 5.428 | 2019-10-23 | 11.422 | 2020-02-03 | 24.588 |  | 15.084 | 2020-12-24 |  |  |  |  | 74.131 | 8.236 |  |  | 2020-10-01
| 122 | III | 24.10.2018 | LUP0896 | Const of road from Paroh to Arli | SS | Road | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 155.25 | 145.25 | 08/2003 | 122.02 | 109.741 | 121.9332 | 100% | 100% |  |  | 40.495 | 2019-05-10 | 19.803 | 2019-07-01 | 44.437 | 2019-07-25 | 5.006 | 2020-03-16 | [6 empty] | 109.741 | 12.1922 | 23.3168 |  | 2019-20 | e-NIT No. 33 of 2018-19 Dated 24-11-2018, e-NIT No. 53 of 2018-19 Dated 12-02-2019
| 123 | III | 24.10.2018 | LUP0897 | Imprvtt./Upgd of road from Bhagtha to Manoon Length= 2.50 Km | SS | Road | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 108.49 | 108.49 | 09/2004 | 73.79 | 66.037 | 73.3737 | 100% | 100% |  |  | 20.673 | 2019-07-16 | 6.194 | 2019-11-26 | 29.424 | 2020-07-30 | 9.746 | 2020-01-11 | [6 empty] | 66.037 | 7.3367 |  |  | 2020-09-01 | e-NIT No. 53 of 2018-19 Dated 12-02-2019
| 124 | III | 24.10.2018 | LUP0898 | Extn. Of road from Kadmal ( Nikki Mashha) to Nomain Length = 2.84 Km | SS | Road | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 70.02 | 70.02 | 07/2004 | 51.2 | 57.276 | 63.6394 | 100% | 100% |  |  | 21.978 | 2019-05-29 | 24.098 | 2020-07-07 | 4.117 | 1900-01-06 02:00 | 7.083 | 2020-01-11 | [6 empty] | 57.276 | 6.3634 |  |  | 2020-09-01
| 125 | III | 24.10.2018 | LUP0899 | Road from Kadmal to Dhanna Length= 1.00 Km. | SS | Road | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 96.4 | 96.4 | 11/2008 | 53.68 | 47.847 | 53.1628 | 100% | 100% |  |  | 13.313 | 2019-05-29 | 23.585 | 2019-10-09 | 10.949 | 2020-03-16 | [8 empty] | 47.847 | 5.3158 | 43.2372 |  | 2019-20 | Fresh e-NIT No. 32 of 2018-19 Dated 16-11-2018, e-NIT No. 24 of 2019-20 dated 02-08-2019, e-NIT No. 63 of 2019-20 Dated 14-12-2019
| 126 | III | 24.10.2018 | LUP0900 | Road from Palli to village Binari ( Muttal) Length=2.00 Km ) | SS | Road | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 126.99 | 126.99 | 06/2007 | 122.17 | 109.909 | 122.1199 | 100% | 100% |  |  | 39.918 | 2019-05-23 | 29.102 | 2019-10-04 | 28.122 | 2020-02-03 | 12.767 | 2020-12-19 | [6 empty] | 109.909 | 12.2109 |  |  | 2020-07-01
| 127 | V | 12.12.2018 | LUP1519 | Const of Road from Aghar Jitto to Pangatha | SS | Road | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 847 | 87.5 | 08/2007 | 589.99 | 65.798 | 73.1082 | 100% | 100% |  |  | 17.908 | 2019-11-05 | 35.177 | 2020-02-03 | 12.713 | 2020-08-11 | [8 empty] | 65.798 | 7.3102 | 14.3918 |  | 2019-20 | e-NIT No. 40 of 2018-19 Dated 01-01-2019, e-NIT No. 67 of 2019-20 Dated 22-01-2020
| 128 | V | 12.12.2018 | LUP1520 | Const of 40 mtr span steel foot bridge over Junnie Nallah Moori | SS | Bridge | R&B | Jammu | Reasi | Katra | Rajesh Kumar Gupta | 144.2 | 56.26 | 09/2001 | 16.9 | 50.609 | 56.2317 | 100% | 100% |  |  | 23.659 | 2019-09-12 | 26.95 | 2019-12-17 | [10 empty] | 50.609 | 5.6227 | 0.02834 |  | 2019-20 | Fresh e-NIT No. 59 of 2018-19 Dated 05-03-2019 | 2019-10-01
| 129 | I | 03.10.2018 | LUP0108 | Construction of 1x25 Mtr Span RCC Steel Girder bridge between Guree and Keripora Bijbehara | SS | Bridge | R&B | Kashmir | Anantnag | Khanabal | Mohammad Ayub Wani |  | 67.56 | 2010-09-01 |  | 60.732 | 67.4793 | 100% | 100% |  |  | 51.462 | 2020-01-14 | 9.27 | 2020-08-03 | [10 empty] | 60.732 | 6.7473 | 0.080675 |  | 2019-20
| 130 | I | 03.10.2018 | LUP0109 | Construction of Overhead Peadestrian Crossing at Bijbehara on Jammu Srinagar NH | SS | Bridge | R&B | Kashmir | Anantnag | Khanabal | Mohammad Ayub Wani |  | 79 | 2011-12-01 |  | 59.049 | 65.6093 | 100% | 99% |  |  | 59.049 | 2020-02-18 | [12 empty] | 59.049 | 6.5603 |  |  | 2019-20 | SICOP
| 131 | III | 24.10.2018 | LUP0759 | Constr.of steel trussed jeepable Bridge at Bangidar Anantnag | SS | Bridge | R&B | Kashmir | Anantnag | Khanabal | Mohammad Ayub Wani |  | 285 | 2008-01-01 |  | 228.168 | 253.5175 | 100% | 100% |  |  | 155.34 | 2019-06-12 | 58.572 | 2019-10-24 | 14.256 | 2020-08-17 | [8 empty] | 228.168 | 25.3495 | 31.4825 |  | 2019-20 | 1) NIT No. 115/2016-17/E-tendering/6726-35 Dt 09/01/2017 2) NIT No. 99/2018-19/E-tendering/6591-6601 Dt 30/11/2018 3) NIT No. 43/2019-20/E-tendering/2774-84 Dt 23/07/2019 4) SICOP
| 132 | VI | 28.02.2019 | LUP1919 | Const. of Parking Places at Kishtwar Town on NH 244 | SS | Road | R&B | Jammu | Kishtwar | Kishtwar | MOHINDER KUMAR | 164.64 | 134.64 | 08/2016 | 125.83 | 113.249 | 125.831 | 100% | 100% |  |  | 63.758 | 2020-02-17 | 46.53 | 2020-03-31 | 2.961 | 2020-08-03 | [8 empty] | 113.249 | 12.582 | 8.809 |  | 2019-20
| 133 | I | 03.10.2018 | LUP0120 | Construction of 1x12 Mtr span bridge in Km 1st on Adipora Mishpora road | SS | Bridge | R&B | Kashmir | Kulgam | Kulgam | Mohammad Sidiq Dar |  | 46.8 | 2014-10-01 |  | 41.735 | 46.3718 | 100% | 100% |  |  | 13.636 | 2019-11-26 | 28.099 | 2020-01-01 | [10 empty] | 41.735 | 4.6368 | 0.42824 |  | 2019-20 | 103/2018-19/R&B/Kul/E-tendering/ 5621-40 Dated:- 12-10-2018
| 134 | I | 03.10.2018 | LUP0121 | Construction of 1x10 Mtr span bridge on Khudwani Ganjipora Road. | SS | Bridge | R&B | Kashmir | Kulgam | Kulgam | Mohammad Sidiq Dar |  | 83.84 | 2017-10-01 |  | 57.707 | 64.1182 | 100% | 92% |  |  | 57.707 | 2019-09-04 | [12 empty] | 57.707 | 6.4112 |  |  | 2019-20 | 116/2018-19/R&B/Kul/E-tendering/6269-80 Dated:- 01-11-2018 112/2019-20/R&B/Ku l/E-tendering/8241-61 Dated: 5-2-2020
| 135 | I | 03.10.2018 | LUP0122 | Construction of 1x8 Mtr span bridge in Km 1st on Frisal Chanigam road | SS | Bridge | R&B | Kashmir | Kulgam | Kulgam | Mohammad Sidiq Dar |  | 56.65 | 2017-02-01 |  | 50.418 | 56.0194 | 100% | 100% |  |  | 32.329 | 2019-06-12 | 2.998 | 2019-12-24 | 13.79 | 2020-03-31 | 1.301 | [7 empty] | 50.418 | 5.6014 | 0.63056 |  | 2019-20 | 104/2018-19/R&B/Kul/E-tendering/ 5644-65 Dated: 12-10-2018 28/2019-20/R&B/Kul/E-tendering/1779-99 Dated: 13-5-2019
| 136 | V | 12.12.2018 | LUP1521 | Upgrd of Gadwani Jaibal incld. C.R.Pora road | SS | Road | R&B | Kashmir | Kulgam | Kulgam | Mohammad Sidiq Dar |  | 145.1 | 2015-07-01 |  | 102.107 | 113.4511 | 100% | 100% |  |  | 57.294 | 2019-07-03 | 25.532 | 2019-09-27 | 19.281 | 2020-09-24 | [8 empty] | 102.107 | 11.3441 | 31.6489 |  | 2020-09-01
| 137 | IV | 20.11.2018 | LUP1251 | Construction of Bogund Kulpora road | SS | Road | R&B | Kashmir | Kulgam | Kulgam | Mohammad Sidiq Dar | 152.26 | 105.36 | 2018-06-01 |  | 66.967 | 74.407 | 100% | 86% |  |  | 62.129 | 2020-10-14 | 4.838 | 2020-12-19 | [10 empty] | 66.967 | 7.44 |  | 2020-12-01 | 2020-12-01
| 138 | I | 03.10.2018 | LUP0143 | Constr of 1x45 mtr span RCC Bridge over Nallah Manigah at Reshi Mohalla Manzhar Hyhama Lolab | SS | Bridge | R&B | Kashmir | Kupwara | Kupwara | S Gurdev Singh |  | 69.44 | 2017-05-01 |  | 35.166 | 39.0729 | 100% | 90% |  |  | 25.2 | 2019-07-16 | 9.966 | 2020-01-01 | [10 empty] | 35.166 | 3.9069 |  |  | 2019-20
| 139 | I | 03.10.2018 | LUP0144 | Construction of proposed single lane steel bridge at Dobwan Kachama | SS | Bridge | R&B | Kashmir | Kupwara | Kupwara | S Gurdev Singh |  | 93.06 | 2013-04-01 |  | 64.36 | 71.5104 | 100% | 100% |  |  | 34.564 | 2019-07-09 | 29.796 | 2019-12-17 | [10 empty] | 64.36 | 7.1504 | 21.5496 |  | 2019-20 |  | 2019-07-01
| 140 | I | 03.10.2018 | LUP0145 | Const of 1x15 m span steel; decked bridge over Nallah Hud at Kralpora Bus Adda | SS | Bridge | R&B | Kashmir | Kupwara | Kupwara | S Gurdev Singh |  | 91.61 | 2013-04-01 |  | 46.347 | 51.4962 | 100% | 100% |  |  | 17.528 | 2019-07-16 | 7.581 | 2019-10-04 | 19.552 | 2019-12-17 | 1.686 | 2020-09-24 | [6 empty] | 46.347 | 5.1492 | 40.1138 |  | 2019-20 |  | 2019-07-01
| 141 | III | 24.10.2018 | LUP0797 | Wasarkote Lonaharia Bridge 1x15 Mtr Span | SS | Bridge | R&B | Kashmir | Kupwara | Kupwara | S Gurdev Singh |  | 147.78 | 2014-01-01 |  | 53.82 | 59.7994 | 100% | 47% |  |  | 34.425 | 2020-03-31 | 19.395 | 2020-09-24 | [10 empty] | 53.82 | 5.9794 |  |  | 2019-20
| 142 | IV | 20.11.2018 | LUP1258 | Construction of Rest House at Anderbugh | SS | NFB | R&B | Kashmir | Kupwara | Kupwara | S Gurdev Singh |  | 35.14 | 2016-10-01 |  | 28.011 | 31.123 | 100% | 94% |  |  | 28.011 | 2020-09-03 | [12 empty] | 28.011 | 3.112 |  |  | 2019-20 |  | 2020-03-01
| 143 | IV | 20.11.2018 | LUP1259 | Construction of Rest House at Panzagam | SS | NFB | R&B | Kashmir | Kupwara | Kupwara | S Gurdev Singh |  | 58.72 | 2019-02-01 |  | 38.928 | 43.2529 | 100% | 100% |  |  | 18.378 | 2019-06-12 | 20.55 | 2019-12-23 | [10 empty] | 38.928 | 4.3249 | 15.4671 |  | 2019-20 |  | 2019-07-01
| 144 | VI | 28.02.2019 | LUP1929 | Construction of 2x25 Mtr double lane steel girder bridge instead of construction of 1x45 Mtr span double lane steel girder bridge including strengthening of existing bridge over nallah Kalarooch in Km 6th of Kupwara Sogam road at Khumriyal | SS | Bridge | R&B | Kashmir | Kupwara | Kupwara | S Gurdev Singh |  | 152.48 | 2016-08-01 |  | 93.887 | 104.3178 | 100% | 99% |  |  | 40.077 | 2019-08-23 | 3.297 | 2019-10-18 | 13.669 | 2019-12-17 | 6.521 | 2020-04-15 | 15.747 | 2020-07-27 | 14.576 | 2020-01-05 |  |  | 93.887 | 10.4308 |  |  | 2020-08-01 |  | 2020-12-01
| 145 | V | 12.12.2018 | LUP1535 | Const of 21.00 Mtr C/C Span Motorable deck type Plate Girder Bridge over Nallah Tukson on Bagga Gulabgarh Road | SS | Bridge | R&B | Jammu | Reasi | Mahore | Davinder Singh | 121.4 | 37.2 | 03/2016 | 79.42 | 14.328 | 15.9198 | 100% | 100% |  |  | 14.328 | 2020-01-01 | [12 empty] | 14.328 | 1.5918 | 21.2802 |  | 2019-20
| 146 | V | 12.12.2018 | LUP1538 | Const. of Road From Sungri to Bagudass (Missing Link) L 0.70 kms | SS | Road | R&B | Jammu | Reasi | Mahore | Davinder Singh | 161.54 | 142.54 | 07/2015 | 89.9 | 65.349 | 72.6093 | 100% | 100% | 12.508 |  | 33.66 | 2019-09-18 | 31.689 | 2020-03-31 | [10 empty] | 65.349 | 7.2603 |  |  | 2020-11-01
| 147 | I | 03.10.2018 | LUP0060 | Construction of road from Bajwal to Siot including 80 m span motorable bridge at Nalani Pattan | SS | Road / Bridge | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 519.46 | 214.46 | 6/2009 | 115 | 102.831 | 114.2555 | 100% | 100% |  |  | 102.831 | 2020-05-23 | [12 empty] | 102.831 | 11.4245 | 100.2045 |  | 2019-20 | 82 of 2018-19 Dt. 20.11.2018
| 148 | I | 03.10.2018 | LUP0061 | Construction of 40 Mtr Span Steel Girder Motorable Bridge at Rawarian Talla (Sunderbani) | SS | Bridge | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 327.4 | 98.9 | 4/2012 | 64.68 | 33.152 | 36.8352 | 100% | 81% |  |  | 33.152 | 2020-07-30 | [12 empty] | 33.152 | 3.6832 |  |  | 2020-10-01
| 149 | II | 10.10.2018 | LUP0472 | 45 M Span motorable bridge at Kalara on Kharsoo Teryath Road | SS | Bridge | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 264.9 | 219.4 | 6/2011 | 175.23 | 135.699 | 150.7752 | 100% | 95% |  |  | 101.43 | 2019-05-21 | 14.609 | 2019-10-04 | 19.66 | 2020-08-11 | [8 empty] | 135.699 | 15.0762 |  |  | 2020-11-01
| 150 | III | 24.10.2018 | LUP0837 | Const.of road from Dharamsal-Badanoo road | SS | Road | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 160.5 | 85.5 | 7/2008 | 67.9 | 76.914 | 85.4591 | 100% | 100% |  |  | 17.577 | 2019-07-01 | 24.192 | 2019-10-04 | 35.145 | 2020-12-31 | [8 empty] | 76.914 | 8.5451 |  |  | 2020-07-01
| 151 | III | 24.10.2018 | LUP0838 | Link road from Solki Bridge to Gaddi Gazi Muzaffar Shah | SS | Road | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 172.95 | 163.95 | 6/2012 | 124.53 | 79.333 | 88.1469 | 100% | 97% |  |  | 22.68 | 2019-12-17 | 16.957 | 2020-03-06 | 24.347 | 2020-04-15 | 15.349 | 2020-09-18 | [6 empty] | 79.333 | 8.8139 |  |  | 2019-20 | 80 of 2018-19 Dt. 19.11.2018
| 152 | III | 24.10.2018 | LUP0840 | Const.of road from Mangal Singh Chowk to Berari Dhanika Nowshera | SS | Road | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 95 | 53 | 4/2013 | 27.43 | 41.878 | 46.5306 | 100% | 100% |  |  | 11.939 | 2019-07-01 | 11.76 | 2019-09-18 | 18.179 | 2020-04-15 | [8 empty] | 41.878 | 4.6526 | 6.4694 |  | 2019-20 | 81 of 2018-19 Dt. 19.11.2018
| 153 | III | 24.10.2018 | LUP0841 | Sunderbani to Loharakote | SS | Road | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 108.75 | 67.75 | 6/2012 | 64 | 60.745 | 67.4938 | 100% | 100% |  |  | 60.745 | 2020-07-27 | [12 empty] | 60.745 | 6.7488 | 0.25623 |  | 2020-06-01
| 154 | III | 24.10.2018 | LUP0845 | Const.of road from Dabbar to Sat Sahal | SS | Road | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 189 | 139.5 | 6/2013 | 130.96 | 103.235 | 114.7044 | 100% | 86% |  |  | 35.553 | 2019-09-18 | 67.682 | 2020-06-26 | [10 empty] | 103.235 | 11.4694 |  |  | 2020-10-01
| 155 | III | 24.10.2018 | LUP0848 | Const.of road from Rajal to Hanjana via Malika Mohra Km 2nd. | SS | Road | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 167.5 | 138 | 6/2010 | 60.02 | 53.115 | 59.0161 | 100% | 63% |  |  | 53.115 | 2020-02-27 | [12 empty] | 53.115 | 5.9011 |  |  | 2019-20 | 93 of 2018-19 Dt. 09.01.2019
| 156 | III | 24.10.2018 | LUP0852 | Const.of road from Kalideh to Baba Narsingh. | SS | Road | R&B | Jammu | Rajouri | Nowshera | Prem Kumar | 208.55 | 127.55 | 4/2011 | 49.13 | 34.023 | 37.803 | 100% | 100% |  |  | 18.857 | 2019-07-08 | 15.166 | [11 empty] | 34.023 | 3.78 | 89.747 |  | 2019-20 | 82 of 2018-19 Dt. 20.11.2018
| 157 | III | 24.10.2018 | LUP0893 | Chassana to sarsote up to Malikote, Package No: JK14-18, statge-I, Phase-V, block Mahore. | SS | Road | R&B | Jammu | Reasi | PMGSY Mahore | Roshan Din | 719.95 | 143.32 | 10/2018 | 147.36 | 120.898 | 134.3298 | 100% | 100% |  |  | 110.25 | 2019-07-16 | 10.648 | 2019-12-09 | [10 empty] | 120.898 | 13.4318 | 8.9902 |  | 2019-20
| 158 | I | 03.10.2018 | LUP0064 | Const of 25 m span FJB over Suran River Pharoo Tehsil Surankote. | SS | Bridge | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 46.99 | 29.39 | 4/2011 | 29.39 | 21.788 | 24.2086 | 100% | 100% |  |  | 21.788 | 2020-07-07 | [12 empty] | 21.788 | 2.4206 | 5.1814 |  | 2019-20
| 159 | I | 03.10.2018 | LUP0065 | Constt. Of 28 M span steel FJB at Bagnuwali , tehsil Surankote, distt., poonch. | SS | Bridge | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 61.28 | 33.28 | 4/2011 | 25.5 | 27.753 | 30.8364 | 100% | 100% |  |  | 23.193 | 2019-12-09 | 4.56 | 2020-12-22 | [10 empty] | 27.753 | 3.0834 |  |  | 2019-20
| 160 | I | 03.10.2018 | LUP0068 | Const of 40 M span steel FJB over Chungan Nallah at Chak Banola, distt. Poonch. | SS | Bridge | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 74.16 | 47.66 | 6/2010 | 31.54 | 33.666 | 37.4063 | 100% | 100% |  |  | 14.039 | 2020-07-27 | 5.148 |  | 14.479 | 2020-12-24 | [8 empty] | 33.666 | 3.7403 |  |  | 2020-06-01
| 161 | I | 03.10.2018 | LUP0069 | Const. of 50M span M/able bridge at Rajpura on Zairat Chowkiwala balnai road Km 1st | SS | Bridge | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 185.34 | 158.34 | 6/2015 | 158.34 | 142.181 | 157.9773 | 100% | 100% |  |  | 65.601 | 2019-06-12 | 6.39 | 2019-12-23 | 4.545 | 2020-02-14 | 32.345 | 2020-04-15 | 33.3 | 2020-10-01 |  |  |  |  | 142.181 | 15.7963 | 0.36269 |  | 2020-07-01
| 162 | II | 10.10.2018 | LUP0470 | Const. of 30 M Span Motorable Bridge at Kotan Sadwala to Soian panakhan | SS | Bridge | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 150 | 35 | 6/2014 | 35 | 23.018 | 25.5753 | 100% | 95% |  |  | 23.018 | 2020-01-11 | [12 empty] | 23.018 | 2.5573 |  |  | 2020-09-01
| 163 | II | 10.10.2018 | LUP0471 | Const of 45 M span Steel FJB at Chattral nallah near Mohalla Chattral Mendhar | SS | Bridge | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 100 | 66 | 4/2010 | 45.4 | 0 | 0 | 100% | 54% | 13.473 | [15 empty] | 0 | 0 |  |  | 2020-11-01
| 164 | III | 24.10.2018 | LUP0805 | Const. of road from Charallan to Sangla via Dandidhara | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 155.5 | 108 | 5/2013 | 84.02 | 93.545 | 103.9378 | 100% | 97% |  |  | 28.289 | 2020-02-14 | 52.568 | 2020-10-21 | 12.688 | 2021-02-12 | [8 empty] | 93.545 | 10.3928 |  |  | 2020-10-01
| 165 | III | 24.10.2018 | LUP0807 | Const. of 150 Mtr span Motorable bridge at Kulani over Mandi Nallah | SS | Bridge | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 532.92 | 249.78 | 6/2011 | 249.78 | 224.404 | 249.3353 | 100% | 100% |  |  | 61.65 | 2020-02-17 | 22.387 | 2020-07-07 | 53.89 | 2020-07-27 | 11.777 | 2020-09-03 | 74.7 | 2020-12-19 |  |  |  |  | 224.404 | 24.9313 |  |  | 2020-07-01
| 166 | III | 24.10.2018 | LUP0810 | Const. of road "Kalai to High School Kalai road. | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 167.62 | 111.62 | 6/2010 | 46.92 | 98.46 | 109.3989 | 100% | 100% |  |  | 73.08 | 2020-06-26 | 25.38 | 2020-12-15 | [10 empty] | 98.46 | 10.9389 | 2.2211 |  | 2020-09-01
| 167 | III | 24.10.2018 | LUP0811 | Const. of Link road to Mohalla Dupprian to Lassana | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 72.13 | 57.13 | 06/2013 | 50.5 | 25.718 | 28.5753 | 100% | 72% |  |  | 16.841 | 2019-10-24 | 8.877 | 2020-10-01 | [10 empty] | 25.718 | 2.8573 |  |  | 2020-07-01
| 168 | III | 24.10.2018 | LUP0812 | Const. of road from Jogi More to Mohalla Manhasan. | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 129.49 | 99.99 | 6/2007 | 68.35 | 65.557 | 72.8404 | 100% | 83% |  |  | 29.247 | 2019-12-09 | 16.19 | 2020-07-27 | 20.12 | 2020-12-19 | [8 empty] | 65.557 | 7.2834 |  | 2021-02-01 | 2020-12-01
| 169 | III | 24.10.2018 | LUP0814 | Const. of road from Malti Link road | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 119.95 | 89.45 | 5/2010 | 79.78 | 50.792 | 56.435 | 100% | 100% |  |  | 50.792 | 2020-02-03 | [12 empty] | 50.792 | 5.643 | 33.015 |  | 2019-20
| 170 | III | 24.10.2018 | LUP0815 | Const. of link road Kasalian. | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 214.89 | 175.39 | 6/2011 | 119.74 | 141.387 | 157.0951 | 100% | 100% |  |  | 122.688 | 2019-09-25 | 9.718 | 2020-07-29 | 8.981 | 2020-12-31 | [8 empty] | 141.387 | 15.7081 |  |  | 2019-20
| 171 | III | 24.10.2018 | LUP0816 | Const. of link road from Shiv Khori to Temple upto Nabani | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 197.97 | 166.47 | 6/2009 | 116.36 | 148.064 | 164.5139 | 100% | 100% |  |  | 104.76 | 2020-07-07 | 43.304 | 2021-02-19 | [10 empty] | 148.064 | 16.4499 |  |  | 2020-09-01
| 172 | III | 24.10.2018 | LUP0817 | Const. of road from Dashal Mendhar to Holy Shrine Mian Charag Alam. | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 285.75 | 185 | 5/2013 | 185.61 | 162.244 | 180.2693 | 100% | 98% |  |  | 54.917 | 2020-02-14 | 43.742 | 2020-04-15 | 63.585 | 2020-12-31 | [8 empty] | 162.244 | 18.0253 |  |  | 2020-10-01
| 173 | III | 24.10.2018 | LUP0818 | Const. of road from Jugal to Kullian road to Topa | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 274.1 | 254.1 | 6/2012 | 231.9 | 106.298 | 118.1077 | 100% | 52% |  |  | 57.57 | 2020-04-15 | 48.728 | 2020-12-31 | [10 empty] | 106.298 | 11.8097 |  |  | 2020-11-01
| 174 | III | 24.10.2018 | LUP0819 | Const. of road from Ari to Pathanateer to Salwah | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 259.75 | 222.25 | 6/2012 | 157.44 | 172.456 | 191.6159 | 100% | 90% |  |  | 77.391 | 2020-04-15 | 95.065 | 2020-12-19 | [10 empty] | 172.456 | 19.1599 |  |  | 2020-10-01
| 175 | III | 24.10.2018 | LUP0821 | Const. of balance work of road from Behra to Salwah | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 187.61 | 166.61 | 6/2013 | 162.26 | 119.201 | 132.4442 | 100% | 80% |  |  | 45.247 | 2020-02-17 | 35.636 | 2020-10-01 | 38.318 | 2021-03-02 | [8 empty] | 119.201 | 13.2432 |  |  | 2020-10-01
| 176 | III | 24.10.2018 | LUP0823 | Const. of balance work of Sekloo Saloonia road. | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 105.8 | 86.3 | 6/2013 | 54.97 | 74.064 | 82.2925 | 100% | 100% |  |  | 50.481 | 2020-06-26 | 23.583 | 2021-02-19 | [10 empty] | 74.064 | 8.2285 |  |  | 2020-09-01
| 177 | III | 24.10.2018 | LUP0825 | Up-gradation of Harni BG Road Km 7th to 10th | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 230.97 | 201.47 | 5/2012 | 167.81 | 180.687 | 200.7613 | 100% | 100% |  |  | 81.165 | 2019-12-09 | 90.072 | 2020-02-14 | 9.45 | 2020-08-03 | [8 empty] | 180.687 | 20.0743 | 0.70867 |  | 2019-20
| 178 | III | 24.10.2018 | LUP0826 | Const. of road from Dolati Zayrat to Danna Doyian | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 159 | 130.5 | 5/2017 | 130 | 114.419 | 127.131 | 100% | 100% |  |  | 54.135 | 2020-06-26 | 60.284 | 2021-02-19 | [10 empty] | 114.419 | 12.712 |  |  | 2020-10-01
| 179 | III | 24.10.2018 | LUP0827 | Const. of road from Sakhi Maidan Kalai Km 33rd to PMGSY road. | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 84 | 71.5 | 5/2016 | 34.16 | 30.696 | 34.1063 | 100% | 60% |  |  | 30.696 | [13 empty] | 30.696 | 3.4103 |  |  | 2020-09-01
| 180 | III | 24.10.2018 | LUP0828 | Const. of road from PMGSY 1.85 to Danna Kunuyian. | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 227 | 215 | 6/2014 | 181.27 | 135.686 | 150.7607 | 100% | 75% |  |  | 52.751 | 2019-09-05 | 82.935 | 2020-06-26 | [10 empty] | 135.686 | 15.0747 |  |  | 2020-10-01
| 181 | VI | 28.02.2019 | LUP1930 | Construction of road from Hathi Matha to Devi mang | SS | Road | R&B | Jammu | Poonch | Poonch | Mohammad Parvez | 278 | 144.7 | 06/2005 | 115.5 | 124.981 | 138.8664 | 100% | 100% |  |  | 81.032 | 2020-02-14 | 2.943 | 2020-07-29 | 41.006 | 2020-10-01 | [8 empty] | 124.981 | 13.8854 | 5.8336 |  | 2019-20
| 182 | I | 03.10.2018 | LUP0156 | Constr. of 1x15 mtr steel girder Wandakpora (Hanjipora Bridge) at Hanjipora | SS | Bridge | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo | 157 | 33 | 2008-06-01 |  | 26.451 | 29.3897 | 100% | 100% |  |  | 23.557 | 2019-09-04 | 2.894 | 2020-08-17 | [10 empty] | 26.451 | 2.9387 | 3.6103 |  | 2019-20
| 183 | I | 03.10.2018 | LUP0157 | Constr. Of 2x20 mtr bridge on Hurdimir Saimoh Road | SS | Bridge | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 69.5 | 2011-04-01 |  | 56.417 | 62.6849 | 100% | 100% |  |  | 23.906 | 2019-07-25 | 10.004 | 2020-04-15 | 22.507 | 2020-09-09 | [8 empty] | 56.417 | 6.2679 | 6.8151 |  | 2020-06-01
| 184 | III | 24.10.2018 | LUP0829 | Constr. Of 1x15 Mtr span Plate girder bridge at Hariparigam Tral | SS | Bridge | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 54.84 | 2015-09-01 |  | 49.356 | 54.8395 | 100% | 100% |  |  | 29.595 | 2020-02-06 | 14.463 | 2020-05-23 | 5.298 | 2020-07-07 | [8 empty] | 49.356 | 5.4835 | 0.0005484 |  | 2020-06-01
| 185 | III | 24.10.2018 | LUP0830 | Const./Upgradation of Payer banderpora, Banderpora Koli and Payer Chandgam Road | SS | Road | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 85.42 | 2010-10-01 |  | 75.4 | 83.7769 | 100% | 100% |  |  | 75.4 | 2019-07-25 | [12 empty] | 75.4 | 8.3769 | 1.6431 |  | 2019-20 | 01) 13/EEP/RNB/2019-20/915-25 Dated:- 07-05-2019 02) 36/EEP/RNB/2019-20/1783-93 Dated:- 14-06-2019
| 186 | III | 24.10.2018 | LUP0831 | Construction of Double lane approach road to AIIMS at Awantipora upto G-2nd level ( phase 1st from Islamic university to AIIMS) | SS | Road | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 114.87 | 2017-02-01 |  | 31.974 | 35.5263 | 100% | 100% |  |  | 31.974 | 2019-07-08 | [12 empty] | 31.974 | 3.5523 | 79.3437 |  | 2020-10-01
| 187 | IV | 20.11.2018 | LUP1260 | Construction of 1.30 Mtr span plate girder bridge on Chewa Chaankitar road at Chaankitar | SS | Bridge | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 93.27 | 2015-05-01 | 307.85 | 75.435 | 83.8158 | 100% | 100% |  |  | 28.182 | 2019-07-01 | 47.253 | 2020-08-17 | [10 empty] | 75.435 | 8.3808 | 9.4542 |  | 2020-06-01
| 188 | IV | 20.11.2018 | LUP1261 | Construction of 1x60 Mtr span truss girder bridge over Sasar Nallah at Arabal on Bellow Arabal Nikas road | SS | Bridge | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo | 712.03 | 214.15 | 2015-06-01 |  | 185.753 | 206.3902 | 100% | 100% |  |  | 20.489 | 2019-12-17 | 126.939 | 2020-08-03 | 38.325 | 2020-12-19 | [8 empty] | 185.753 | 20.6372 |  |  | 2020-10-01
| 189 | IV | 20.11.2018 | LUP1262 | Construction of R&B Divisional Office at Rajpora, Pulwama | SS | NFB | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 92.1 | 2015-08-01 |  | 79.658 | 88.508 | 100% | 100% |  |  | 17.785 | 2019-12-24 | 22.205 | 2020-08-03 | 39.668 | 2021-01-29 | [8 empty] | 79.658 | 8.85 |  | 2020-11-01 | 2020-12-01
| 190 | IV | 20.11.2018 | LUP1264 | Construction of road from NH-44 to group centre CRPF & Commando Training Centre J&K Police CTC Lethpora ( Lethpora – Barsoo- Loop) | SS | Road | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 360.19 | 2017-03-01 |  | 247.223 | 274.6895 | 100% | 100% |  |  | 86.913 | 2019-09-18 | 3.12 | 2019-12-17 | 157.19 | 2020-01-12 | [8 empty] | 247.223 | 27.4665 |  |  | 2020-10-01
| 191 | V | 12.12.2018 | LUP1526 | Upgrd of Damhal Larve Narbal road with allied links | SS | Road | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 261.88 | 2017-02-01 |  | 221.336 | 245.9264 | 100% | 100% |  |  | 39.276 | 2020-02-14 | 131.083 | 2020-09-03 | 50.977 | 2020-01-05 | [8 empty] | 221.336 | 24.5904 |  |  | 2020-09-01
| 192 | V | 12.12.2018 | LUP1528 | Strengthening/upgrd of Pahoo Chakpora road incld. Narbal Hakripora road, allied links & Pahoo Dogam road | SS | Road | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 299.09 | 2017-03-01 |  | 162.962 | 181.0671 | 100% | 69% |  |  | 45.377 | 2020-03-06 | 117.585 | 2020-09-03 | [10 empty] | 162.962 | 18.1051 |  | 2020-11-01 | 2020-12-01
| 193 | V | 12.12.2018 | LUP1529 | Upgrd of Wagum to Uricharsoo and Prichoo Wagum road with allied links via Degree College | SS | Road | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 347.43 | 2017-03-01 |  | 241.233 | 268.034 | 100% | 100% |  |  | 80.204 | 2019-09-27 | 19.52 | 2020-02-06 | 27.196 | 2020-09-09 | 114.313 | 2020-12-15 | [6 empty] | 241.233 | 26.801 | 79.396 |  | 2020-10-01
| 194 | V | 12.12.2018 | LUP1531 | Strengthening/upgrd of roads near Ziyarat Sharief Awantipora incld. Storm Water Drain | SS | Road | R&B | Kashmir | Pulwama | Pulwama | Mohammad Yousuf Tramboo |  | 288.08 | 2016-10-01 |  | 138.651 | 154.0551 | 100% | 100% |  | 34.5 | 67.965 | 2019-10-18 | 32.676 | 2020-03-04 | 38.01 | 2020-08-21 | [8 empty] | 138.651 | 15.4041 |  |  | 2020-10-01
| 195 | I | 03.10.2018 | LUP0111 | Constr of Bridge over Nallah Kraloo on Kraloo Uril road | SS | Bridge | R&B | Kashmir | Kulgam | Qazigund | Basharat Jaleel Bhat |  | 94.39 | 2012-09-01 |  | 75.832 | 84.2569 | 100% | 100% |  |  | 56.579 | 2019-06-12 | 19.253 | 2020-03-31 | [10 empty] | 75.832 | 8.4249 | 10.1331 |  | 2019-20 | 1) NIT No. 71/EEQ/2017-18/3585-99 Dated 28-08-2017 | 2021-01-01
| 196 | I | 03.10.2018 | LUP0112 | Construction of 1x30 Mtr span steel trussed bridge over Kraloo Nallah in Km 1st of Y.K.Pora to Batnagoo via Peer Takiya road ( Peer Takiya Bridge) | SS | Bridge | R&B | Kashmir | Kulgam | Qazigund | Basharat Jaleel Bhat |  | 108.17 | 2012-08-01 |  | 87.273 | 96.969 | 100% | 100% |  |  | 49.735 | 2019-06-12 | 37.538 | 2019-10-24 | [10 empty] | 87.273 | 9.696 | 11.201 |  | 2019-20 | 1) NIT No. 67/EEQ/2018-19/3931-46 Dated 11-10-2018 2) NIT No. 78/EEQ/2018-19/4628-42 Dated 10-11-2018 3) NIT No. EEQ/15/2013-14/1149-63 Dated 06-06-2013 4) Order to Divisional General Manager SICOP-Srinagar Vide SE(PWD)R&B Circle Ang-Kulgam Vide No. 969-70 Dated 12-05-2014. | 2021-01-01
| 197 | I | 03.10.2018 | LUP0114 | Construction of 1x37 Mtr span girder bridge at Lalipora to Khanland ( balance cost) | SS | Bridge | R&B | Kashmir | Anantnag | Qazigund | Basharat Jaleel Bhat |  | 69.3 | 2012-09-01 |  | 54.59 | 60.6549 | 100% | 100% |  |  | 50.771 | 2019-10-04 | 3.819 | 2020-01-14 | [10 empty] | 54.59 | 6.0649 | 8.6451 |  | 2019-20 | 1) NIT-EEQ/19/2017-18/762-76 Dated 18-05-2017, 2) Supply order by CE(R&B) Kashmir Vide No. PS/11631-33 Dated 20-07-2011 to Divisonal Manager Project Engineer SICOP-srinagar | 2021-01-01
| 198 | I | 03.10.2018 | LUP0115 | Construction of 2x30 Mtr span steel girder bridge at Badasgam A to Badasgam B over Bud Khul | SS | Bridge | R&B | Kashmir | Anantnag | Qazigund | Basharat Jaleel Bhat |  | 225.27 | 2011-08-01 |  | 150.592 | 167.3228 | 100% | 100% |  |  | 80.524 | 2019-05-21 | 70.068 | 2019-12-09 | [10 empty] | 150.592 | 16.7308 | 57.9472 |  | 2019-20 | 1) NIT-114/EEQ/2017-18/6560 Dated 03-01-2018 2) Order No. 4933 Dated 22-11-2018 and Divisional Manager SICOP-Ang No. SICOP/DM/A/ 18-19/260-62 Dated 24-11-2018 3) Supply order by CE(R&B) Kashmir vide his No. PS/5525-27 Dated 30-05-2011 to Divisional Manager SICOP-Srinagar | 2021-01-01
| 199 | I | 03.10.2018 | LUP0123 | Construction of 2x30 mtr. Span steel girder bridge over Nallah Vethvathru in km 2nd of Babapora link road Phase 1st | SS | Bridge | R&B | Kashmir | Kulgam | Qazigund | Basharat Jaleel Bhat |  | 293.98 | 2012-07-01 |  | 258.829 | 287.5849 | 100% | 100% |  |  | 186.945 | 2019-07-08 | 71.884 | 2019-11-26 | [10 empty] | 258.829 | 28.7559 | 6.3951 |  | 2019-20 | 1) NIT No. 02/EEQ/2018-19/151-65 Dated 24-04-2018 2) NIT No. 50/EEQ/2017-18/2045-60 Dated 30-06-2017 3) NIT No. 40/EEQ/2012-13/3450-80 Dated 11-09-2012 4) Order to Divisional Manager SICOP-Anantnag Vide SE(PWD)R&B Circle Ang-Kulgam Vide No. 8204 Dated 22-01-2015 | 2021-01-01
| 200 | I | 03.10.2018 | LUP0124 | Construction of 2x30 Mtr span steel girder foot bridge over Nallah Sadran at Vessu Sadoora Chopan Mohalla | SS | Bridge | R&B | Kashmir | Anantnag | Qazigund | Basharat Jaleel Bhat |  | 155.62 | 2012-07-01 |  | 105.147 | 116.8288 | 100% | 87.8% |  |  | 105.147 | 2019-07-08 | [12 empty] | 105.147 | 11.6818 |  |  | 2020-08-01
| 201 | I | 03.10.2018 | LUP0125 | Construction of 1x30 Mtr span Jeepable foot bridge at Village Amanpora | SS | Bridge | R&B | Kashmir | Kulgam | Qazigund | Basharat Jaleel Bhat |  | 118.73 | 2011-11-01 |  | 96.741 | 107.4889 | 100% | 100% |  |  | 84.937 | 2019-06-12 | 11.804 | 2020-07-07 | [10 empty] | 96.741 | 10.7479 | 11.2411 |  | 2019-20 | 1)NIT No. 91/EEQ/2017-18/4782-95 Dated 14-10-2017 2) Order No. 4209 Dated 16-02-2015 to the Divisonal Manager SICOP-Anantang | 2021-01-01
| 202 | III | 24.10.2018 | LUP0756 | Construction of 3x30 Mtr span steel girder bridge at Nowpora Lonepora on nallah Sandran | SS | Bridge | R&B | Kashmir | Anantnag | Qazigund | Basharat Jaleel Bhat | 441.6 | 302.1 | 2011-09-01 |  | 215.881 | 239.8654 | 100% | 86% |  |  | 57.258 | 2020-01-14 | 56.862 | 2020-03-06 | 74.34 | 2020-06-25 | 27.421 | 2021-02-12 | [6 empty] | 215.881 | 23.9844 |  |  | 2020-10-01 |  | 2020-12-01
| 203 | I | 03.10.2018 | LUP0049 | Const of 40 mtr span steel Motorable bridge over Sukh Tawi at Irwan Khetar, Manjakote | SS | Bridge | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 253.37 | 137.57 | 08/2012 | 117.57 | 111.992 | 124.4343 | 100% | 100% |  |  | 49.05 | 2019-07-01 | 52.304 | 2020-03-31 | 10.638 | 2020-09-24 | [8 empty] | 111.992 | 12.4423 | 13.1357 |  | 2019-20 | e-NIT No. 86 of 2017-18 Dated:-04-01-2018 endorsment No : No :- EER/R&B/6/2017-18/11288-11317 dated : 04-01-2018
| 204 | I | 03.10.2018 | LUP0050 | 17 M Span Motorable bridge at Gurian Panihad | SS | Bridge | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 75 | 61 | 10/2012 | 61 | 31.518 | 35.0196 | 100% | 85% | 12.132 |  | 31.518 | 2020-10-01 | [12 empty] | 31.518 | 3.5016 |  |  | 2020-07-01
| 205 | I | 03.10.2018 | LUP0051 | 32M span LMV bridge near Jamia Masjid Manjakote [Dawain More Gulhati] | SS | Bridge | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 237.5 | 96.64 | 09/2012 | 96.67 | 56.355 | 62.616 | 100% | 100% |  |  | 31.524 | 2019-07-01 | 24.831 | 2020-09-03 | [10 empty] | 56.355 | 6.261 | 34.024 |  | 2019-20 | NIT No:- 76 of 2018-19 Dated:- 19-11-2018 (E-tendering) endorsment No : No :- 9700-29 & dated : 19- 11-2018
| 206 | I | 03.10.2018 | LUP0055 | Construction of 25.00 Mtr span foot Bridge at Sora Galla | SS | Bridge | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 180 | 114 | 07/2014 | 114 | 74.582 | 82.8681 | 100% | 84% |  |  | 25.937 | 2019-07-03 | 48.645 | 2020-04-15 | [10 empty] | 74.582 | 8.2861 |  |  | 2020-10-01
| 207 | I | 03.10.2018 | LUP0056 | 20 M Span Motorable bridge at Swari over Jamola Nallah | SS | Bridge | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 130.72 | 126.72 | 08/2015 | 126.72 | 108.1 | 120.1099 | 100% | 95% |  |  | 37.305 | 2019-08-23 | 27.117 | 2019-10-04 | 27.743 | 2020-06-25 | 15.935 | 2020-12-19 | [6 empty] | 108.1 | 12.0099 |  | 2020-12-01 | 2020-12-01
| 208 | III | 24.10.2018 | LUP0856 | Const. of road from Khalabat to Nowgran. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 252.6 | 176.85 | 06/2014 | 123.553 | 104.15 | 115.7211 | 100% | 80% |  |  | 39.661 | 2019-08-23 | 10.977 | 2020-07-07 | 17.737 | 2020-12-19 | 35.775 | 2021-02-19 | [6 empty] | 104.15 | 11.5711 |  |  | 2020-10-01
| 209 | III | 24.10.2018 | LUP0857 | Const. of road from Dassal to Dassal Seeran. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 198.35 | 136.6 | 06/2008 | 114.77 | 88.929 | 98.809 | 100% | 87% |  |  | 40.914 | 2019-09-18 | 37.08 | 2020-07-30 | 10.935 | 2020-01-11 | [8 empty] | 88.929 | 9.88 |  |  | 2020-11-01
| 210 | III | 24.10.2018 | LUP0862 | Const. of road from Kalali to Bhattian | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 239.47 | 191.85 | 08/2010 | 181.2 | 162.693 | 180.7682 | 100% | 100% |  |  | 130.95 | 2019-07-25 | 31.743 | 2020-03-31 | [10 empty] | 162.693 | 18.0752 | 11.0818 |  | 2019-20
| 211 | III | 24.10.2018 | LUP0868 | Const. of road from main road Phalyana to New colony Phalyana (Attal Colony). | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 103.05 | 79.55 | 10/2016 | 71.8 | 52.22 | 58.0216 | 100% | 80% |  |  | 21.62 | 2019-09-18 | 12.744 | 2020-01-27 | 17.856 | 2020-04-15 | [8 empty] | 52.22 | 5.8016 |  |  | 2020-08-01
| 212 | III | 24.10.2018 | LUP0870 | Const. of road Khandli Bridge to Thathi (Thanooni). | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 128.94 | 114.94 | '08/2011 | 108.879 | 97.962 | 108.8456 | 100% | 96% |  |  | 32.987 | 2019-10-24 | 39.775 | 2020-06-25 | 25.2 | 2020-12-24 | [8 empty] | 97.962 | 10.8836 |  |  | 2020-10-01
| 213 | III | 24.10.2018 | LUP0871 | Const. of road from Prori Panihad road to H.S at Panihad ( Missing link). | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 145.93 | 109.93 | 09/2014 | 109.5 | 93.112 | 103.4567 | 100% | 96% |  |  | 35.937 | 2019-07-25 | 36.925 | 2020-03-31 | 20.25 | 2020-12-24 | [8 empty] | 93.112 | 10.3447 |  |  | 2020-11-01
| 214 | III | 24.10.2018 | LUP0872 | Const. of road from Sarano to PEO Manyalan. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 143.46 | 111.46 | 09/2010 | 109.46 | 77.17 | 85.7436 | 100% | 83% |  |  | 31.652 | 2019-09-12 | 35.244 | 2020-01-01 | 10.274 | 2020-06-25 | [8 empty] | 77.17 | 8.5736 |  |  | 2020-11-01
| 215 | III | 24.10.2018 | LUP0873 | Const. of road from Potha to Androlla | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 185 | 141.75 | 07/2006 | 134.7 | 60.967 | 67.7404 | 100% | 84% | 34.334 |  | 29.996 | 2020-01-14 | 30.971 | 2020-07-27 | [10 empty] | 60.967 | 6.7734 |  |  | 2020-11-01
| 216 | III | 24.10.2018 | LUP0875 | Dhangri Dalhori Road and Extension upto Kanthol. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 207.1 | 116.1 | 08/2008 | 114.6 | 81.126 | 90.1391 | 100% | 88% |  |  | 32.48 | 2020-02-03 | 48.646 | 2020-09-24 | [10 empty] | 81.126 | 9.0131 |  |  | 2020-09-01
| 217 | III | 24.10.2018 | LUP0876 | Const. of road from Mohalla Chowdhary Gulzar Ahmed (Ex-MLC_) to Baba Jammu Sahib in village Dhanore dhidian Tehsil and DisttRajouri. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 65 | 48.5 | 08/2014 | 46.93 | 43.536 | 48.3728 | 100% | 100% |  |  | 7.749 | 2019-05-10 | 20.597 | 2019-07-23 | 12.966 | 2019-11-26 | 2.224 | 2020-03-31 | [6 empty] | 43.536 | 4.8368 | 0.12715 |  | 2019-20 | NIT No:- 76 of 2018-19 Dated:- 19-11-2018 (E-tendering) endorsment No : No :- 9700-29 & dated : 19- 11-2018
| 218 | III | 24.10.2018 | LUP0877 | Const. of road from Badhoon Crusher to Khui Draman. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 114.6 | 108.6 | 07/2005 | 106.17 | 95.395 | 105.9934 | 100% | 100% |  |  | 33.558 | 2019-05-17 | 20.295 | 2019-07-23 | 40.35 | 2019-12-09 | 1.192 | 2020-06-25 | [6 empty] | 95.395 | 10.5984 | 2.6066 |  | 2019-20 | NIT No:- 78 of 2018-19 Dated:- 27-11-2018endorsment No : No :- 9866-9895 & dated : 27- 11-2018
| 219 | III | 24.10.2018 | LUP0882 | Const. of link road from PMGSY Chalal Bagla Sabzi to Danna. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 76.76 | 69.26 | 10/2009 | 67.95 | 48.446 | 53.8284 | 100% | 80% |  |  | 15.03 | 2019-09-05 | 8.298 | 2020-02-03 | 25.118 | 2020-01-11 | [8 empty] | 48.446 | 5.3824 |  | 2021-03-01 | 2020-12-01
| 220 | III | 24.10.2018 | LUP0888 | Const. of missing link to connect Sokar Gali with PMGSY Ujhan to Leeran. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 114.6 | 75 | 09/2012 | 73.88 | 43.515 | 48.3495 | 100% | 67% |  |  | 17.308 | 2019-07-03 | 20.736 | 2020-02-03 | 5.471 | 2020-01-11 | [8 empty] | 43.515 | 4.8345 |  |  | 2020-11-01
| 221 | III | 24.10.2018 | LUP0892 | Upgradation of link road of BGSB University. | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 190 | 172.5 | 06/2006 | 172.5 | 147.173 | 163.5239 | 100% | 100% |  |  | 146.633 | 2019-09-05 | 0.54 | 2020-09-24 | [10 empty] | 147.173 | 16.3509 | 8.9761 |  | 2019-20 | NIT No:- 03 of 2019-20 Dated:- 19-04-2019 Endorsment NO : 591-620 Dated : 19-4-2019
| 222 | VI | 28.02.2019 | LUP1933 | Const. of VIP suit in PWD Dak Bungalow at Koteranka | SS | NFB | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 108.83 | 91.83 | 09/2015 | 90.95 | 75.015 | 83.3492 | 100% | 95% |  |  | 52.65 | 2019-09-05 | 22.365 | 2020-03-31 | [10 empty] | 75.015 | 8.3342 |  |  | 2019-20
| 223 | VI | 28.02.2019 | LUP1935 | Const. of Ujhan Darhal Kandi Road | SS | Road | R&B | Jammu | Rajouri | Rajouri | Sh. Mohd Zubair | 634.7 | 502.64 | 06/2010 | 407.8 | 340.407 | 378.2262 | 100% | 81% |  |  | 288.603 | 2020-10-29 | 51.804 | 2021-02-19 | [10 empty] | 340.407 | 37.8192 |  |  | 2020-11-01
| 224 | VI | 28.02.2019 | LUP1948 | Const. of Hewaga Neel Road | SS | Road | R&B | Jammu | Ramban | Ramban | Maqbool Hussain | 220.94 | 60.4 | 05/2013 | 52 | 38.97 | 43.2996 | 100% | 100% |  |  | 18 | 2020-02-06 | 10.44 | 2020-03-31 | 10.53 | 2020-12-19 | [8 empty] | 38.97 | 4.3296 | 17.1004 |  | 2020-07-01
| 225 | VI | 28.02.2019 | LUP1949 | Sangaldan Kanthan Road | SS | Road | R&B | Jammu | Ramban | Ramban | Maqbool Hussain | 162.11 | 99.11 | 06/2007 | 47.89 | 43.091 | 47.8784 | 100% | 98% |  |  | 24.461 | 2020-01-20 | 18.63 | 2020-10-01 | [10 empty] | 43.091 | 4.7874 |  |  | 2020-07-01
| 226 | VI | 28.02.2019 | LUP1950 | Const.of Bus Stand at Ukhral | SS | Road | R&B | Jammu | Ramban | Ramban | Maqbool Hussain | 180 | 170 | 05/2015 | 130 | 112.4 | 124.8876 | 100% | 79% |  |  | 30.622 | 2020-01-20 | 18.441 | 2020-10-21 | 63.337 | 2020-12-31 | [8 empty] | 112.4 | 12.4876 |  |  | 2020-09-01
| 227 | VI | 28.02.2019 | LUP1951 | Banihal Lamber Road | SS | Road | R&B | Jammu | Ramban | Ramban | Maqbool Hussain | 281.78 | 266.78 | 06/1980 | 180 | 179.279 | 199.1969 | 100% | 100% |  |  | 97.2 | 2019-12-23 | 19.691 | 2020-02-14 | 55.026 | 2020-07-27 | 7.362 | 2020-10-21 | [6 empty] | 179.279 | 19.9179 | 67.5831 |  | 2020-07-01
| 228 | VI | 28.02.2019 | LUP1952 | Const. of 50 mtr span Motorable Bridge over Bishlari Nallah & Approach Road to Degree College Banihal | SS | Bridge | R&B | Jammu | Ramban | Ramban | Maqbool Hussain | 250 | 169 | 06/2018 | 169 | 95.4 | 105.9989 | 100% | 80% |  |  | 95.4 | 2020-01-27 | [12 empty] | 95.4 | 10.5989 |  |  | 2020-10-01
| 229 | V | 12.12.2018 | LUP1533 | Const. of Road from Reasi at Kayala L-3.90 kms | SS | Road | R&B | Jammu | Reasi | Reasi | Er. Janak Raj | 418.55 | 215.65 | 04/2004 | 234.73 | 126.032 | 140.0342 | 100% | 100% |  |  | 37.963 | 2019-10-24 | 62.081 | 2020-01-20 | 25.988 | [9 empty] | 126.032 | 14.0022 | 75.6158 |  | 2020-09-01
| 230 | V | 12.12.2018 | LUP1537 | Construction of Ransoo to Kotla Road | SS | Road | R&B | Jammu | Reasi | Reasi | Er. Janak Raj | 287.8 | 371.55 | 05/2004 | 142.44 | 208.023 | 231.1344 | 100% | 100% |  |  | 52.724 | 2019-11-26 | 36.736 | 2020-01-20 | 46.753 | 2020-09-24 | 71.81 | 2020-10-21 | [6 empty] | 208.023 | 23.1114 | 140.4156 |  | 2020-09-01
| 231 | V | 12.12.2018 | LUP1540 | Const. of Road from Karwa to Kotli Road L=5 km | SS | Road | R&B | Jammu | Reasi | Reasi | Er. Janak Raj | 296.28 | 280.78 | 06/1989 | 257.12 | 231.412 | 257.1219 | 100% | 100% |  |  | 38.886 | 2020-02-03 | 36.466 | 2020-07-30 | 156.06 | 2020-12-10 | [8 empty] | 231.412 | 25.7099 | 23.6581 |  | 2020-09-01
| 232 | V | 12.12.2018 | LUP1542 | 120 m span steel plate girder bridge on River Ballani & 30 mtr span steel girder Bridge over Balganga Nallah near Village Kanjli, Reasi | SS | Bridge | JKPCC | Jammu | Reasi | Reasi | Er. Janak Raj | 996 | 266.9 | 02/2008 | 182.9 | 188.579 | 209.5301 | 100% | 100% |  |  | 89.519 | 2020-07-07 | 41.262 |  | 57.798 | 2021-01-01 | [8 empty] | 188.579 | 20.9511 |  |  | 2020-11-01
NS | 233 | I | 03.10.2018 | LUP0036 | Const. of 132 m span foot suspension bridge over River Sasanter at Hunded | SS | Bridge | R&B | Jammu | Samba | Samba | Rajesh Abrol | 190.16 | 18.66 | 4/2009 | 18.66 | 0 | 0 | 100% | [17 empty] | 0 | 0 |  | 2021-03-01 | 2021-01-01 |  | 2021-01-01
| 234 | I | 03.10.2018 | LUP0037 | Const.of 10 mtr span bridge at kaluchak purmandal road Km 1st Distt Samba | SS | Bridge | R&B | Jammu | Samba | Samba | Rajesh Abrol | 75 | 20 | 4/2015 | 14.93 | 9.109 | 10.121 | 100% | 100% |  |  | 9.109 | 2020-08-03 | [12 empty] | 9.109 | 1.012 | 9.879 |  | 2019-20 | 86 of 2018-19 Dt. 13-12-2018 | 2020-05-01
| 235 | I | 03.10.2018 | LUP0038 | Const. of 25 mtr span vented causeway on Nallah at Ban Khad nera Masjid | SS | Bridge | R&B | Jammu | Samba | Samba | Rajesh Abrol | 75 | 45.76 | 04/2016 | 33.95 | 25.911 | 28.7897 | 100% | 100% |  |  | 21.096 | 2020-01-14 | 4.815 | 2020-03-13 | [10 empty] | 25.911 | 2.8787 | 16.9703 |  | 2019-20 | 16 of 2019-20 dt. 21-05-2019 | 2020-02-01
| 236 | III | 24.10.2018 | LUP0901 | Const. of Circular road at village Abtal | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 84.45 | 42.95 | 04/2004 | 32.8 | 28.791 | 31.9897 | 100% | 100% |  |  | 22.779 | 2019-11-26 | 6.012 | 2020-03-31 | [10 empty] | 28.791 | 3.1987 | 10.9603 |  | 2019-20 | 02 of 2019-20 Dt. 23-04-2019 & 91 of 2018-19 Dt. 27-12-2018 | 2019-07-01
| 237 | III | 24.10.2018 | LUP0903 | Link road Bain Glad to Basantar | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 84 | 44.5 | 04/2009 | 42.66 | 34.611 | 38.4563 | 100% | 100% |  |  | 10.77 | 2020-03-13 | 23.841 | 2020-09-03 | [10 empty] | 34.611 | 3.8453 | 6.0437 |  | 2020-06-01 |  | 2020-06-01
| 238 | III | 24.10.2018 | LUP0904 | const. of link road from Nallah to Nallah Dalhote | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 52 | 18.25 | 05/2011 | 18.25 | 12.672 | 14.0799 | 100% | 92% |  |  | 12.672 | 2020-09-24 | [12 empty] | 12.672 | 1.4079 |  |  | 2020-10-01 |  | 2020-10-01
| 239 | III | 24.10.2018 | LUP0906 | Const. of Ramgarh to Rudwan road | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 52 | 26.89 | 04/2011 | 17.94 | 16.147 | 17.9409 | 100% | 100% |  |  | 16.034 | 2019-09-27 | 0.113 | 2020-08-03 | [10 empty] | 16.147 | 1.7939 | 8.9491 |  | 2019-20 | 91 of 2018-19 Dt. 27-12-2018 | 2019-06-01
| 240 | III | 24.10.2018 | LUP0907 | Mahal Adda to Mahalshan including link road Ramgarh to Rudwan | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 230 | 24 | 04/2010 | 18.92 | 12.525 | 13.9165 | 100% | 100% |  |  | 12.416 | 2019-09-27 | 0.109 | 2020-08-03 | [10 empty] | 12.525 | 1.3915 | 10.0835 |  | 2019-20 | 91 of 2018-19 Dt. 27-12-2018 | 2019-06-01
| 241 | III | 24.10.2018 | LUP0909 | Const. of link road to Shamshan Ghat at Vijaypur | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 70 | 44.75 | 05/2009 | 34.37 | 28.719 | 31.9097 | 100% | 100% |  |  | 9.639 | 2019-09-27 | 19.08 | 2020-03-04 | [10 empty] | 28.719 | 3.1907 | 12.8403 |  | 2019-20 | 50 of 2018-19 Dt. 24-07-2018 & 02 of 2019-20 Dt. 23-04-2019 | 2019-09-01
| 242 | V | 12.12.2018 | LUP1543 | Const.of Chak Salarian to Raraian Road | SS | Road |  | Jammu | Samba | Samba | Rajesh Abrol | 142.9 | 100.4 | 04/2009 | 75.67 | 56.214 | 62.4594 | 100% | 100% |  |  | 51.489 | 2019-12-17 | 4.725 | 2020-03-13 | [10 empty] | 56.214 | 6.2454 | 37.9406 |  | 2019-20 | 10 of 2019-20 Dt. 10-06-2019 | 2019-12-01
| 243 | V | 12.12.2018 | LUP1545 | Const. of link road of Baba Chamlial | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 59.71 | 25.21 | 04/2009 | 21.99 | 22.448 | 24.942 | 100% | 100% |  |  | 19.809 | 2019-10-24 | 2.639 | 2020-08-03 | [10 empty] | 22.448 | 2.494 | 0.26803 |  | 2019-20 | 10 of 2019-20 Dt. 10-06-2019 | 2019-09-01
| 244 | V | 12.12.2018 | LUP1547 | Const of link road from main road to Temple at patti incl. link road to Jogi Mohalla Smailpur | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 260.5 | 195.7 | 04/2012 | 162.46 | 67.441 | 74.9337 | 100% | 54% |  |  | 52.281 | 2020-08-11 | 15.16 | 2020-01-11 | [10 empty] | 67.441 | 7.4927 |  |  | 2020-11-01
| 245 | V | 12.12.2018 | LUP1548 | Samba Pangdour road incl. link road to Katli | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 247.83 | 165.33 | 04/2010 | 165.33 | 143.901 | 159.8884 | 100% | 98% |  |  | 134.991 | 2020-01-20 | 8.91 | 2020-07-27 | [10 empty] | 143.901 | 15.9874 |  |  | 2019-20 | 07 of 2019-20 Dt. 04-05-2019 | 2020-02-01
| 246 | V | 12.12.2018 | LUP1549 | upgradation of link road to Kamala and Radha Swami Ashram | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 139.8 | 105.8 | 04/2011 | 75.01 | 54.346 | 60.3838 | 100% | 68% |  |  | 30.119 | 2019-09-12 | 24.227 | 2020-12-19 | [10 empty] | 54.346 | 6.0378 |  |  | 2020-10-01 |  | 2020-10-01
| 247 | V | 12.12.2018 | LUP1552 | Const. of link road from smailpur to Patti Kheddian road including link road to Sanarki Plotta and Kotli | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 298 | 192.5 | 04/2009 | 145.21 | 102.864 | 114.2922 | 100% | 100% |  |  | 32.126 | 2019-12-17 | 14.697 | 2020-07-29 | 45.9 | 2020-09-03 | 10.141 | 2020-10-29 | [6 empty] | 102.864 | 11.4282 | 78.2078 |  | 2020-09-01 |  | 2020-09-01
| 248 | V | 12.12.2018 | LUP1553 | Imp. Of link road from village Trindi (Sarva) | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 119.87 | 87.07 | 04/2009 | 72.68 | 46.302 | 51.4462 | 100% | 100% |  |  | 46.17 | 2019-11-26 | 0.132 | 2020-08-11 | [10 empty] | 46.302 | 5.1442 | 35.6238 |  | 2019-20 | 10 of 2019-20 Dt. 10-05-2019 & 93 of 2018-19 Dt. 03-01-2018 | 2019-12-01
| 249 | V | 12.12.2018 | LUP1554 | Imptt. Upgdtt. Of Ghagwal to Rajpura Road | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 230 | 144.5 | 05/2010 | 141.88 | 114.447 | 127.1621 | 100% | 93% |  |  | 76.284 | 2020-03-31 | 5.864 | 2020-07-27 | 32.299 | 2020-09-03 | [8 empty] | 114.447 | 12.7151 |  |  | 2020-06-01 |  | 2020-06-01
| 250 | V | 12.12.2018 | LUP1556 | Const.of link road to Baba Sidh Gorian (Goran Chak) | SS | Road | R&B | Jammu | Samba | Samba | Rajesh Abrol | 57.15 | 30.1 | 04/2009 | 30 | 26.685 | 29.6497 | 100% | 100% |  |  | 13.59 | 2019-09-27 | 13.095 | 2020-09-24 | [10 empty] | 26.685 | 2.9647 | 0.4503 |  | 2020-06-01 |  | 2020-06-01
| 251 | III | 24.10.2018 | LUP0910 | Constr. Of 2x25 Mtr span bridge over Tongir Nallah in Km 3rd of Chitragam Rebbon Road | SS | Bridge | R&B | Kashmir | Shopian | Shopian | Abdul Qayoom Kirmani |  | 189 | 2013-01-01 |  | 162.73 | 180.8093 | 100% | 100% |  |  | 55.832 | 2019-10-04 | 106.898 | 2020-08-11 | [10 empty] | 162.73 | 18.0793 | 8.1907 |  | 2019-20
| 252 | III | 24.10.2018 | LUP0911 | Launching of 2x24 Mtr baily Bridge on Trenz Sheikhpora Road | SS | Bridge | R&B | Kashmir | Shopian | Shopian | Abdul Qayoom Kirmani |  | 58.35 | 2014-11-01 |  | 49.79 | 55.3217 | 100% | 100% |  |  | 8.411 | 2019-11-26 | 12.725 | 2019-12-23 | 10.384 | 2020-03-04 | 18.27 | 2020-08-11 | [6 empty] | 49.79 | 5.5317 | 3.0283 |  | 2019-20 | 1)164/6873-83 Dtd:- 23-09-2015, (2)184 of 2015-16 Dtd:- 05/2015, (3) 73 of 2016-17 Dtd:- 10/2016, (4) 75/4540-50 Dtd:- 20-09-2019.
| 253 | III | 24.10.2018 | LUP0912 | Construction of circuit house at Padpawan Shopian | SS | NFB | R&B | Kashmir | Shopian | Shopian | Abdul Qayoom Kirmani |  | 57.13 | 2006-09-01 |  | 51.298 | 56.9972 | 100% | 100% |  |  | 3.734 | 2019-08-23 | 10.539 | 2019-10-24 | 37.025 | 2020-08-03 | [8 empty] | 51.298 | 5.6992 | 0.13279 |  | 2020-06-01 | 2)184 of 2015-16 Dtd:- 05/2015
| 254 | V | 12.12.2018 | LUP1559 | Upgrd of Narwaw to Reshnagri Kanjiullar Gadipora road | SS | Road | R&B | Kashmir | Shopian | Shopian | Abdul Qayoom Kirmani |  | 100 | 2015-11-01 |  | 86.388 | 95.9857 | 100% | 96% |  |  | 79.636 | 2019-11-26 | 6.752 | 2020-02-17 | [10 empty] | 86.388 | 9.5977 |  |  | 2019-20 | 1) 54/4107-32 Dtd:- 20-01-2014, (2) 20/1589-1615 Dtd:- 24-06-2015, (3) 159 of 09/2015, (4) 52/3932-57 Dtd:- 15-10-2014, (5) 13 of 2019-20 Dtd:- 13-05-2019.
| 255 | I | 03.10.2018 | LUP0129 | Construction of 1x100 Mtr Span Suspension Foot Bridge over Nallah Pohru at Seelu connecting Seelu with Hib Dangerpora | SS | Bridge | R&B | Kashmir | Baramulla | Sopore | S. Gurdev singh |  | 83.29 | 2011-03-01 |  | 72.512 | 80.5681 | 100% | 100% |  |  | 67.566 | 2019-11-26 | 4.946 | 2020-08-21 | [10 empty] | 72.512 | 8.0561 | 2.7219 |  | 2019-20 | NIT No 29 of 19-20/2645-65 dated 03-06-2019 and SICOP/MM/17-18/1794 dated 31-03-18
| 256 | III | 24.10.2018 | LUP0767 | Upgradation of Wadoora Bala and Wadoora Payeen with allied links | SS | Road | R&B | Kashmir | Baramulla | Sopore | S. Gurdev singh |  | 270.81 | 2011-09-01 |  | 172.931 | 192.1436 | 100% | 100% |  |  | 114.516 | 2019-09-12 | 41.111 | 2019-12-17 | 17.304 | 2020-12-22 | [8 empty] | 172.931 | 19.2126 |  |  | 2019-20 | NIT No 7 of 19-20/808-27 dated 23-04-2019 and 222/17401-20 dated 04-01-2019
| 257 | III | 24.10.2018 | LUP0768 | Upgradation of inner links at Warapora | SS | Road | R&B | Kashmir | Baramulla | Sopore | S. Gurdev singh |  | 457.92 | 2011-07-01 |  | 269.61 | 299.5637 | 100% |  |  |  | 134.766 | 2019-09-12 | 67.915 | 2019-11-26 | 7.599 | 2020-07-27 | 59.33 | 2020-10-29 | [6 empty] | 269.61 | 29.9537 |  |  | 2020-10-01
| 258 | I | 03.10.2018 | LUP0107 | Construction of proposed single lane plate girder steel bridge at Banyari Hajin ( 80 Mtr) | SS | Bridge | JKPCC | Kashmir | Bandipora | Sumbal | Hamid Ahmad Bhat |  | 37.24 | 2009-06-01 |  | 30.618 | 34.0197 | 100% | 95% |  |  | 30.618 | 2020-08-03 | [12 empty] | 30.618 | 3.4017 |  |  | 2019-20
| 259 | III | 24.10.2018 | LUP0800 | Re-Constr. Of damaged portion of EEs Quarter at Gomal Tanghdar | SS | NFB | R&B | Kashmir | Kupwara | Tangdar | ER.Manzoor Ahamed Sheikh |  | 52.22 | 2012-03-01 |  | 46.998 | 52.2195 | 100% | 100% |  |  | 11.905 | 2019-10-23 | 7.496 | 2019-12-24 | 15.444 | 2020-03-04 | 12.153 | 2020-09-18 | [6 empty] | 46.998 | 5.2215 | 0.0005222 |  | 2019-20 | 39 fo 2018-19 dated 11-08-18, 28 of 2019-20 dated 10-07-19, 24 of 2019-20 dated 26-06-20
| 260 | I | 03.10.2018 | LUP0045 | 20 mtr span girder m/able bridge in nallah Thathli Saddal km 9th RD 0-100 on Kainthgali Bhamag. | SS | Bridge | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 107.16 | 27.28 | 06/2013 | 27.28 | 14.238 | 15.8198 | 100% | 78% |  |  | 14.238 | 2019-09-18 | [12 empty] | 14.238 | 1.5818 |  |  | 2019-20 | ENIT No 157 of 3/2013 dated 04-03-13
| 261 | II | 10.10.2018 | LUP0475 | 35.00 Mtr. Span foot bridge over Nallah Bowl at Village Gorahan Block Ghordi Tehsil Ramnagar | SS | Bridge | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 80 | 49.6 | 09/2018 | 51.29 | 33.696 | 37.4396 | 100% | 100% |  |  | 33.696 | 2020-02-27 | [12 empty] | 33.696 | 3.7436 | 12.1604 |  | 2019-20 | ENIT No 8 of 5/2018 dated 08-05-18
| 262 | II | 10.10.2018 | LUP0477 | Const of 43.00 mtrs span truss bridge (through type) over Birwannallah at Chakhar connecting village Debrah | SS | Bridge | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 262.6 | 247.6 | 10/2018 | 138.89 | 111.501 | 123.8888 | 100% | 70% |  |  | 57.744 | 2019-09-18 | 53.757 | 2020-07-27 | [10 empty] | 111.501 | 12.3878 |  |  | 2020-07-01
| 263 | III | 24.10.2018 | LUP0918 | Improvement/Upgradation of road from Suketar to Upper Badana in Kud Tehsil Chenani Distt. Udhampur ( L=1.50 km). | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 208.35 | 170.85 | 01/2014 | 120.66 | 108.854 | 120.9477 | 100% | 70% |  |  | 33.569 | 2019-07-16 | 32.796 | 2019-12-09 | 25.371 | 2020-01-01 | 17.118 | 2020-07-10 | [6 empty] | 108.854 | 12.0937 |  |  | 2020-07-01
| 264 | III | 24.10.2018 | LUP0920 | Shatral to SC Basti Swalta village Tajoor ( L=2.20 Km) | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 149.75 | 126.95 | 04/2012 | 87.77 | 78.696 | 87.4391 | 100% | 77% |  |  | 25.812 | 2019-09-27 | 52.884 | 2020-10-14 | [10 empty] | 78.696 | 8.7431 |  |  | 2020-07-01
| 265 | V | 12.12.2018 | LUP1560 | Const . Of Road from Bhati to Malli Via Jasarkote | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 384.42 | 345.42 | 06/2017 | 246.93 | 90.364 | 100.4034 | 100% | 78% | 80.025 |  | 48.6 | 2019-11-26 | 41.764 | [11 empty] | 90.364 | 10.0394 |  | 2020-12-01 | 2020-12-01 | 2) 20/1589-1615 Dtd:- 24-06-2015
| 266 | V | 12.12.2018 | LUP1562 | Road from Sui to Bassian via Barigarh L-1 kms | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 221.47 | 200.97 | 08/2009 | 109.99 | 92.916 | 103.239 | 100% | 74% |  |  | 30.303 | 2019-10-24 | 40.68 | 2019-11-26 | 21.933 | 2020-10-21 | [8 empty] | 92.916 | 10.323 |  |  | 2020-07-01 | 4) 52/3932-57 Dtd:- 15-10-2014
| 267 | V | 12.12.2018 | LUP1565 | Const.of Road from Salmeri to Balli Towards Krimchi Panchyat Sial jattan (Udhampur) incl. link road to Tope | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 218.52 | 197.02 | 09/2009 | 138.45 | 111.661 | 124.0665 | 100% | 80% |  |  | 69.264 | 2020-03-12 | 26.62 |  | 15.777 | 2021-01-28 | [8 empty] | 111.661 | 12.4055 |  |  | 2020-09-01
| 268 | V | 12.12.2018 | LUP1569 | Road from Battal Ballian Bye pass Nh 44 to Roun Domail L=5.25 kms | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 389.57 | 370.07 | 07/2014 | 258.45 | 229.763 | 255.2897 | 100% | 80% |  |  | 59.465 | 2019-07-08 | 71.784 | 2019-10-18 | 74.205 | 2020-01-01 | 24.309 | 2020-05-23 | [6 empty] | 229.763 | 25.5267 |  |  | 2020-07-01
| 269 | V | 12.12.2018 | LUP1570 | Cherri Sial to Kawa road | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 158 | 140 | 04/2008 | 83.7 | 77.093 | 85.658 | 100% | 76% |  |  | 33.561 | 2019-11-26 | 18.872 | 2020-05-23 | 24.66 | 2020-07-07 | [8 empty] | 77.093 | 8.565 |  |  | 2020-07-01
| 270 | VI | 28.02.2019 | LUP1956 | Const. / upgradation of Road from CEO office Udhampur to Mohalla Dhandyal | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 87.46 | 70.47 | 04/2018 | 53.22 | 35.7 | 39.6663 | 100% | 65% |  |  | 15.651 | 2020-07-07 | 20.049 | 2020-12-24 | [10 empty] | 35.7 | 3.9663 |  |  | 2020-10-01
| 271 | VI | 28.02.2019 | LUP1957 | Const. of Road to Village Upper Badole via PTC Nalanda Academy Udhampur | SS | Road | R&B | Jammu | Udhampur | Udhampur | Pawan Kumar | 190.03 | 175.65 | 08/2009 | 117.98 | 102.91 | 114.3433 | 100% | 100% |  |  | 27.342 | 2019-09-18 | 31.36 | 2020-09-03 | 44.208 | 2020-12-14 | [8 empty] | 102.91 | 11.4333 | 61.3067 |  | 2020-09-01
| 272 | I | 03.10.2018 | LUP0135 | Constr of single lane 60 mtr steel trussed Bridge at River Jehlum at Peernai Uri | SS | Bridge | JKPCC | Kashmir | Baramulla | Uri | Nisar Ahmad Pandit |  | 42.13 | 2010-07-01 |  | 23.949 | 26.6097 | 100% | 100% |  |  | 23.949 | 2019-12-09 | [12 empty] | 23.949 | 2.6607 | 15.5203 |  | 2019-20 | Issuance Date 15-05-2019. No. SSDU/ 2019/ 317-22.
| 273 | I | 03.10.2018 | LUP0116 | Construction of 2 x 20 M span girder Bridge over Nallah Grawan near Syedpora Kharati Vailoo | SS | Bridge | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat | 261.85 | 123.04 | 2014-08-01 |  | 91.746 | 101.939 | 100% | 93% |  |  | 87.669 | 2020-01-01 | 4.077 | 2020-08-20 | [10 empty] | 91.746 | 10.193 |  |  | 2020-10-01 |  | 2020-10-01
| 274 | I | 03.10.2018 | LUP0117 | Construction of 1x30 Mtr Span Steel Trussed bridge over Nallah Aripath in Km 10th of Gopalpora Tailwani Issue Wangam Shangus road | SS | Bridge | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 68 | 2014-08-01 |  | 49.112 | 54.5683 | 100% | 100% |  |  | 33.111 | 2020-08-03 | 16.001 | 2020-10-21 | [10 empty] | 49.112 | 5.4563 | 13.4317 |  | 2019-20 |  | 2020-03-01
| 275 | IV | 20.11.2018 | LUP1208 | Construction of 2 x25 mtr span steel girder bridge over Nallah Bringi at Village Poru Goihard | SS | Bridge | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 46 | 2011-07-01 |  | 30.122 | 33.4686 | 100% | 100% |  |  | 16.217 | 2019-07-16 | 5.733 | 2020-07-29 | 8.172 | 2020-10-21 | [8 empty] | 30.122 | 3.3466 | 12.5314 |  | 2019-20 |  | 2019-09-01
| 276 | IV | 20.11.2018 | LUP1209 | Construction/Upgradation of OHE Kantigund | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 93.7 | 2011-03-01 |  | 83.75 | 93.0546 | 100% | 100% |  |  | 83.75 | 2020-08-03 | [12 empty] | 83.75 | 9.3046 | 0.64538 |  | 2020-07-01 |  | 2020-07-01
| 277 | IV | 20.11.2018 | LUP1210 | Construction/Upgradation of Ohe Piasan road | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 89.21 | 2011-03-01 |  | 75.474 | 83.8592 | 100% | 100% |  |  | 65.367 | 2019-07-16 | 10.107 | 2020-10-21 | [10 empty] | 75.474 | 8.3852 | 5.3508 |  | 2019-20 |  | 2019-09-01
| 278 | IV | 20.11.2018 | LUP1211 | Construction of road from Sunbari to Hill bund | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 53.99 | 2014-07-01 |  | 42.158 | 46.8418 | 100% | 93% |  |  | 30.134 | 2020-10-21 | 12.024 | 2020-12-19 | [10 empty] | 42.158 | 4.6838 |  |  | 2020-09-01 |  | 2020-10-01
| 279 | IV | 20.11.2018 | LUP1212 | Chakilpora Thimran road | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 73.04 | 2009-03-01 |  | 56.889 | 63.2094 | 100% | 100% |  |  | 46.152 | 2019-10-18 | 10.737 | 2020-02-14 | [10 empty] | 56.889 | 6.3204 | 9.8306 |  | 2019-20 |  | 2020-03-01
| 280 | IV | 20.11.2018 | LUP1213 | Upgradation/Strengthening of Larnoo Draway road including link | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 40.96 | 2011-03-01 |  | 36.864 | 40.9596 | 100% | 100% |  |  | 36.864 | 2020-10-21 | [12 empty] | 36.864 | 4.0956 | 0.0004096 |  | 2020-07-01 |  | 2020-07-01
| 281 | IV | 20.11.2018 | LUP1214 | Construction of road from Akingam to Damhal via Hardpora | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 79.72 | 2011-03-01 |  | 45.706 | 50.7839 | 100% | 90% |  |  | 45.706 | 2020-10-21 | [12 empty] | 45.706 | 5.0779 |  |  | 2020-09-01 |  | 2020-09-01
| 282 | IV | 20.11.2018 | LUP1215 | Construction of road from Shangus to Andoo road | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 144.15 | 2013-07-01 |  | 128.692 | 142.9897 | 100% | 100% |  |  | 125.372 | 2020-07-29 | 3.32 | 2020-10-21 | [10 empty] | 128.692 | 14.2977 | 1.1603 |  | 2020-07-01 |  | 2020-07-01
| 283 | IV | 20.11.2018 | LUP1221 | Construction of road from Ranipora Rakhi Brah Deethu Sonach road | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 303.89 | 2011-03-01 |  | 227.999 | 253.3297 | 100% | 100% | 38.502 |  | 115.425 | 2020-03-31 | 58.95 | 2020-08-03 | 53.624 | 2020-10-21 | [8 empty] | 227.999 | 25.3307 |  |  | 2020-09-01 |  | 2020-09-01
| 284 | VI | 28.02.2019 | LUP1844 | Constr.of Khull Brah Kralgund road | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 111.06 | 2012-03-01 |  | 60.485 | 67.2049 | 100% | 63% |  |  | 60.485 | 2020-08-03 | [12 empty] | 60.485 | 6.7199 |  |  | 2020-10-01 |  | 2020-10-01
| 285 | VI | 28.02.2019 | LUP1845 | Constr.of Brah Dawoodpora road | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 114.1 | 2012-12-01 |  | 51.121 | 56.8005 | 100% | 58% |  |  | 51.121 | 2020-08-03 | [12 empty] | 51.121 | 5.6795 |  |  | 2020-10-01 |  | 2020-10-01
| 286 | VI | 28.02.2019 | LUP1846 | Constr of Arhama Badasgam road | SS | Road | R&B | Kashmir | Anantnag | Vailoo | Mehraj-ud-Din Bhat |  | 71.63 | 2012-03-01 |  | 60.547 | 67.2738 | 100% | 100% |  |  | 32.623 | 2019-10-04 | 27.924 | 2020-07-30 | [10 empty] | 60.547 | 6.7268 | 4.3562 |  | 2019-20 |  | 2020-03-01

## Work wise status
STATUS OF LANGUISHING PROJECTS
Rs in lacs
S. No | LUP Code | Name of Project / Location | District | Sanctioned Amount | Expdt incurred | Remarks
1 | LUP0027 | Const of 15mtr span single lane RCC bridge over Palyal Nallah onkotli Palyal link road at Chowadhi including approach road and protection work | Jammu | 61 | 37.778 | Completed
2 | LUP0028 | Const. of 15.30 mtr span vented causeway near Temple/ Little Flower School at Greater kailash | Jammu | 43.44 | 38.889 | Completed
3 | LUP0029 | Const .of 45 mtr Span vented causeway along with approach road on village phinder | Jammu | 143.44 | 47.804
4 | LUP0030 | Const of Multi Box culvert at Lawaki Nallah Nariayana | Jammu | 280 | 122.211
5 | LUP0031 | Const. of Bridge over Kanah Nallah Seoni to Lale Da Chabara | Jammu | 236 | 212.337 | Completed
6 | LUP0032 | Const of Multi Span Box culvert on Pouni Chak to Akalpur Road with Approaches | Jammu | 35 | 29.7 | Completed
7 | LUP0033 | 13 mtr span RCC culvert on link road from Nai Basti to Govt. Middle school Lower Muthi Jammu | Jammu | 32 | 12.438 | Completed
8 | LUP0034 | Const . Of 26.70 mtr span Multi box Vented Causeway over Choi Nallah at Dhateryal at Village Halque (Bl | Jammu | 146.61 | 87.928 | Completed
9 | LUP0035 | Const .of 27.70 mtr span vneted causeway with 5 nos. Vents (5.0 m X 5.0 ) on road from Ghari to Ladore Block Marh Jammu | Jammu | 85 | 75.473 | Completed
10 | LUP0036 | Const. of 132 m span foot suspension bridge over River Sasanter at Hunded | Samba | 18.66 | 0 | Completed
11 | LUP0037 | Const.of 10 mtr span bridge at kaluchak purmandal road Km 1st Distt Samba | Samba | 20 | 9.109 | Completed
12 | LUP0038 | Const. of 25 mtr span vented causeway on Nallah at Ban Khad nera Masjid | Samba | 45.76 | 25.911 | Completed
13 | LUP0039 | Const .of 15 mtr span (Single lane) reinforced Cement bridge over Banyari Nallah on Khanpur banyari Link Road District Kathua | Kathua | 87.24 | 56.606 | Completed
14 | LUP0040 | Const.of 25 mtr spand bridge on Krola Gharit upto Kasori Road | Kathua | 42.1 | 15.381 | Completed
15 | LUP0041 | Const. of 40 mtr span vented causeway on Bhaiya & Mela link Road | Kathua | 50 | 32.679 | Completed
16 | LUP0042 | Const. of 105 m span vented causeway in Km 5th on Hiranagar Jandi Road Kathua | Kathua | 48.35 | 26.082 | Completed
17 | LUP0043 | 40 mtr span RCc bridge on Kathua Khad in Kathua Town | Kathua | 201.85 | 118.467
18 | LUP0044 | Const of 120 m span double lane pre- stressed concrete bridge over Bheeni Nallah at Katli state sector | Kathua | 1106.5 | 153.9
19 | LUP0045 | 20 mtr span girder m/able bridge in nallah Thathli Saddal km 9th RD 0-100 on Kainthgali Bhamag. | Udhampur | 27.28 | 14.238 | Completed
20 | LUP0047 | Const. of 48 mtr span motorable bridge on Kund Morh (Sunder Morh) to Cheeral Road in 4th Km over Plasoo nallah. | Reasi | 242 | 158.328
21 | LUP0048 | Const. of 25 Mtr span steel girder Foot Bridge Gosha over nallah Ishni. | Reasi | 54.9 | 0
22 | LUP0049 | Const of 40 mtr span steel Motorable bridge over Sukh Tawi at Irwan Khetar, Manjakote | Rajouri | 137.57 | 111.992 | Completed
23 | LUP0050 | 17 M Span Motorable bridge at Gurian Panihad | Rajouri | 61 | 31.518 | Completed
24 | LUP0051 | 32M span LMV bridge near Jamia Masjid Manjakote [Dawain More Gulhati] | Rajouri | 96.64 | 56.355 | Completed
25 | LUP0052 | 25 M Span Motorable bridge in km 1st RD 0 to 50 on Baigonar to Alal road | Rajouri | 129.28 | 33.408
26 | LUP0053 | Construction of 38.00 mtr span Motorable bridge over Gakhrote on Kotedhara Peeri road | Rajouri | 148.35 | 85.84
27 | LUP0054 | Construction of 25 M Span motorable Bridge at Ratala Jamola | Rajouri | 144.27 | 45.639
28 | LUP0055 | Construction of 25.00 Mtr span foot Bridge at Sora Galla | Rajouri | 114 | 74.582 | Completed
29 | LUP0056 | 20 M Span Motorable bridge at Swari over Jamola Nallah | Rajouri | 126.72 | 108.1 | Completed
30 | LUP0057 | Const. of 62 Mtr Span Light Motor Vehicle Steel Girder Bridge (Single Lane) over Solki Nallah at Potha Dhangar. | Rajouri | 159.95 | 61
31 | LUP0058 | Construction of 40 m span Light Motor Vehicle Steel Girder Bridge over River Triyath at Kathanu near Sunderbani | Rajouri | 48.79 | 0
32 | LUP0059 | Construction of 132 M span motorable bridge at Bareri Nallah | Rajouri | 739.74 | 0
33 | LUP0060 | Construction of road from Bajwal to Siot including 80 m span motorable bridge at Nalani Pattan | Rajouri | 214.46 | 102.831 | Completed
34 | LUP0061 | Construction of 40 Mtr Span Steel Girder Motorable Bridge at Rawarian Talla (Sunderbani) | Rajouri | 98.9 | 33.152 | Completed
35 | LUP0062 | Construction of 45 Mtr span Motorable Bridge at Patli Ganaya road. | Rajouri | 242.5 | 140.94
36 | LUP0064 | Const of 25 m span FJB over Suran River Pharoo Tehsil Surankote. | Poonch | 29.39 | 21.788 | Completed
37 | LUP0065 | Constt. Of 28 M span steel FJB at Bagnuwali , tehsil Surankote, distt., poonch. | Poonch | 33.28 | 27.753 | Completed
38 | LUP0068 | Const of 40 M span steel FJB over Chungan Nallah at Chak Banola, distt. Poonch. | Poonch | 47.66 | 33.666 | Completed
39 | LUP0069 | Const. of 50M span M/able bridge at Rajpura on Zairat Chowkiwala balnai road Km 1st | Poonch | 158.34 | 142.181 | Completed
40 | LUP0070 | Const. of 85 Mtr span steel foot bridge over river Marsudar at Bungam Tagood. | Kishtwar | 123.95 | 61.925 | Completed
41 | LUP0071 | Const. of Foot Suspension Bridge over river Chenab at Mirool Dool. | Kishtwar | 160 | 41.612
42 | LUP0072 | Const. of motorable Bridge over Chilli nallah in Km 4th RD 50-100 of Gajote to Dugli road. | Doda | 90.9 | 62.874 | Completed
43 | LUP0073 | Const. of motorable Bridge over Jathi nallah Gajote in Km 2nd RD 275 - 3235 of Gajote to Dugli road (34 Mtr span) | Doda | 68.2 | 39.15 | Completed
44 | LUP0075 | 41.50 Mtr span super-structure Foot Bridge at Lamoth (Dranga) | Doda | 59.1 | 17
45 | LUP0076 | Missing link by way of Bridge and re-installation of existing Bridge (Const. of 45 mtr span Bridge over Koti Nallah at Doda Bharat road) | Doda | 174.5 | 157.05 | Completed
46 | LUP0077 | Const. of 46 mtr span Foot Jhulla Bridge over Chilly nallah at Juri B. | Doda | 16.38 | 0 | Completed
47 | LUP0078 | Const. of 40 Mtr span FJb over Chilly Nallah over Chowan. | Doda | 9.53 | 0 | Completed
48 | LUP0079 | Const. of 50 M span FJB over Chansar nalah at Mahndan. | Doda | 12.58 | 3.492 | Completed
49 | LUP0080 | Const. of 40 Mtr span FJB at Inhara Bhagat Mohalla Bisran. | Doda | 10.44 | 4.662 | Completed
50 | LUP0081 | Const.of 50 mtr span Foot Bridge at Tilogra Hanu over Jakyas Nallah. | Doda | 44.66 | 0
51 | LUP0082 | Construction of 1x30 Mtr Trussed Girder Bridge with Chequered plate decking & side approaches at Baghi-i-Mehtab connecting Bund Road Rawalpora | Srinagar | 43.11 | 37.612 | Completed
52 | LUP0083 | Const of Steel Girder bridge with RCC Deck Slab at Tankipora near DC office Srinagar (Two Bridges with carriage way of 5.5 Mtr each ) | Srinagar | 610.4 | 237.057
53 | LUP0084 | Construction of suspension Foot Bridge over river Jehlum (1x127 Mtr & 2x15 Mtr) at Takanwari Palpora | Srinagar | 130.65 | 66.03
54 | LUP0085 | Construction of Auditorium cum Conference Hall at Raj Bhavan Srinagar | Srinagar | 932.75 | 758.463
55 | LUP0086 | Constr of 1x50 mtr Treussed girder Jeepable Dand Foot Bridge over Doodganga Nallah near Alipora Chadoora | Budgam | 71.43 | 35.157
56 | LUP0087 | Constt of 2x22 mtr span P/G steel bridge over Nallah Shaliganga at Quangipora Chadoora | Budgam | 234.24 | 58.808
57 | LUP0088 | Construction of 1x36 Mtr Span Steel girder Foot bridge on Nallah Sukhnag at Peth Kanihama Hanjibugh | Budgam | 90.12 | 41.846 | Completed
58 | LUP0089 | Constr of 1x8 mtr span steel decked Bridge on Gumboora Ichhama road over Nallah Satmar in Km 2nd including approach road | Budgam | 88.75 | 50.835
59 | LUP0090 | Const of 2x20 mtr span steel girder bridge on Hazarpora Kandhama link road at Khag | Budgam | 165.88 | 112.095 | Completed
60 | LUP0091 | Constt. of 3x27 mtr span steel trussed girder bridge over Nallah Shaliganga on at Dragger Hill Kachwari road | Budgam | 513.869 | 426.064 | Completed
61 | LUP0092 | Construction of 1x40 Mtr single Span bridge over Nallah Ferozpora at Town-hall Magam | Budgam | 357.98 | 0
62 | LUP0093 | Construction of 2x31 Mtr span steel trussed girder bridge over nallah Shaliganga on Nair Gund Guhi-Dragger road | Budgam | 338 | 255.297
63 | LUP0094 | Const of 3x24 mtr span single lane plate girder bridge at Bamloora Ganderbal | Ganderbal | 394.61 | 240.066
64 | LUP0095 | Constr.of 82 mtr span truss girder Bridge over Nallah Sindh at Akhal Kangan | Ganderbal | 512.99 | 0
65 | LUP0096 | Const of 68 Mtr span truss girder bridge over Nallah Sindh at Tanchatri Kangan Ganderbal | Ganderbal | 384.53 | 0
66 | LUP0097 | Constr.of 70 mtr span combined plate/truss girder Bridge over Nallah Sindh at Yechama Kangan | Ganderbal | 211.25 | 0
67 | LUP0098 | Constr of 1x18 mtr span trussed girder Foot Bridge at Checkpora Aragam Bandipora | Bandipora | 82.93 | 23.143 | Completed
68 | LUP0099 | Const of 1x25 mtr span foot bridge at Athwathoo Bandipora | Bandipora | 86.71 | 48.99 | Completed
69 | LUP0100 | Constr. of 1x50 mtr span through type steel bridge over river kishan Ganga at Dawar Gurez | Bandipora | 122.85 | 78.184 | Completed
70 | LUP0101 | Construction of 1x30 span trussed girder bridge at (P.T.L) Purana Tulail over Satni Nallah | Bandipora | 87 | 74.201
71 | LUP0102 | Constr. of 1x10 Mtr and 1x40 Mtr span bridges on Achoora Bypass road at Gurez | Bandipora | 339.02 | 242.277
72 | LUP0103 | Construction of 1x40 Mtr span trussed girder bridge Dangithal Tulail | Bandipora | 203.77 | 0
73 | LUP0104 | Constr. of 1x20 mtr plate girder Bridge at Gujran Tulail | Bandipora | 133.87 | 50.792
74 | LUP0105 | Constr. of suspension Foot Bridge 150 Mtr long over river Jehlum at Shadipora | Bandipora | 363.18 | 86.899
75 | LUP0106 | Constr. of 2 x 24.50 Mtr + 1x50 Mtr. span foot bridge over River Jehlum at Sumbal | Bandipora | 419.13 | 55.8
76 | LUP0107 | Construction of proposed single lane plate girder steel bridge at Banyari Hajin ( 80 Mtr) | Bandipora | 37.24 | 30.618 | Completed
77 | LUP0108 | Construction of 1x25 Mtr Span RCC Steel Girder bridge between Guree and Keripora Bijbehara | Anantnag | 67.56 | 60.732 | Completed
78 | LUP0109 | Construction of Overhead Peadestrian Crossing at Bijbehara on Jammu Srinagar NH | Anantnag | 79 | 59.049 | Completed
79 | LUP0110 | Construction of 1x15 Mtr Span steel Girder bridge at Hanjipora Guree on Km 1st of Guree Aader Seepan road | Anantnag | 101 | 54.081
80 | LUP0111 | Constr of Bridge over Nallah Kraloo on Kraloo Uril road | Kulgam | 94.39 | 75.832 | Completed
81 | LUP0112 | Construction of 1x30 Mtr span steel trussed bridge over Kraloo Nallah in Km 1st of Y.K.Pora to Batnagoo via Peer Takiya road ( Peer Takiya Bridge) | Kulgam | 108.17 | 87.273 | Completed
82 | LUP0113 | Construction of 1x30 Mtr span Motorable bridge instead of foot bridge at Hakradan Waripora Kund over Nallah Khider/Budikhul | Kulgam | 144.72 | 41.342
83 | LUP0114 | Construction of 1x37 Mtr span girder bridge at Lalipora to Khanland ( balance cost) | Anantnag | 69.3 | 54.59 | Completed
84 | LUP0115 | Construction of 2x30 Mtr span steel girder bridge at Badasgam A to Badasgam B over Bud Khul | Anantnag | 225.27 | 150.592 | Completed
85 | LUP0116 | Construction of 2 x 20 M span girder Bridge over Nallah Grawan near Syedpora Kharati Vailoo | Anantnag | 123.04 | 91.746 | Completed
86 | LUP0117 | Construction of 1x30 Mtr Span Steel Trussed bridge over Nallah Aripath in Km 10th of Gopalpora Tailwani Issue Wangam Shangus road | Anantnag | 68 | 49.112 | Completed
87 | LUP0118 | Construction 3x25 Mtr span steel girder bridge over Bringi on Sagam Kandiwara road | Anantnag | 384.68 | 199.797
88 | LUP0119 | Construction 2x25 Mtrs span steel girder bridge over nallah Aripath at Noonwani Brakpora for light motor vehicles | Anantnag | 236.31 | 42.537
89 | LUP0120 | Construction of 1x12 Mtr span bridge in Km 1st on Adipora Mishpora road | Kulgam | 46.8 | 41.735 | Completed
90 | LUP0121 | Construction of 1x10 Mtr span bridge on Khudwani Ganjipora Road. | Kulgam | 83.84 | 57.707 | Completed
91 | LUP0122 | Construction of 1x8 Mtr span bridge in Km 1st on Frisal Chanigam road | Kulgam | 56.65 | 50.418 | Completed
92 | LUP0123 | Construction of 2x30 mtr. Span steel girder bridge over Nallah Vethvathru in km 2nd of Babapora link road Phase 1st | Kulgam | 293.98 | 258.829 | Completed
93 | LUP0124 | Construction of 2x30 Mtr span steel girder foot bridge over Nallah Sadran at Vessu Sadoora Chopan Mohalla | Anantnag | 155.62 | 105.147 | Completed
94 | LUP0125 | Construction of 1x30 Mtr span Jeepable foot bridge at Village Amanpora | Kulgam | 118.73 | 96.741 | Completed
95 | LUP0126 | Construction 2x20 Mtr span bridge at Bona Manigam Chanderkote (Redesigned as 1x40 Mtr span bridge) | Kulgam | 13 | 0
96 | LUP0127 | Const of 1x22 mtr span steel girder bridge over Nallah at Pethgam Wagoora | Baramulla | 56.09 | 50.003 | Completed
97 | LUP0128 | Construction 1x120 mtr span trussed girder steel foot bridge over river Jehlum at Fish Market, Baramulla | Baramulla | 250 | 222.715 | Completed
98 | LUP0129 | Construction of 1x100 Mtr Span Suspension Foot Bridge over Nallah Pohru at Seelu connecting Seelu with Hib Dangerpora | Baramulla | 83.29 | 72.512 | Completed
99 | LUP0130 | Rehabilitation of 54 mtr long Bridge (1x14 mtr+1x40 mtr span) on Kunzer Chanapora road by way of construction of approaches & other allied works | Baramulla | 374 | 132.044
100 | LUP0131 | Constr. of 1x25 mtr span double lane steel trussed Bridge at Budibugh Pattan | Baramulla | 250.77 | 141.217
101 | LUP0132 | Constr. of 80 mtr span Malganipora Wadoora Foot bridge over Pohru Nallah | Baramulla | 172.08 | 23.713
102 | LUP0133 | Construction of 150 Mtr long foot bridge at Seer Jagir Sopore | Baramulla | 622.21 | 0
103 | LUP0134 | Constr. of 70 mtr span single lane trussed girder Bridge over River Jehlum at Jhulla Uri | Baramulla | 560.41 | 26.712
104 | LUP0135 | Constr of single lane 60 mtr steel trussed Bridge at River Jehlum at Peernai Uri | Baramulla | 42.13 | 23.949 | Completed
105 | LUP0136 | Mehrajpora, Sopore, Baramulla | Baramulla | 1618.09 | 0
106 | LUP0137 | Construction of Jetty Bridge at District Baramulla | Baramulla | 2186.87 | 0
107 | LUP0138 | Construction of 132 Meter long 3 spans bridge at Doabgah Darpora road | Baramulla | 856 | 0
108 | LUP0139 | Const of 2x32 mtr span trussed girder foot bridge over Nallah Pohru at Hangishort | Kupwara | 130.86 | 91.688 | Completed
109 | LUP0140 | Constr. of 1x12 Mtr span steel girder bridge near Food Store Lontha over Nallah Batmaji | Kupwara | 108.73 | 55.744
110 | LUP0141 | Const of 10 Mtr span steel girder bridge near Chawan mohalla Bagh Beela over nallah Kundrawal | Kupwara | 89.21 | 32.589
111 | LUP0142 | Construction of road with 1x35M span bridge at Bitch Mohalla over Nallah Batapora | Kupwara | 102.6 | 1.168
112 | LUP0143 | Constr of 1x45 mtr span RCC Bridge over Nallah Manigah at Reshi Mohalla Manzhar Hyhama Lolab | Kupwara | 69.44 | 35.166 | Completed
113 | LUP0144 | Construction of proposed single lane steel bridge at Dobwan Kachama | Kupwara | 93.06 | 64.36 | Completed
114 | LUP0145 | Const of 1x15 m span steel; decked bridge over Nallah Hud at Kralpora Bus Adda | Kupwara | 91.61 | 46.347 | Completed
115 | LUP0146 | Const of proposed single lane 30 mtr bridge at Marsari Zoon Reshi, Kupwara | Kupwara | 102.31 | 68.152
116 | LUP0147 | Construction of 100 Mtr long steel decked bridge at Trehgam Bangergund Road over Nallah Kahmil at Bangergund Incl. Washed Away causeway (damaged in Floods) | Kupwara | 318.95 | 30.621
117 | LUP0148 | Construction of 92 Mtr single lane steel trussed girder birdge at Kanthpora Lolab Kupwara | Kupwara | 157.6 | 0
118 | LUP0149 | Construction of 3x40 Mtr span long steel truss girder bridge over nallah Kahmil at Kunan Kupwara | Kupwara | 343.75 | 0
119 | LUP0150 | Construction of 110 Mtr long single lane steel girder bridge at Check Hatmulla Drugmulla Kupwara | Kupwara | 276.32 | 0
120 | LUP0151 | Construction of 3x40 Mtr long composed decked foot bridge over Nallah Pohru with Approaches at Shartwari Nagri Kupwara | Kupwara | 304.18 | 0
121 | LUP0152 | Constr.of 200 mtr long single lane PSC girder Bridge over Kehmil Nallah at Aloosa Pachkout Kupwara | Kupwara | 743.4 | 0
122 | LUP0153 | Constr of 2x55 mtr span long single lane TG steel Bridge over Mawar Nallah at Drangsoo Langate Kupwara | Kupwara | 805.19 | 0
123 | LUP0154 | Constr. of 3x30 mtr span truss girder tractor crossing/Foot Bridge over Kehmil Nallh at Bohipora Kupwara | Kupwara | 141.78 | 0
124 | LUP0155 | Constr.of 260 mtr long single lane PSC girder Bridge at Tumina Chowkibal, Kupwara | Kupwara | 611.79 | 0
125 | LUP0156 | Constr. of 1x15 mtr steel girder Wandakpora (Hanjipora Bridge) at Hanjipora | Pulwama | 33 | 26.451 | Completed
126 | LUP0157 | Constr. Of 2x20 mtr bridge on Hurdimir Saimoh Road | Pulwama | 69.5 | 56.417 | Completed
127 | LUP0158 | Construction of 109 Mtr span double lane plate girder bridge over river Jehlum at Reshipora Pulwama | Pulwama | 625.51 | 232.293
128 | LUP0159 | Construction of double lane trussed girder Bridge over River Jehlum (129 mtr span) at Dogripora | Pulwama | 785.29 | 0
129 | LUP0160 | Cosnt of Road from KM 4th Doda Bhaderwah Road to Nai Dangri | Shopian | 313.8 | 204.281
130 | LUP0469 | Const of 33m concrete motorable bridge over Nallah between Sec. A & G Sainik Colony Adjacent to Railway Track | Jammu | 120 | 107.913 | Completed
131 | LUP0470 | Const. of 30 M Span Motorable Bridge at Kotan Sadwala to Soian panakhan | Poonch | 35 | 23.018 | Completed
132 | LUP0471 | Const of 45 M span Steel FJB at Chattral nallah near Mohalla Chattral Mendhar | Poonch | 66 | 0 | Completed
133 | LUP0472 | 45 M Span motorable bridge at Kalara on Kharsoo Teryath Road | Rajouri | 219.4 | 135.699 | Completed
134 | LUP0473 | 20 M span motorable bridge at Swawa on Kalsian Handan road | Rajouri | 94.5 | 72.065
135 | LUP0474 | Const. of 25 Mtr span Steel Girder Motorable Bridge with its approaches including link road to village Maghal Katra | Reasi | 288.5 | 197.731 | Completed
136 | LUP0475 | 35.00 Mtr. Span foot bridge over Nallah Bowl at Village Gorahan Block Ghordi Tehsil Ramnagar | Udhampur | 49.6 | 33.696 | Completed
137 | LUP0476 | 45.00 Mtr Span Motorable Bridge on Kogha Pinger Bainsta of Kogha Thali Road incl approach road | Udhampur | 823.06 | 249.489
138 | LUP0477 | Const of 43.00 mtrs span truss bridge (through type) over Birwannallah at Chakhar connecting village Debrah | Udhampur | 247.6 | 111.501 | Completed
139 | LUP0753 | Construction of 1x30 Mtr span steel decked bridge in Km 1st of Kilam Gund road and widening/ upgradation from RD 0-600 Mtr. | Kulgam | 444.3 | 136.755
140 | LUP0754 | Suspension Foot Bridge over River Jehlum at Padshahi Bagh, Bijbehara | Anantnag | 318 | 58.752
141 | LUP0755 | Const. of 1x10 mtr span steel girder Bridge over Katoo Satkipora Nallah at Kaloo Village | Anantnag | 159.09 | 71.28
142 | LUP0756 | Construction of 3x30 Mtr span steel girder bridge at Nowpora Lonepora on nallah Sandran | Anantnag | 302.1 | 215.881 | Completed
143 | LUP0757 | Construction of 2x30 Mtr span steel girder bridge at Bonagund Zamalgam on nallah Sandran | Anantnag | 322.95 | 181.314
144 | LUP0758 | Construction of 3x20 Mtr span steel girder bridge at Rashipora Hergawas on Nallah Sandran | Anantnag | 94.7 | 11.934
145 | LUP0759 | Constr.of steel trussed jeepable Bridge at Bangidar Anantnag | Anantnag | 285 | 228.168 | Completed
146 | LUP0760 | Constr.of overhead Foot Bridge from Amusement Park to Golf Course at Pahalgam | Anantnag | 127 | 71.208
147 | LUP0761 | Const. of 1x11 mtr span plate girer motorable Bridge over Khundri Nallah at Peer Mohalla Erin Bandipora | Bandipora | 78.81 | 64.276 | Completed
148 | LUP0762 | Upgradation of Sumbal Wangipora, Sumbal Nasbal, Sumbla Arampora & Dumpora road and allied links | Bandipora | 469.2 | 261.908
149 | LUP0763 | Const of 2x20 mtr span steel girder bridge over nallah Ningli at Dongdara Sangrama | Baramulla | 240.29 | 168.066
150 | LUP0764 | Upgradation of Binner Shitloo road | Baramulla | 253.18 | 125.772
151 | LUP0765 | Upgradation of Khamoh Bosiyan road | Baramulla | 221.27 | 9.234
152 | LUP0766 | Upgradation of Botangoo Muqam Shaheed Mir Road | Baramulla | 440.75 | 238.867
153 | LUP0767 | Upgradation of Wadoora Bala and Wadoora Payeen with allied links | Baramulla | 270.81 | 172.931 | Completed
154 | LUP0768 | Upgradation of inner links at Warapora | Baramulla | 457.92 | 269.61 | Completed
155 | LUP0769 | Upgradation of Mirgund Shadipora road via Checki Razak Khan | Baramulla | 249.48 | 26.417
156 | LUP0770 | Construction of road from Zandfaran to Gurivan | Baramulla | 156.64 | 132.468 | Completed
157 | LUP0771 | Construction of road from Khaitangan to Takya Wagoora via Gousia Colony upto High School wagoora with allied links | Baramulla | 213.67 | 114.496
158 | LUP0772 | Upgradation of Malpora to Larridora via Kawhar | Baramulla | 100.59 | 85.829 | Completed
159 | LUP0773 | Kanispora inner links | Baramulla | 204.76 | 156.132
160 | LUP0774 | Constr. of 1x20 mtr span trussed Bridge on Nallah Gogaldara Pethsharan Road | Budgam | 322.14 | 122.781
161 | LUP0775 | Constr. Of 1x18 mtr span steel girder Bridge with RCC slab deck in Km 5th at Sebdan over Ahaji Canal connecting to Bathar Railway Road | Budgam | 118.25 | 99.156 | Completed
162 | LUP0776 | Constr of 1x24 mtr span steel bridge at Karipora (Intermediate lane truss girder bridge) | Budgam | 136.27 | 86.215 | Completed
163 | LUP0777 | Construction of 25 Mtr span bridge at Loolipora Yaham | Budgam | 61.81 | 0
164 | LUP0779 | Construction of Dak Bunglow at Fatehpora Ganderbal | Ganderbal | 249.53 | 47.891
165 | LUP0780 | Construction of Nilgrath Baltal road | Ganderbal | 374.2 | 266.908 | Completed
166 | LUP0781 | Const. of road from Bund-Khandyal-Lalyal | Jammu | 82.49 | 66.111 | Completed
167 | LUP0782 | Const. of road from Milk Derian Balla enclave to Rama Channi Masjid Mohalla (L- 2.00 kms) upto ITBP Camp including const. of vented causeway | Jammu | 57 | 46.778 | Completed
168 | LUP0783 | Const. of road (double lane) to Public Park at Kharian via NIITS College. | Jammu | 151.6 | 104.288 | Completed
169 | LUP0784 | Const. of road in Bilal Colony Channi Rama including deep drain | Jammu | 173.89 | 63.032
170 | LUP0785 | Const. of road from Kotli Galabana to Kullian Khalsa road in km 3rd via Bhure-De-Kothey | Jammu | 157.4 | 35.496 | Completed
171 | LUP0786 | Imprvtt./ Upgd of road from Kangrail Majali road to Ratti Chappri. | Jammu | 105.28 | 61.799 | Completed
172 | LUP0787 | Imprvtt./ Upgd of road from main road Jandyal to Tower road via Bhupa Talab Beri Chapri Ranjan. | Jammu | 87.5 | 47.907 | Completed
173 | LUP0788 | Const. of road from Burn to Karlie | Jammu | 128.39 | 0
174 | LUP0789 | Const. of road from 4th Tawi Bridge to Karnaile Chak | Jammu | 70.35 | 59.376 | Completed
175 | LUP0790 | Const. of 18 Mtr span Steel Girder Bridge at Bhore Camp Jammu | Jammu | 83.2 | 60.839 | Completed
176 | LUP0791 | Const. of link road from Dhaba/Tube well Morh to DugWell/Cremation Ground Sallan | Kathua | 52.55 | 30.798 | Completed
177 | LUP0792 | Const. of Pranta Patyari to Balan Talab road | Kathua | 40 | 35.757 | Completed
178 | LUP0793 | Const. of link road to Patoli | Kathua | 48 | 27.684 | Completed
179 | LUP0794 | Kalaspur to Darhal Kathua | Kathua | 19.5 | 14.301 | Completed
180 | LUP0795 | Jasrota to Rakh Hoshiari road | Kathua | 90.53 | 56.502 | Completed
181 | LUP0796 | Maroli to Kalaspur via Upper Govindsar link road Kathua | Kathua | 46.65 | 24.957 | Completed
182 | LUP0797 | Wasarkote Lonaharia Bridge 1x15 Mtr Span | Kupwara | 147.78 | 53.82 | Completed
183 | LUP0798 | Constr. Of 10 Mtr span Bridge on Nallah Talri at Warpora Ahgam | Kupwara | 52.38 | 23.628 | Completed
184 | LUP0799 | Constr. Of 14Mtr span double barrel box type culvert on Zaferkhani Mandoori Road in Km 1st | Kupwara | 46.2 | 40.394 | Completed
185 | LUP0800 | Re-Constr. Of damaged portion of EEs Quarter at Gomal Tanghdar | Kupwara | 52.22 | 46.998 | Completed
186 | LUP0801 | Construction of 3x40 Mtr (120 Mtr) long steel truss girder bridge over nallah Kahmil | Kupwara | 520.73 | 0
187 | LUP0802 | Construction of single lane P/G Steel bridge at Nagri Gamandar | Kupwara | 338.34 | 0
188 | LUP0803 | Construction/Upgradation of road Kenyal Dachina to Dogripora including Lilum to Waisa road | Kupwara | 121.19 | 107.208 | Completed
189 | LUP0804 | Construction/Upgradation of Kuligam Kandhar Changdi road | Kupwara | 168.75 | 124.341
190 | LUP0805 | Const. of road from Charallan to Sangla via Dandidhara | Poonch | 108 | 93.545 | Completed
191 | LUP0806 | 25 mtr sapn steel m/able Bridge over Suran Nallah at Behram Galla on link road to vilage Behramgalla | Poonch | 59.5 | 13.837
192 | LUP0807 | Const. of 150 Mtr span Motorable bridge at Kulani over Mandi Nallah | Poonch | 249.78 | 224.404 | Completed
193 | LUP0808 | Const. of road from Kattiwala to Phir via Kalsan | Poonch | 260.31 | 100.364
194 | LUP0809 | Const. of road Dhundak Marhote to Mohalla Mahiran. | Poonch | 97.37 | 22.5
195 | LUP0810 | Const. of road "Kalai to High School Kalai road. | Poonch | 111.62 | 98.46 | Completed
196 | LUP0811 | Const. of Link road to Mohalla Dupprian to Lassana | Poonch | 57.13 | 25.718 | Completed
197 | LUP0812 | Const. of road from Jogi More to Mohalla Manhasan. | Poonch | 99.99 | 65.557 | Completed
198 | LUP0813 | Const. of link road Hari Budha Surankote. | Poonch | 50.63 | 22.615
199 | LUP0814 | Const. of road from Malti Link road | Poonch | 89.45 | 50.792 | Completed
200 | LUP0815 | Const. of link road Kasalian. | Poonch | 175.39 | 141.387 | Completed
201 | LUP0816 | Const. of link road from Shiv Khori to Temple upto Nabani | Poonch | 166.47 | 148.064 | Completed
202 | LUP0817 | Const. of road from Dashal Mendhar to Holy Shrine Mian Charag Alam. | Poonch | 185 | 162.244 | Completed
203 | LUP0818 | Const. of road from Jugal to Kullian road to Topa | Poonch | 254.1 | 106.298 | Completed
204 | LUP0819 | Const. of road from Ari to Pathanateer to Salwah | Poonch | 222.25 | 172.456 | Completed
205 | LUP0820 | Const. of road from Ratti Jabri to Lower Sanjote via Kachar Mohalla Qazian | Poonch | 219.68 | 108.178
206 | LUP0821 | Const. of balance work of road from Behra to Salwah | Poonch | 166.61 | 119.201 | Completed
207 | LUP0823 | Const. of balance work of Sekloo Saloonia road. | Poonch | 86.3 | 74.064 | Completed
208 | LUP0824 | Up-gradation of Buffliaz Phagla road | Poonch | 247.89 | 109.523
209 | LUP0825 | Up-gradation of Harni BG Road Km 7th to 10th | Poonch | 201.47 | 180.687 | Completed
210 | LUP0826 | Const. of road from Dolati Zayrat to Danna Doyian | Poonch | 130.5 | 114.419 | Completed
211 | LUP0827 | Const. of road from Sakhi Maidan Kalai Km 33rd to PMGSY road. | Poonch | 71.5 | 30.696 | Completed
212 | LUP0828 | Const. of road from PMGSY 1.85 to Danna Kunuyian. | Poonch | 215 | 135.686 | Completed
213 | LUP0829 | Constr. Of 1x15 Mtr span Plate girder bridge at Hariparigam Tral | Pulwama | 54.84 | 49.356 | Completed
214 | LUP0830 | Const./Upgradation of Payer banderpora, Banderpora Koli and Payer Chandgam Road | Pulwama | 85.42 | 75.4 | Completed
215 | LUP0831 | Construction of Double lane approach road to AIIMS at Awantipora upto G-2nd level ( phase 1st from Islamic university to AIIMS) | Pulwama | 114.87 | 31.974 | Completed
216 | LUP0832 | Upgd of road from Samote to Targain | Rajouri | 217.4 | 117.775
217 | LUP0833 | Const. of link road from Chalal Bagla PMGSY road to Garanghi | Rajouri | 94 | 36.149
218 | LUP0834 | Const. of road from main road Muradpur to Govt.Girls High School Muradpur via Chirst School. | Rajouri | 269.78 | 112.091
219 | LUP0835 | Road from Sain Wlaidad Ziazrat (Paja) to Ghambir Gali | Rajouri | 212.5 | 128.571
220 | LUP0836 | Const. of road from Sarooti to Batala. | Rajouri | 145.31 | 55.887
221 | LUP0837 | Const.of road from Dharamsal-Badanoo road | Rajouri | 85.5 | 76.914 | Completed
222 | LUP0838 | Link road from Solki Bridge to Gaddi Gazi Muzaffar Shah | Rajouri | 163.95 | 79.333 | Completed
223 | LUP0839 | Const.of road from Mougla to Akher | Rajouri | 99.95 | 52.701
224 | LUP0840 | Const.of road from Mangal Singh Chowk to Berari Dhanika Nowshera | Rajouri | 53 | 41.878 | Completed
225 | LUP0841 | Sunderbani to Loharakote | Rajouri | 67.75 | 60.745 | Completed
226 | LUP0842 | Const.of road at Jaba to Baba Maimal Makam Nowshera | Rajouri | 141.5 | 34.931
227 | LUP0843 | Const.of road from Thandapani to Khuakhetar via Chaja including link to Pune Khetar Palwal. | Rajouri | 93.85 | 13.048
228 | LUP0844 | Road from Nonial to Masjid Mohalla Nowshera | Rajouri | 217.1 | 90.897
229 | LUP0845 | Const.of road from Dabbar to Sat Sahal | Rajouri | 139.5 | 103.235 | Completed
230 | LUP0846 | Const.of road from Asthana Angoora Nowshera. | Rajouri | 217 | 48.581
231 | LUP0847 | Const.of road from main road Kheri to Gujjar Basti through Chhibber Mohalla village Kheri. | Rajouri | 98.35 | 41.058
232 | LUP0848 | Const.of road from Rajal to Hanjana via Malika Mohra Km 2nd. | Rajouri | 138 | 53.115 | Completed
233 | LUP0849 | Const.of road from Kachain to Mangla Mata. | Rajouri | 249.3 | 27.402
234 | LUP0850 | Const.of road from Shiv Mandir to Thanda Dub Gagrote Nowshera | Rajouri | 212.45 | 86.932
235 | LUP0851 | Const.of approach road to Dharat Bridge. | Rajouri | 141.48 | 56.476
236 | LUP0852 | Const.of road from Kalideh to Baba Narsingh. | Rajouri | 127.55 | 34.023 | Completed
237 | LUP0853 | Const.of road from main road Dandani to Gojri Pul. | Rajouri | 166 | 40.137
238 | LUP0854 | Const.of road from Lamberi Mokrayala to Shiv Mandir via Shiv Chowk. | Rajouri | 279 | 32.342
239 | LUP0855 | Const. of road from Pathan Mohra to Mubarak Pura Rajouri | Rajouri | 166.7 | 42.219
240 | LUP0856 | Const. of road from Khalabat to Nowgran. | Rajouri | 176.85 | 104.15 | Completed
241 | LUP0857 | Const. of road from Dassal to Dassal Seeran. | Rajouri | 136.6 | 88.929 | Completed
242 | LUP0858 | Const. of road from Charota Gala to Pata Khetar. | Rajouri | 167.88 | 56.232
243 | LUP0859 | Const. of road from Km 5th Army Gate Gurdanbala to Mohra Dhara. | Rajouri | 173.95 | 60.037
244 | LUP0860 | Const. of road from Chamba to Paryali road. | Rajouri | 226.69 | 173.556
245 | LUP0861 | Const. of road from Muradpur to Mohalla Loharan. | Rajouri | 248.62 | 69.12
246 | LUP0862 | Const. of road from Kalali to Bhattian | Rajouri | 191.85 | 162.693 | Completed
247 | LUP0863 | Const. of road from Kakora (Dowa) to Kote via Pir Mohalla. | Rajouri | 250 | 142.954
248 | LUP0864 | Const. of road from Choor Gala to Mohra Drakhan. | Rajouri | 226.3 | 95.058
249 | LUP0865 | Const. of road from Patrara to Baigino. | Rajouri | 119.7 | 47.273
250 | LUP0866 | Const. of road from Agrati to Jabar. | Rajouri | 178.9 | 44.949
251 | LUP0867 | Peer Kanju to Thandikassi Rajouri | Rajouri | 271.7 | 126.792
252 | LUP0868 | Const. of road from main road Phalyana to New colony Phalyana (Attal Colony). | Rajouri | 79.55 | 52.22 | Completed
253 | LUP0869 | Approach road to Medical College at Mera | Rajouri | 280.9 | 99.531
254 | LUP0870 | Const. of road Khandli Bridge to Thathi (Thanooni). | Rajouri | 114.94 | 97.962 | Completed
255 | LUP0871 | Const. of road from Prori Panihad road to H.S at Panihad ( Missing link). | Rajouri | 109.93 | 93.112 | Completed
256 | LUP0872 | Const. of road from Sarano to PEO Manyalan. | Rajouri | 111.46 | 77.17 | Completed
257 | LUP0873 | Const. of road from Potha to Androlla | Rajouri | 141.75 | 60.967 | Completed
258 | LUP0874 | Const. of road from Kalal Kass to Dragri via Dhanna. | Rajouri | 249.5 | 167.436
259 | LUP0875 | Dhangri Dalhori Road and Extension upto Kanthol. | Rajouri | 116.1 | 81.126 | Completed
260 | LUP0876 | Const. of road from Mohalla Chowdhary Gulzar Ahmed (Ex-MLC_) to Baba Jammu Sahib in village Dhanore dhidian Tehsil and DisttRajouri. | Rajouri | 48.5 | 43.536 | Completed
261 | LUP0877 | Const. of road from Badhoon Crusher to Khui Draman. | Rajouri | 108.6 | 95.395 | Completed
262 | LUP0878 | Const. of road from Saaj to Basan road to Kallar Jabrian via Nara Danna | Rajouri | 174.9 | 99.644
263 | LUP0879 | Const. of road from Muglia More to Azmatabad. | Rajouri | 118.6 | 51.903
264 | LUP0880 | Bharatpur to Shahpur ( link road Bharatpuri) | Rajouri | 75.5 | 0
265 | LUP0881 | Const. of road from Shahdra Sharief to Sora via Kopra Qazian. | Rajouri | 170.59 | 21.888
266 | LUP0882 | Const. of link road from PMGSY Chalal Bagla Sabzi to Danna. | Rajouri | 69.26 | 48.446 | Completed
267 | LUP0883 | Const. of road from Sorah to Shahdra Sharief from Sorah side including road from High school Rajdhani to Bisa tota Mohra | Rajouri | 191.5 | 157.63
268 | LUP0884 | Const. of road from Sorah to Ghambir Muglan. | Rajouri | 225.05 | 85.935
269 | LUP0885 | Impvtt./Upgd. of road from Saaj to Basan Km 1st to 4th and 5th onwards. | Rajouri | 252.64 | 136.638
270 | LUP0886 | Const. of road from leeranwali bawli to Baba Sain walidad. | Rajouri | 217.84 | 106.325
271 | LUP0887 | Const. of circular road from Baigonara to Alal. | Rajouri | 180.4 | 46.943
272 | LUP0888 | Const. of missing link to connect Sokar Gali with PMGSY Ujhan to Leeran. | Rajouri | 75 | 43.515 | Completed
273 | LUP0889 | Const. of road from PMGSY road Fatehpur to Peer Meera Baksh Badshah. | Rajouri | 73.1 | 28.238
274 | LUP0891 | Const. of link road from Lah wali Bowli to Alidhara | Rajouri | 204 | 87.273
275 | LUP0892 | Upgradation of link road of BGSB University. | Rajouri | 172.5 | 147.173 | Completed
276 | LUP0893 | Chassana to sarsote up to Malikote, Package No: JK14-18, statge-I, Phase-V, block Mahore. | Reasi | 143.32 | 120.898 | Completed
277 | LUP0894 | Bhalla to shibrass(up to Neoch) road. Package No:-JK14-43, Stage-I, Phase-VI, block Mahore. | Reasi | 135.23 | 0
278 | LUP0895 | Imprvtt./Upgd of road from Kalika Nagar to Latori Length= 3.50 Km | Reasi | 89.51 | 74.131 | Completed
279 | LUP0896 | Const of road from Paroh to Arli | Reasi | 145.25 | 109.741 | Completed
280 | LUP0897 | Imprvtt./Upgd of road from Bhagtha to Manoon Length= 2.50 Km | Reasi | 108.49 | 66.037 | Completed
281 | LUP0898 | Extn. Of road from Kadmal ( Nikki Mashha) to Nomain Length = 2.84 Km | Reasi | 70.02 | 57.276 | Completed
282 | LUP0899 | Road from Kadmal to Dhanna Length= 1.00 Km. | Reasi | 96.4 | 47.847 | Completed
283 | LUP0900 | Road from Palli to village Binari ( Muttal) Length=2.00 Km ) | Reasi | 126.99 | 109.909 | Completed
284 | LUP0901 | Const. of Circular road at village Abtal | Samba | 42.95 | 28.791 | Completed
285 | LUP0902 | Const. of road Pakhri to Kajyal | Samba | 98 | 10.71
286 | LUP0903 | Link road Bain Glad to Basantar | Samba | 44.5 | 34.611 | Completed
287 | LUP0904 | const. of link road from Nallah to Nallah Dalhote | Samba | 18.25 | 12.672 | Completed
288 | LUP0905 | Const. of Naneetar Basti Tali Samba Sumb road | Samba | 25.8 | 7.551
289 | LUP0906 | Const. of Ramgarh to Rudwan road | Samba | 26.89 | 16.147 | Completed
290 | LUP0907 | Mahal Adda to Mahalshan including link road Ramgarh to Rudwan | Samba | 24 | 12.525 | Completed
291 | LUP0908 | Const. of road from Nud to Badla Brahmana via Sarai Village | Samba | 134.58 | 59.276
292 | LUP0909 | Const. of link road to Shamshan Ghat at Vijaypur | Samba | 44.75 | 28.719 | Completed
293 | LUP0910 | Constr. Of 2x25 Mtr span bridge over Tongir Nallah in Km 3rd of Chitragam Rebbon Road | Shopian | 189 | 162.73 | Completed
294 | LUP0911 | Launching of 2x24 Mtr baily Bridge on Trenz Sheikhpora Road | Shopian | 58.35 | 49.79 | Completed
295 | LUP0912 | Construction of circuit house at Padpawan Shopian | Shopian | 57.13 | 51.298 | Completed
296 | LUP0913 | Strengthening/upgradation of Arkahr- Losedanew road, Kunsoo Zainbatoo Krawoorah Gulshanpora road including Lasedanew Malikgund Killora road | Shopian | 321.87 | 159.719
297 | LUP0914 | Const of 2x25 + 1x55 mtr span 1.80 M wide foot bridge over Jehlum connecting gundbal Soiteng at Batwara with National Highway | Srinagar | 271.06 | 49.95
298 | LUP0915 | Construction of community centre at Checki Mehtan, Baghi-i-Mehtab | Srinagar | 54.11 | 37.976 | Completed
299 | LUP0916 | Construction of approach road on Soiteng side of Vethpora Soiteng Bridge | Srinagar | 463.75 | 0
300 | LUP0917 | Construction of 1x35 Mtr span plate girder bridge on Darbagh to Ehal road across Maloori Nallah (including Approaches) | Srinagar | 100.05 | 0
301 | LUP0918 | Improvement/Upgradation of road from Suketar to Upper Badana in Kud Tehsil Chenani Distt. Udhampur ( L=1.50 km). | Udhampur | 170.85 | 108.854 | Completed
302 | LUP0919 | Goswami Talai to Bay Kannada Panchayat Babey Block Dudu ( L-2.75 Km ) | Udhampur | 253.2 | 90.522
303 | LUP0920 | Shatral to SC Basti Swalta village Tajoor ( L=2.20 Km) | Udhampur | 126.95 | 78.696 | Completed
304 | LUP0921 | Const. of road from Mongri to Ajjal Dabbar (Phase I) ( L= 2.50 km) | Udhampur | 240.94 | 41.616
305 | LUP1208 | Construction of 2 x25 mtr span steel girder bridge over Nallah Bringi at Village Poru Goihard | Anantnag | 46 | 30.122 | Completed
306 | LUP1209 | Construction/Upgradation of OHE Kantigund | Anantnag | 93.7 | 83.75 | Completed
307 | LUP1210 | Construction/Upgradation of Ohe Piasan road | Anantnag | 89.21 | 75.474 | Completed
308 | LUP1211 | Construction of road from Sunbari to Hill bund | Anantnag | 53.99 | 42.158 | Completed
309 | LUP1212 | Chakilpora Thimran road | Anantnag | 73.04 | 56.889 | Completed
310 | LUP1213 | Upgradation/Strengthening of Larnoo Draway road including link | Anantnag | 40.96 | 36.864 | Completed
311 | LUP1214 | Construction of road from Akingam to Damhal via Hardpora | Anantnag | 79.72 | 45.706 | Completed
312 | LUP1215 | Construction of road from Shangus to Andoo road | Anantnag | 144.15 | 128.692 | Completed
313 | LUP1216 | Construction of road from Thajiwara – Kadpora road | Anantnag | 216.91 | 58.542
314 | LUP1217 | Construction of road from Goriwan to Gohihard via Wandevalgam | Anantnag | 78.15 | 13.649
315 | LUP1218 | Construction of road interior road at Boontooru | Anantnag | 207.89 | 107.481
316 | LUP1219 | Upgradation of link road from High School Gohan to Malmarg | Anantnag | 147.9 | 70.378
317 | LUP1220 | Upgradation of Mohripora Kandiwara Soaf road | Anantnag | 365.1 | 229.752
318 | LUP1221 | Construction of road from Ranipora Rakhi Brah Deethu Sonach road | Anantnag | 303.89 | 227.999 | Completed
319 | LUP1222 | Construction of Sardab Tatroon Khutroon road | Bandipora | 101.71 | 17.203
320 | LUP1223 | Construction of Badugam wazirthal road including Construction of 1x40 Mtr span bridge | Bandipora | 164.53 | 0
321 | LUP1224 | Construction of 1x22 Mtr span steel girder bridge on Chanmohalla link road over existing nallah | Baramulla | 44.27 | 30.38 | Completed
322 | LUP1225 | Construction of 1x20 Mtr span steel girder bridge over existing nallah at Bangdhara | Baramulla | 41.94 | 37.746 | Completed
323 | LUP1226 | Construction of /Upgradation of road from Yedipora Hyderbeigh via Nillah Palpora to Wanigam | Baramulla | 167.57 | 74.461 | Completed
324 | LUP1227 | Construction of Dak Bunglow at Chijhama Rafiabad | Baramulla | 168.73 | 120.837
325 | LUP1228 | Construction of 1x10 Mtr span steel decked bridge on Wamin Nallah at Brass Gujjar Basti | Budgam | 44.68 | 40.005 | Completed
326 | LUP1229 | Construction of 1x10 Mtr span steel decked bridge on Gogaldara Nallah at Shuplin Gujjar Basti | Budgam | 66.29 | 9.009
327 | LUP1230 | Construction of 1x22 Mtr span steel girder bridge at Rakhi Wachoo Khansahib | Budgam | 173.72 | 138.062 | Completed
328 | LUP1231 | Construction of 1x10 Mtr span RCC Minor bridge over nallah Anem on Loolipora Kalipora road at Khag | Budgam | 185.44 | 114.331
329 | LUP1232 | Construction of 100.00 Mtr span single lane plate girder bridge over nallah sukhnag at sail Beerwah Budgam | Budgam | 442.36 | 0
330 | LUP1233 | Construction of Arwah-Wuhangam bridge at Arwah Beeru Budgam | Budgam | 210.86 | 54.885
331 | LUP1234 | Const. of Road from Bhoroo to village Jalgah via Rehi Naska Chinta Bhaderwah District Doda Length =2.225 km | Doda | 183.25 | 154.638
332 | LUP1235 | Const. of 54 Mtr span Motorable through Type Single Truss Bridge over Neeru Nallah at Kulsari Bhaderwah | Doda | 22.95 | 0 | Completed
333 | LUP1236 | Const. of 40 mtr span Motrable through Type Single Truss Bridge over Nehrru Nallah at Dheraja Bhaderwah. | Doda | 115.5 | 0 | Completed
334 | LUP1237 | Upgradation of Bhalla Derka via Dugga road | Doda | 214.1 | 79.064
335 | LUP1238 | Const. of road from Dumail Amirangar to Kharoti l= 3.50 km | Doda | 187.5 | 0
336 | LUP1240 | Const. of road from Launcher Morh to Akhrote Bagh | Doda | 60 | 35.633 | Completed
337 | LUP1241 | Gatha Gawari Hospital road | Doda | 39.74 | 29.833 | Completed
338 | LUP1242 | Const. of road from Sarol Bagh Temple to Shamshan Gath | Doda | 66 | 27.909
339 | LUP1243 | Const . Of Link Road from Shahpura Pranoo to Fangota in Distt. Doda | Doda | 244.81 | 125.755 | Completed
340 | LUP1244 | Impvt. And Up gd. Of link Road Jandiyal | Jammu | 204.38 | 89.478
341 | LUP1245 | Impvt. And Upgd. of link road from Beri Chapri to Mera Dabbar Block | Jammu | 161 | 90.194 | Completed
342 | LUP1246 | Cosnt. of Road Bajalta Peer Baba including link of Mohallah Mohd Ali | Jammu | 461.2 | 238.847 | Completed
343 | LUP1247 | Imp. /Up-gradation of Road from Sarah sandori | Jammu | 326.5 | 191.007 | Completed
344 | LUP1248 | Imp . Of track from Severbatti to Tunder Lopara including julla bridge | Kishtwar | 144.25 | 0
345 | LUP1249 | Const. of Charya Kandote link Road its take off point from NH IB to Charya at Km 1st RD (725) L-1.700 | Kishtwar | 116.56 | 59.097
346 | LUP1250 | Construction of PWD Complex at Tsawalgam Kulgam ( Double Story) | Kulgam | 358.75 | 115.064
347 | LUP1251 | Construction of Bogund Kulpora road | Kulgam | 105.36 | 66.967 | Completed
348 | LUP1252 | Construction/Upgradation of Shirpora Baldara incld Frisal Ziyarat Ayar and Frisal Shadcheck road | Kulgam | 64.94 | 37.488
349 | LUP1253 | Construction/Upgradation of Nillow Begam including Nillow Awhatoo road ( 4.00 Km) | Kulgam | 162.59 | 49.622
350 | LUP1254 | Construction/Upgradation of Labdipora Laroo Byepass road incld. Industrial road with allied links (5.35 Km) | Kulgam | 475.25 | 0
351 | LUP1255 | Construction of road from Nandimarg to Gulabgarh (upto Pandow Chollan Kashmir side) Phase 1st (Km 1st to 6th ) | Kulgam | 788.22 | 111.57
352 | LUP1256 | Construction/Upgradation of Kulgam Chatbal Panipora Kutbal including Bon Kandipora road (05.00 Km) | Kulgam | 96.39 | 0
353 | LUP1257 | Construction of 1x25 Mtr. Span Bridge at Loolipora Yahama | Kupwara | 61.81 | 42.06 | Completed
354 | LUP1258 | Construction of Rest House at Anderbugh | Kupwara | 35.14 | 28.011 | Completed
355 | LUP1259 | Construction of Rest House at Panzagam | Kupwara | 58.72 | 38.928 | Completed
356 | LUP1260 | Construction of 1.30 Mtr span plate girder bridge on Chewa Chaankitar road at Chaankitar | Pulwama | 93.27 | 75.435 | Completed
357 | LUP1261 | Construction of 1x60 Mtr span truss girder bridge over Sasar Nallah at Arabal on Bellow Arabal Nikas road | Pulwama | 214.15 | 185.753 | Completed
358 | LUP1262 | Construction of R&B Divisional Office at Rajpora, Pulwama | Pulwama | 92.1 | 79.658 | Completed
359 | LUP1263 | Construction of Road From Dar Ganie Gund to The Shrine of Sheikh Baqir Sahib via Sofi Gund at Tral | Pulwama | 384.01 | 81.835
360 | LUP1264 | Construction of road from NH-44 to group centre CRPF & Commando Training Centre J&K Police CTC Lethpora ( Lethpora – Barsoo- Loop) | Pulwama | 360.19 | 247.223 | Completed
361 | LUP1265 | Upgradation of Manloo Chanchmarg via Kharsinard Kanikhull including Manloo Bhat Mohalla link road | Shopian | 419.92 | 211.798
362 | LUP1266 | Construction of road from Ziarat Sharief Arhama to Pinjura at Shopian | Shopian | 80.27 | 59.315
363 | LUP1267 | Strengthening/Upgradation of Shalinard Nagbal Alishahpora via Wadipora road Km 1-2 | Shopian | 117.07 | 81.593
364 | LUP1268 | Strengthening / Upgradation of Shopian Aharbal road | Shopian | 329.71 | 128.018
365 | LUP1269 | Upgradation/Construction of road from Salfia Masjid Bongam to Guglooru including Lalnard to Pinjoora via Baba Mohalla | Shopian | 174.93 | 35.4
366 | LUP1270 | Construction of 4.75 Mtr span RCC culvert at Novbugh Gulab Bagh including construction of protection works and development of approaches | Srinagar | 124.36 | 111.785 | Completed
367 | LUP1271 | Construction/Upgradation of New Theed Mulnar road, Badamibagh Sheep road, Badadiya link road, Baba Ghulam-u-Din road and other allied links in the area | Srinagar | 772.54 | 281.427
368 | LUP1500 | Construction of approach road leading to Govt, Degree College Putushay at Bandipora | Bandipora | 185.79 | 31.804
369 | LUP1501 | Inner links at Kehnoosa | Bandipora | 215.93 | 175.569 | Completed
370 | LUP1502 | Upgrd of Kaloosa Khayar road | Bandipora | 606.68 | 437.214
371 | LUP1503 | Construction of 1x40 mtr steel trussed Girder Bridge at Neeru Shot Gurez | Bandipora | 246.95 | 10.486
372 | LUP1504 | Constr. of 1x40 mtr trussed Girder Bridge at Sheikhpora Tulail Gurez | Bandipora | 237.91 | 19.914
373 | LUP1505 | Development of land for Public Park at Sopore | Baramulla | 137.48 | 84.428
374 | LUP1506 | Constr of RCC Counter Forte retaining wall at Miran Resport (Humahma Heights) Humhama | Budgam | 188.77 | 0
375 | LUP1507 | Construction of 1x37 mtr span steel truss girder Bridge over Nallah Sukhnag at Km 4th on Wadwan Narbal road | Budgam | 462.26 | 117.194
376 | LUP1508 | Construction of Kremshore Dreygam and Dreygam Banderpora road | Budgam | 300.45 | 269.733 | Completed
377 | LUP1509 | Construction of inner links of Village Suresh & Larkipora Khag | Budgam | 273.19 | 169.864 | Completed
378 | LUP1510 | Construction of Budran link road in Pendobooni | Budgam | 159.69 | 47.728
379 | LUP1511 | Construction of Kathwar Check Kathwar road Kulbagh Tilumpora and allied links | Budgam | 303.05 | 198.792
380 | LUP1512 | Const. of link road from Basiyara to Bade De Paili and extn. Upto Panjpeer , Bua Datti Temple and Raja Mandlik Dev Sthan | Jammu | 133.5 | 60.84
381 | LUP1513 | Up-gradation of Dori Degair Road from Single Lane to Double Lane | Jammu | 291 | 229.194 | Completed
382 | LUP1514 | Imp/Up-gradation of Main babliana road form Rajiv Gandhi Hospital to Peer Baba at Gangyal includng Barsati Nallah Babliana | Jammu | 204.5 | 29.601
383 | LUP1515 | Roads in Sainik Colony | Jammu | 383.91 | 344.682 | Completed
384 | LUP1516 | Const of Road from Bathindi to Ratti Sarari Vai Bermini | Jammu | 197.22 | 140.32 | Completed
385 | LUP1517 | Const.of Road from Jarai Bhagthalli Road Km 2nd to Kathua Jarai road Chamble Da bhag D-1 Canal incl. main Jarai Road | Kathua | 364.5 | 25.56
386 | LUP1518 | imptt./upgradation of road from Aghar Jitto(Didi) to Garan Length 2 kms | Reasi | 92.01 | 25.278
387 | LUP1519 | Const of Road from Aghar Jitto to Pangatha | Reasi | 87.5 | 65.798 | Completed
388 | LUP1520 | Const of 40 mtr span steel foot bridge over Junnie Nallah Moori | Reasi | 56.26 | 50.609 | Completed
389 | LUP1521 | Upgrd of Gadwani Jaibal incld. C.R.Pora road | Kulgam | 145.1 | 102.107 | Completed
390 | LUP1522 | Constr.of Double Storeyed City Retreat Kutbal Kulgam | Kulgam | 107.24 | 52.51
391 | LUP1523 | Construction of Dak Bunglow at Handwara | Kupwara | 159.9 | 0
392 | LUP1524 | Construction/upgrd of Bakhihaker Shaloora road | Kupwara | 597.31 | 82.39
393 | LUP1525 | Upgrd of Kandi Sadhu Ganga road | Kupwara | 245.77 | 142.051 | Completed
394 | LUP1526 | Upgrd of Damhal Larve Narbal road with allied links | Pulwama | 261.88 | 221.336 | Completed
395 | LUP1527 | Widening/upgrd of Pulwama to Waibugh road incld. Ashmandar Murren link | Pulwama | 450.06 | 111.166
396 | LUP1528 | Strengthening/upgrd of Pahoo Chakpora road incld. Narbal Hakripora road, allied links & Pahoo Dogam road | Pulwama | 299.09 | 162.962 | Completed
397 | LUP1529 | Upgrd of Wagum to Uricharsoo and Prichoo Wagum road with allied links via Degree College | Pulwama | 347.43 | 241.233 | Completed
398 | LUP1530 | Constr of 1x15 mtr span plate girder Bridge at Sheikh Mohalla Hari Tral | Pulwama | 115.75 | 38.457
399 | LUP1531 | Strengthening/upgrd of roads near Ziyarat Sharief Awantipora incld. Storm Water Drain | Pulwama | 288.08 | 138.651 | Completed
400 | LUP1532 | Const. of Road from Manda to Koyali | Rajouri | 285.9 | 111.119
401 | LUP1533 | Const. of Road from Reasi at Kayala L-3.90 kms | Reasi | 215.65 | 126.032 | Completed
402 | LUP1534 | Const of road from Dera Baba to Bamyal via Kanji | Reasi | 760.5 | 509.424
403 | LUP1535 | Const of 21.00 Mtr C/C Span Motorable deck type Plate Girder Bridge over Nallah Tukson on Bagga Gulabgarh Road | Reasi | 37.2 | 14.328 | Completed
404 | LUP1536 | Const. of road from Gura Charala to Sadoti Block Pouni | Reasi | 381.5 | 98.647
405 | LUP1537 | Construction of Ransoo to Kotla Road | Reasi | 371.55 | 208.023 | Completed
406 | LUP1538 | Const. of Road From Sungri to Bagudass (Missing Link) L 0.70 kms | Reasi | 142.54 | 65.349 | Completed
407 | LUP1539 | Const. of Road from Matlote to Pattian in Km 7th and Km 8th 0.1000 L=2 km | Reasi | 107.42 | 65.083
408 | LUP1540 | Const. of Road from Karwa to Kotli Road L=5 km | Reasi | 280.78 | 231.412 | Completed
409 | LUP1541 | Const. of Road from Sounchal Gali to Ans Nallah | Reasi | 179.07 | 34.362
410 | LUP1542 | 120 m span steel plate girder bridge on River Ballani & 30 mtr span steel girder Bridge over Balganga Nallah near Village Kanjli, Reasi | Reasi | 266.9 | 188.579 | Completed
411 | LUP1543 | Const.of Chak Salarian to Raraian Road | Samba | 100.4 | 56.214 | Completed
412 | LUP1544 | Const of link road from Rangoor Camp to Chajwal (L=4 kms) | Samba | 201.38 | 50.58
413 | LUP1545 | Const. of link road of Baba Chamlial | Samba | 25.21 | 22.448 | Completed
414 | LUP1546 | Imp. Of link road to Mohalla Chouhana(Old) | Samba | 110.06 | 22.001
415 | LUP1547 | Const of link road from main road to Temple at patti incl. link road to Jogi Mohalla Smailpur | Samba | 195.7 | 67.441 | Completed
416 | LUP1548 | Samba Pangdour road incl. link road to Katli | Samba | 165.33 | 143.901 | Completed
417 | LUP1549 | upgradation of link road to Kamala and Radha Swami Ashram | Samba | 105.8 | 54.346 | Completed
418 | LUP1550 | Up-gradation of link road to Bari Khad | Samba | 107.84 | 33.284
419 | LUP1551 | Const of link road from Dassal to Baba Brahmdev | Samba | 161.68 | 29.34
420 | LUP1552 | Const. of link road from smailpur to Patti Kheddian road including link road to Sanarki Plotta and Kotli | Samba | 192.5 | 102.864 | Completed
421 | LUP1553 | Imp. Of link road from village Trindi (Sarva) | Samba | 87.07 | 46.302 | Completed
422 | LUP1554 | Imptt. Upgdtt. Of Ghagwal to Rajpura Road | Samba | 144.5 | 114.447 | Completed
423 | LUP1555 | Const of road from Naran to Muthi Kalan | Samba | 54.7 | 23.156
424 | LUP1556 | Const.of link road to Baba Sidh Gorian (Goran Chak) | Samba | 30.1 | 26.685 | Completed
425 | LUP1557 | Upgrd of Mohanpora-Khurampora road incld. Mohanpora Ladi, Imam Sahib Kenigam via Kadgam and Imam Sahib Chiterwash road | Shopian | 185.61 | 121.688
426 | LUP1558 | Upgrd of Ranipora Khasipora | Shopian | 188.64 | 67.746
427 | LUP1559 | Upgrd of Narwaw to Reshnagri Kanjiullar Gadipora road | Shopian | 100 | 86.388 | Completed
428 | LUP1560 | Const . Of Road from Bhati to Malli Via Jasarkote | Udhampur | 345.42 | 90.364 | Completed
429 | LUP1561 | Const of Road from Chountra Mata to Dheeran (Take off point From Marta) km 14th to Km 19th (Length 6 km) | Udhampur | 866.88 | 400.234
430 | LUP1562 | Road from Sui to Bassian via Barigarh L-1 kms | Udhampur | 200.97 | 92.916 | Completed
431 | LUP1563 | Road from Kaghote to Dalsar L-11.60 kms | Udhampur | 869.23 | 266.103
432 | LUP1564 | Thalora to Pinger Road Km 8th to 14th | Udhampur | 775.86 | 183.816
433 | LUP1565 | Const.of Road from Salmeri to Balli Towards Krimchi Panchyat Sial jattan (Udhampur) incl. link road to Tope | Udhampur | 197.02 | 111.661 | Completed
434 | LUP1566 | imp. /up-graation of Phalata to Assi upto seen Brahmna via Rajpura (L-5 kms ) | Udhampur | 882.8 | 124.859
435 | LUP1567 | Ice Factory to Village Chakhar | Udhampur | 379.67 | 193.479
436 | LUP1568 | Imp. /up-graation of Tikri Chanas Road | Udhampur | 383.59 | 124.119
437 | LUP1569 | Road from Battal Ballian Bye pass Nh 44 to Roun Domail L=5.25 kms | Udhampur | 370.07 | 229.763 | Completed
438 | LUP1570 | Cherri Sial to Kawa road | Udhampur | 140 | 77.093 | Completed
439 | LUP1843 | Upgrd of interior roads at Watnard | Anantnag | 141.46 | 0
440 | LUP1844 | Constr.of Khull Brah Kralgund road | Anantnag | 111.06 | 60.485 | Completed
441 | LUP1845 | Constr.of Brah Dawoodpora road | Anantnag | 114.1 | 51.121 | Completed
442 | LUP1846 | Constr of Arhama Badasgam road | Anantnag | 71.63 | 60.547 | Completed
443 | LUP1847 | Construction/Upgradation of waltangoo Vasakanag road | Anantnag | 190.51 | 24.939
444 | LUP1848 | Upgradation of Mandipora Changoo Chinar links | Anantnag | 299.19 | 70.623
445 | LUP1849 | Construction of road from Khayar to Boinar via Lawaypora at Bandipora | Bandipora | 59.61 | 27.994
446 | LUP1850 | Upgradation of Kehnoosa Rajpora road | Bandipora | 409.06 | 81.411
447 | LUP1851 | Completion of balance works for Construction/ upgradation of Nawa to Runda road | Baramulla | 222.17 | 125.442
448 | LUP1852 | Cosnt of Road from KM 4th Doda Bhaderwah Road to Nai Dangri | Doda | 227.04 | 57.501
449 | LUP1853 | Const. of Chakka to Upper Dandi link road KM 1st RD (0-1000) District Doda Length 1kms | Doda | 45.5 | 37.455 | Completed
450 | LUP1854 | Const. and upgradatin of Shiva Allalbani Link Road from Km 6th to 10th | Doda | 333.96 | 50.922
451 | LUP1855 | Const. of Parmaz Link Road | Doda | 386.73 | 75.654
452 | LUP1856 | Const. of Road from National Highway to Sharerna via Shaja | Doda | 713.91 | 274.83
453 | LUP1857 | Upgradation of Baltal Dumail road by way of Pre-Cast Blocks ( For Shri Amarnath Ji Yatra) | Ganderbal | 794.85 | 404.163
454 | LUP1858 | Construction of 1x20 Mtr span single lane plate girder bridge including Development of road approaches at Bala Sathun on Tulmulla Wakoora road | Ganderbal | 141.42 | 123.354 | Completed
455 | LUP1859 | Const. of internal roads in Gangyal Ekta Vihar Kunjwani and Shanti Nagar, Jammu | Jammu | 315.75 | 199.548
456 | LUP1860 | Roads in Bathindi area including 4 nos. bridges on bathindi Nallah(02 on upstream and 2 no. down stream of Makkah Masjid) | Jammu | 220.26 | 162.487
457 | LUP1861 | Roads from NHI to Kiryani Talab to Dongian via Kargil colony | Jammu | 370.2 | 128.052
458 | LUP1862 | Const. of various links/approach road to Jeevan Nagar Murallian Miran Sahib road Jammu | Jammu | 293.79 | 259.018 | Completed
459 | LUP1863 | Roads in Chowadi near Rauli Talab | Jammu | 65 | 30.245
460 | LUP1864 | Roads in Digiana | Jammu | 236.03 | 209.802 | Completed
461 | LUP1865 | Const. of road form Fatwal to chumbian Panditian L=1 kms | Jammu | 47.6 | 42.804 | Completed
462 | LUP1866 | Imp./Upgradation of link road to Bishnah Ashram W. No 02 upto to KC Morh Bishnah L=1.20 kms | Jammu | 86.8 | 74.25 | Completed
463 | LUP1867 | Const. of Road from Nandpur to Pindi Charkan Via Duali Khui in Km 3rd Rd 800 -1000 km 4th &5th L=22 mtrs | Jammu | 81 | 66.488 | Completed
464 | LUP1868 | Const. of Road from Palli to Chak Avtara L=3 kms | Jammu | 99.8 | 86.522 | Completed
465 | LUP1869 | Const. of Road at Sarore along Distributory No. 3 L=2.40 kms | Jammu | 83.24 | 72.09 | Completed
466 | LUP1870 | Const. of link road from Sai Khurd to Sardari Camp (Birdhipur Bana) L=2 kms | Jammu | 86.7 | 56.592 | Completed
467 | LUP1871 | Cosnt. Of Road from Chak Keema to Karyal L=2 kms | Jammu | 54.86 | 47.943 | Completed
468 | LUP1872 | Const. of link road from Kalapul Satrayian to Chowala Fattu Chak L=1.15 kms | Jammu | 85.2 | 47.695 | Completed
469 | LUP1873 | Const. of Road form Mana to Shamshan Ghat L=2.10 kms | Jammu | 116.5 | 66.807 | Completed
470 | LUP1874 | Const. of Road from Talli Morh to Darsopur Ganda L=1.50 kms | Jammu | 70.5 | 37.157 | Completed
471 | LUP1875 | Const. of Road from Gondla to Shamshan Ghat (Village Agwan) L=1.75 kms | Jammu | 100.1 | 51.129 | Completed
472 | LUP1876 | Const. of link road from Baspur to Samka (Suchetgarh Constituency L=1.80 kms | Jammu | 123.35 | 75.996 | Completed
473 | LUP1877 | Imp/ Upgradation of link road Nari Khaper L=1.10 kms | Jammu | 50 | 24.759 | Completed
474 | LUP1878 | Const. of Internal links at Dhyansar L=2.50 kms | Jammu | 87.1 | 72.54 | Completed
475 | LUP1879 | Imp/ Upgradation of Road from Krishna Nagar to Gazian (Muralian Upto Shamshan Ghat ) L=1 kms | Jammu | 41.85 | 29.822 | Completed
476 | LUP1880 | Const. of Road from Salehar to Chak Majra L- 3 kms | Jammu | 115.85 | 99.747 | Completed
477 | LUP1881 | Const. of Road from Kothi Morh to Lala Chak Road at RD 2-450 on Bari Brahmana Bishnah Road L=1.90 kms | Jammu | 69.5 | 62.442 | Completed
478 | LUP1882 | Const. of link road from Biaspur Parlah to Talad road L=1.40 kms | Jammu | 118.25 | 79.435 | Completed
479 | LUP1883 | Const./ Extension of Road from Kotli Charkan to Byepass Road Bishnah via Dhinday Khurd including links L-2 kms | Jammu | 126.55 | 87.692 | Completed
480 | LUP1884 | Const. of Road from Tanda to Chowala Fattu Chak L 3 kms | Jammu | 132.55 | 109.972 | Completed
481 | LUP1885 | Const. of link road from Haripur to Dangra L 2.50 kms | Jammu | 202.7 | 20.79
482 | LUP1886 | Imp./upgradation and strengthening of Road from Pindi Sarochan to Garore Nallah L=0.96 kms | Jammu | 95 | 58.243 | Completed
483 | LUP1887 | Const. o Road from Deoli Preet Nagar to Shamshan Ghat L=1.80 kms | Jammu | 66.35 | 40.923 | Completed
484 | LUP1888 | Const. of link road from Devigarh to Jobowal L 2.20 kms | Jammu | 114.75 | 90.657 | Completed
485 | LUP1889 | Const. of Road from Makhanpur to Pasgal L 2.50 kms | Jammu | 97 | 85.446 | Completed
486 | LUP1890 | Const. of Road from Palli to Bhatyari via Kanhal L 3 kms | Jammu | 92.6 | 79.416 | Completed
487 | LUP1891 | Const. of Lanes opposite Rajiv Gandhi Hospital Gangyal from House to Sh Balram Singh to Biscuit Factory Jammu | Jammu | 198.1 | 0
488 | LUP1892 | Imp./ Upgradation of Road from Sector F Sainik Colony to Lower Chowadhi | Jammu | 335.5 | 0
489 | LUP1893 | Const. of road including Bridge at Nagrota Migrant Camp to Jagti including Dhammi road | Jammu | 178.7 | 94.056
490 | LUP1894 | Const. of Road from Kanah Chargal to Dhoon | Jammu | 348.65 | 71.667
491 | LUP1895 | Const. of Road from passenger Shed Badsoo to Upper Badsoo | Jammu | 830.7 | 0
492 | LUP1896 | Imp./ Upgradation of Road from Jagti to Tanda | Jammu | 589.18 | 348.372
493 | LUP1897 | Const. of Road from Jakhari (Peer Baba Ji) to Seoura | Jammu | 214.95 | 87.93
494 | LUP1898 | Const. of Road from Nandani to Tara upto Madrasa incl. Vented Causeway | Jammu | 423.17 | 64.971
495 | LUP1899 | Const of Tharakalyal to Alna Trapper Uchapind and Link road Grave Yard to Pongran via Bhudal | Kathua | 93.06 | 25.941
496 | LUP1900 | Const. of Sulari link Road | Kathua | 126.7 | 0
497 | LUP1901 | Const.of Bhaddu to Phongal Road | Kathua | 152.36 | 80.598 | Completed
498 | LUP1902 | Const. of Lakhari to Kunoo Road | Kathua | 147 | 35.301
499 | LUP1903 | Const. of Circular Road to Thantoo Kalai | Kathua | 79.36 | 58.805 | Completed
500 | LUP1904 | Const. of Road from Circular Road from Barota via Mohallah Galleria | Kathua | 174 | 17.464
501 | LUP1905 | Const. of link road from Dhar road to Tarkhan Mohallah Sarmal Mohallah & SC Mohallah in village Pallan | Kathua | 84.5 | 31.445
502 | LUP1906 | Const. of Tilla Bather Road | Kathua | 374.93 | 24.827
503 | LUP1907 | Const. of Marta Nagrota to Pantair via Bari and Khlow road | Kathua | 248.97 | 217.75 | Completed
504 | LUP1908 | Const. of link road from Dhar Road to Mohallah Lunia | Kathua | 289.11 | 34.329
505 | LUP1909 | Const. of 83 mtr causeway on Jandore & Brow via Hote km 5th Rd 850-950 connecting Hatli Manu road. | Kathua | 321.7 | 0
506 | LUP1910 | Imp./Upgradation of Parnalla Seri Mooni Plail Banhore road. | Kathua | 580.74 | 369.925 | Completed
507 | LUP1911 | Double Lanning of Road from National Highway to Sunjwan | Kathua | 241.32 | 193.653
508 | LUP1912 | Const. of Ladoli Link road Billawar incl. Mangloor to Ladoli via Jambal Dode | Kathua | 529.36 | 287.555
509 | LUP1913 | Const. of Road from Lokhli PHE Tube Well via Prillan De Maina to Jardian De Talaian (Bakerwals Basti) | Kathua | 298.4 | 39.798
510 | LUP1914 | Const. of Road from Dungara to Pargan | Kathua | 114.21 | 29.326
511 | LUP1915 | 132 mtr span motorable Bridge over Nallah Bheeni including approaches at Beril in Billawar | Kathua | 628.5 | 0
512 | LUP1917 | Approach Road to Polytechnic College Cherhar | Kishtwar | 64.98 | 36.059
513 | LUP1918 | Const. of Atholi link road and its extension upto Gossi | Kishtwar | 151.05 | 66.921
514 | LUP1919 | Const. of Parking Places at Kishtwar Town on NH 244 | Kishtwar | 134.64 | 113.249 | Completed
515 | LUP1920 | Const. of Thal Kwath Beyond km 4th | Kishtwar | 411.16 | 0
516 | LUP1921 | Const.of Foot bridge over Galwanpora Nallah near Thana | Kishtwar | 63.55 | 0
517 | LUP1923 | Upgradation of Langate Hajin Takiya road including Langate Panditpora Shailnar link | Kupwara | 329.39 | 0 | Completed
518 | LUP1924 | Upgradation of Geeripora Tumpora road | Kupwara | 271.02 | 143.374 | Completed
519 | LUP1925 | Construction/Upgradation of Challagund Gundisana road | Kupwara | 496.91 | 260.143
520 | LUP1926 | Constructionof 1x30 Mtr span steel girder bridge at Gabra ( Mudiyan) including approaches road | Kupwara | 202.91 | 22.385
521 | LUP1927 | Construction of link road from Upper Tadda to Qazi Mohalal | Kupwara | 198 | 129.974
522 | LUP1928 | Construction of Kona Gabra Choorkungi road | Kupwara | 357.21 | 85.456
523 | LUP1929 | Construction of 2x25 Mtr double lane steel girder bridge instead of construction of 1x45 Mtr span double lane steel girder bridge including strengthening of existing bridge over nallah Kalarooch in Km 6th of Kupwara Sogam road at Khumriyal | Kupwara | 152.48 | 93.887 | Completed
524 | LUP1930 | Construction of road from Hathi Matha to Devi mang | Poonch | 144.7 | 124.981 | Completed
525 | LUP1931 | Const. of Road from Dharmsal to Kanthole | Rajouri | 708.7 | 159.327
526 | LUP1932 | Garan Phalli Road | Rajouri | 541 | 165.539
527 | LUP1933 | Const. of VIP suit in PWD Dak Bungalow at Koteranka | Rajouri | 91.83 | 75.015 | Completed
528 | LUP1934 | Const. of Road from Dhandkote to Sokargali | Rajouri | 420.6 | 92.501
529 | LUP1935 | Const. of Ujhan Darhal Kandi Road | Rajouri | 502.64 | 340.407 | Completed
530 | LUP1936 | Patyari to Domel Via Thangiote | Rajouri | 297.56 | 99.69
531 | LUP1937 | Panjnara Phalli Road | Rajouri | 235 | 0
532 | LUP1938 | Link road from Kotedhara Bridge to Sanga Sahib Ziarat | Rajouri | 743.92 | 139.428
533 | LUP1939 | Construction of road from Charyala to chak sarkari via Daryala | Rajouri | 251 | 121.192
534 | LUP1940 | Const of road from katha Bajaran to Saim samat | Rajouri | 395.84 | 95.418
535 | LUP1941 | Const. of Road from Govt Medical College Rajouri to Baba Gulam Shah Badshah Unviversity Rajouri connecting APJ Abdul Kalam Botinical Park | Rajouri | 860 | 266.031
536 | LUP1942 | Const. Of Single Lane Motorable Bridge adjacent to Abdulla Bridge Rajouri | Rajouri | 620 | 85.298
537 | LUP1943 | Const / Widening of Road from Rajouri to BGSB University | Rajouri | 2670.05 | 0
538 | LUP1944 | Const of road from Abdullah Bridge to Court Complex via Anandpur Ashram/Masjid Sharief | Rajouri | 578.1 | 95.515
539 | LUP1945 | Construction of 40 mtr span single lane steel grider motorable bridge including approaches at Tasyala Panjgrain.(distt. Plan) | Rajouri | 194.74 | 86.881
540 | LUP1947 | Const. of Road from Dachan to Ind Via Sasal Road | Ramban | 167.56 | 58.743
541 | LUP1948 | Const. of Hewaga Neel Road | Ramban | 60.4 | 38.97 | Completed
542 | LUP1949 | Sangaldan Kanthan Road | Ramban | 99.11 | 43.091 | Completed
543 | LUP1950 | Const.of Bus Stand at Ukhral | Ramban | 170 | 112.4 | Completed
544 | LUP1951 | Banihal Lamber Road | Ramban | 266.78 | 179.279 | Completed
545 | LUP1952 | Const. of 50 mtr span Motorable Bridge over Bishlari Nallah & Approach Road to Degree College Banihal | Ramban | 169 | 95.4 | Completed
546 | LUP1953 | Imp./Upgradation of Shiv Khori track at ransoo (L=3 kms) | Reasi | 236.9 | 112.784
547 | LUP1954 | Construction of link road from Suchani to Khoo da Talab | Samba | 235.01 | 77.582
548 | LUP1955 | Widening/04-lanning of Bemina Budgam road from Tatoo Ground crossing to Bemina Byepass Crossing ( Phase-I) | Srinagar | 869.57 | 0
549 | LUP1956 | Const. / upgradation of Road from CEO office Udhampur to Mohalla Dhandyal | Udhampur | 70.47 | 35.7 | Completed
550 | LUP1957 | Const. of Road to Village Upper Badole via PTC Nalanda Academy Udhampur | Udhampur | 175.65 | 102.91 | Completed
551 | LUP1958 | Imp./ Upgradation of Pattangarh to Matloa Road | Udhampur | 138.7 | 0
552 | LUP2491 | Upgradation of Handori Seethrseeran Nagbal and Sethseeran Dandmooh road | Baramulla | 494 | 26.05
553 | LUP2492 | Const. of approach road (double lane) for Govt. medical College doda(ghat) km 1st RD 0-750 | Doda | 413.5 | 193.103
554 | LUP2493 | Const. of road from Udhyanpur to Rai Sarwala | Doda | 240 | 53.781
555 | LUP2494 | Const. of road from Dhara to Shirshi | Doda | 281 | 49.914
556 | LUP2495 | Const. of Ghat badroon link road (from HSS Ghat-Medical college) | Doda | 173 | 37.485
557 | LUP2496 | Const. of link road from Beer Bagh to Kanhal via Shiva | Doda | 891 | 109.599
558 | LUP2497 | Const. of link road from Auoti Massri to Karlie via Thelroo Jagrote (take off point from PMGSY road km 5th RD(450) Pranoo to Massri) Distt. Doda length 6 kms | Doda | 974 | 207
559 | LUP2498 | Construction of proposed Community Hall/Centre manigam Ganderbal | Ganderbal | 152.11 | 58.824
560 | LUP2499 | Imp./upgd. of roads in Shastri Nagar including drain, metalling in sector 1 & 2 at Sanjay Nagar. | Jammu | 398.06 | 344.088 | Completed
561 | LUP2500 | const. of link road from Tanta to Devigol via Sarpan Patnazi bunjwah L=3kms | Kishtwar | 414.43 | 50.607
562 | LUP2502 | Const. of road from Manjakote to hayatpura | Rajouri | 410 | 157.121
563 | LUP2503 | Const. of Kotedhar Peeri road (balance length 4.50 kms) | Rajouri | 450.23 | 173.417
564 | LUP2504 | Const. of road from Bajabain thichka road to Ghai saleri | Rajouri | 279 | 121.668
565 | LUP2505 | Const. of road from Shahdra Sharief to Bari Behak | Rajouri | 767.3 | 109.601
566 | LUP2506 | Const. of 3x42 mtr PSC girder double lane Noorjahan bridge at Qamarwari, Srinagar | Srinagar | 258.61 | 74.082
567 | LUP2515 | Const. of road from Palli morh to Bohra Kathua (Teda) | Kathua | 501.97 | 90.432
568 | LUP2516 | Jasyar to Tradal road | Kathua | 223.52 | 52.005
569 | LUP2517 | Const. of link road to Chak Rijju Railway Station road | Kathua | 39 | 34.011 | Completed
570 | LUP2518 | Const. link road to village thein from Basoli road | Kathua | 41.8 | 32.238 | Completed
571 | LUP2519 | Const. of sallan link road | Kathua | 67.79 | 58.473 | Completed
572 | LUP2520 | Const. of link road from old Panchyat Ghar to Muslim mohalla Brow -Andhoi morha Rajpur | Kathua | 202.62 | 33.863
573 | LUP2521 | Const. of link road from Marh Gajnsoo road | Jammu | 198.5 | 0
574 | LUP2522 | Const. of road from Gajansoo bus stand and other allied links in Marh block | Jammu | 159 | 35.978
575 | LUP2523 | Gajnsoo bazar to Rathua on Lohri Chak road | Jammu | 68.3 | 20.43
576 | LUP2524 | Const. of road from Shama chak to chak Makani village | Jammu | 96 | 44.687
577 | LUP2525 | Const. of link road from Pannu the Hatti road to (Sualpur road) to H/O Sh. Ram lal Sharma marh | Jammu | 72.26 | 51.05 | Completed
578 | LUP2526 | Const. of road from dub soodan to rakh kharoon | Jammu | 58.96 | 40.365 | Completed
579 | LUP2527 | Widening of Mishriwala Jhiri road upto double lane specification | Jammu | 587.9 | 81.948
580 | LUP2528 | Const. of road from Ganeshu chak to Karnale chak upto Shamshan ghat | Jammu | 109.54 | 87.775 | Completed
581 | LUP2529 | Imp./upgd. Of Revenue complex road | Jammu | 841.29 | 91.413
582 | LUP2530 | Imp./upgd. Of road from machine Domana to Chibbe Chak in Marh block | Jammu | 115 | 43.449 | Completed
583 | LUP2531 | Const. of road by way of metalling and premixing Phallian to chak desa singh | Jammu | 204 | 97.776
584 | LUP2562 | Construction of Seer Numbal bridge incl approaches on either side | Anantnag | 569.08 | 0
585 | LUP2563 | Upgradation of Verinag Town | Anantnag | 437.31 | 0
586 | LUP2564 | Upgradation of Dangiwacha Yarbugh road incl Dangiwacha Deeddarpora road | Baramulla | 304.76 | 0
587 | LUP2565 | Compleation of Alamdar road from Hapatnar to Chariarisharief | Budgam | 224.52 | 0
588 | LUP2566 | Construction of 1x36 Mtr span steel girder bridge at Babapora Falchal | Budgam | 215.11 | 0
589 | LUP2567 | Construction of road from Sogam to Ranger, Sogam to Kathairgund and Sogam to Gundi Rajab | Budgam | 207.88 | 0
590 | LUP2568 | Upgradation of road from Chararisharief to Batpora Haproo | Budgam | 372.95 | 0
591 | LUP2569 | Upgradation/ Construction of Hayatpora Wahibugh – Kralcheck – Wadipora Wanpora Qazipora Newa road | Budgam | 116.71 | 0
592 | LUP2570 | Upgradation of Omporea Hyderpora via Narkar Road with allied links | Budgam | 574.58 | 0
593 | LUP2571 | Const. / Upgradation of Bijarni to Lal Draman Road | Doda | 748 | 0
594 | LUP2572 | Const. of Dhara Gundna Road Km 21st to 26th | Doda | 242.23 | 0
595 | LUP2573 | Const. and Upgradation of road from Dongian to Jatki Panjpeer | Jammu | 178.37 | 0
596 | LUP2574 | Const. of Lanes near Divya College Kanshipur Ashram road at Lower Gadigarh Jammu including protection work on adjoining road to Divya college | Jammu | 177.54 | 0
597 | LUP2575 | Const. of link road from Rakna to Hatana via upper Razna | Kishtwar | 209.02 | 0
598 | LUP2576 | Construction of Behnipora Butshungi road including Sutkoji Lachampora road ( Phase – 1st ) | Kupwara | 481.38 | 0
599 | LUP2577 | Construction of Proposed 8x25 Mtr foot bridge at Khan Tulwari Langate over nallah Mawar at Handwara | Kupwara | 774.79 | 0
600 | LUP2578 | Const.of Road from Hullar Behra to Dhakki including Kasab L 5 kms | Poonch | 358 | 0
601 | LUP2579 | Const.of 55 m span M/able Bridge over Pandhali Nallah at Dhundak | Poonch | 147.39 | 0
602 | LUP2580 | Construction of road from Balnoi to Tatapani LOC including Const. of Vented Causeway in Bugheli Nallah at Mankote Length = 6Kms | Poonch | 336.66 | 0
603 | LUP2581 | Const. of 135 mtr span steel M/Bridge single lane including 102 mtr wide walk way on either side for linear way of 135 mtr over Rajouri Tawi at Kallar Potha | Rajouri | 772.15 | 93.636
604 | LUP2582 | Const. of road from Bhawani to Laroka | Rajouri | 485.2 | 0
605 | LUP2583 | Const. of Road from Gurdhan to Gurdhanpain | Rajouri | 268.7 | 0
606 | LUP2584 | Const.of Road from Saleri to Saroola | Rajouri | 243.25 | 0
607 | LUP2585 | Const.of 140 mtr span Motorable Bridge over Rajouri Tawi River to Dhanwan Chakli including approaches | Rajouri | 285.38 | 0
608 | LUP2586 | Road from Patrari to Dandesar Bala | Rajouri | 555.7 | 0
609 | LUP2587 | Sorha Bhattian to Badakana (Ralakote) L=3 kms | Rajouri | 143.4 | 0
610 | LUP2588 | Const of link road including approaches to Motorable bridge Tasyala Panjgrain | Rajouri | 281 | 0
611 | LUP2589 | Const. Of Road From Mobil Morh to Tilkathi via Akhorola L 5 kms | Reasi | 791.25 | 0
612 | LUP2590 | Const. Of Road from Sarh to Lanana | Reasi | 439.02 | 0
613 | LUP2591 | Const. of Road from Dhamini to Dewal L 7 kms | Reasi | 609.27 | 0
614 | LUP2592 | Imp./ Upgradation of Dharmari Thuroo road L 5.50 kms | Reasi | 383.2 | 0
615 | LUP2593 | Imptt./ Upgradation of Bansa Muttal Road L 7 km | Reasi | 391.51 | 0
616 | LUP2594 | Strengthening/Upgradation of Shadab Karewa Manloo road including launching of baily bridges over Nallah Rambiara Dachnu Heerpora and Construction of road either side of baily bridges | Shopian | 271.93 | 0
617 | LUP2595 | Strengthening/Widening Construction and upgradation of Shopian Bijbehara road (From Sangloo Chowk to Habdipora) Km 27.50th to 30th | Shopian | 409.96 | 0
618 | LUP2596 | Development of various link roads in Qammerwari/ Qamerabad including Parimpora | Srinagar | 534.1 | 0
619 | LUP2597 | Improvement/upgradation of Owantabhawan Ellahibagh grid station road via Hamzah Colony with allied roads | Srinagar | 289.49 | 134.476
620 | LUP2598 | Imptt/ Upgrd of Shuhama Khimber road including allied links | Srinagar | 282.13 | 0
621 | LUP2599 | Upgradation of Colony Roads of Syed fazalabad, Sir Syed Colony, Shadab Colony, Usmania Colony, Iqbal Colony roads at Doonibagh Ellahibagh Pandach | Srinagar | 539.12 | 247.628
622 | LUP2718 | Const of road from Rehan to Dhar Sakri via Damote (Peeri) | Rajouri | 889.7 | 0